Source: R00 Chairman

Subject: R00 workplan

S1 R00 work plan, rev1

| Week 18 | 3.-5. May | S1 R00 ad hoc Target: Completion of TR 22.976 and distribution for comments to other WGs. |
| --- | --- | --- |
| Week 19 | 12 May | S1 TR presented to S2 R00 |
| Week 20 |  | Email review of comments (on the need basis when comments are received). |
| Week 21 |  |  |
| Week 22 | 31. May | Proposal on S1 R00 task plan, i.e. How the TR is transferred to CRs and possibly to new TS. Identification of relevant rapporteurs. AP. Drafted and emailed by Kokkola/Cataldo. |
| Week 23 | 8. June (14:00-17:00 GMT) | Phone conference Target: Review of task plan. If TR is changed (e.g. based on comments from other WGs). Final version is put on email approval. |
| Week 24 |  |  |
| Week 25 |  |  |
| Week 26 | 26. - 28. June | TSG-SA#8, TR 22.976 for approval |
| Week 27 | 3.-7. July | R00 ad hoc Target: Preparation and review of CRs. |
| Week 28 |  |  |
| Week 29 | 17.-21. July | S1 Plenary Denmark (incl 1½ day R00 ad hoc) Target: Completion and approval of R00 CRs. |
| … |  |  |
| Week 46 | 13.-17. November | S1 Plenary (US) |