## Slide 1: SA1 Rel-18 Time plan

## Slide 2
 | SA1#93 | SA1#94 | SA1#95 | SA1#96
MMTELin5G |  |  |  | 
SACI_MCS |  |  |  | 
RAILSS |  |  |  | 
AMMT |  |  |  | 
5GET |  |  |  | 
EASNS |  |  |  | 
OffNetRail |  |  |  | 
5TRS |  |  |  | 
5GSEI |  |  |  | 
Ranging |  |  |  | 
Resident |  |  |  | 
PIN |  |  |  | 
PALS |  |  |  | 
VMR |  |  |  | 
eFRMCS |  |  |  | 
TACMM |  |  |  | 
SID
WID

## Slide 3: FS_MMTELin5G Planning
Rapporteur: Yan Di
Current completion: 40%
Study carried out in TR: <22.873>
Next steps for TR:
  TR 70% at: SA1#93
  TR 100% at: SA1#94
Next steps after TR:
  This TR will produce CR(s) to 22.173
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#94/SA1#95/SA1#96
Notes: 1

## Slide 4: FS_SACI_MCS Planning
Rapporteur: Jens Toobe
Current completion: 20%
Study carried out in TR: 22.881
Next steps for TR:
  TR 80% at: SA1#94
  TR 100 % at: SA1#95
Next steps after TR:
  This TR will produce CR(s)
  CR(s) to be finalised at
    CRs until: SA1#96
Notes: 1

## Slide 5: FS_RAILSS Planning

## Slide 6: FS_AMMT Planning

## Slide 7: 5GET Planning
Rapporteur: Cyril Michel -> Toon Norp
Current completion: 40%
Study carried out in TR: 22.916
Next steps for TR:
  TR 80% at: SA1#95
  TR 100 % at: SA1#96
Next steps after TR:
  22.916 is a guidelines TR and will not create any follow on normative work
Notes: 1

## Slide 8: FS_EASNS Planning
Rapporteur: SungDuck Chun
Current completion: 60
Study carried out in TR: 22.835
Next steps for TR:
  TR 80% at: SA1#93
  TR 100 % at: SA1#94
Next steps after TR:
  This TR will produce CR(s) to 22.261
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#94/SA1#95
Notes: 1

## Slide 9: FS_OffNetRail Planning
Rapporteur: <Guillaume Gach>
Current completion: <30%> (before SA1#93e)
Study carried out in TR: <22.990>
Next steps for TR:
  TR 80% at: SA1#95>
  TR 100 % at: <SA1#96>
Next steps after TR:
  This TR will not produce CR(s) for Rel-18
Notes: 1

## Slide 10: FS_5TRS Planning
Rapporteur: Betsy Covell
Current completion: 75%
Study carried out in TR: 22.878
Next steps for TR:
  TR 100 % at: SA1#93/SA1#94
  Next steps after TR:
  This TR will produce CR(s) for TS 22.104 and 22.261
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#94/SA1#95
Notes: 1

## Slide 11: 5GSEI Planning
Rapporteur: Xu Xia, China Telecom
Current completion: 60%
Study carried out in TR: 22.867
Next steps for TR:
  TR 80% at: SA1#93
  TR 100 % at: SA1#94
Next steps after TR:
  This TR will produce a new TS, if necessary
  If new TS, TS to be:
    80% at: SA1#95
    100 % at: SA1#96
Notes: 1

## Slide 12: FS_Ranging Planning
Rapporteur: <Xiaowei, jiang>
Current completion: <80%>
Study carried out in TR: <22.855>
Next steps for TR:
  TR 100% at: <SA1#93>/<SA1#94>/<SA1#95>/<SA1#96>
Next steps after TR:
  This TR will produce CR(s)
  If CR(s), CR(s) to be finalised at
    CRs until: <SA1#93>/<SA1#94>/<SA1#95>/<SA1#96>
Notes: 1

## Slide 13: FS_Resident Planning
Rapporteur: Toon Norp (KPN)
Current completion: 50%
Study carried out in TR: 22. 858
Next steps for TR:
  TR 80% at: SA1#93
  TR 100 % at: SA1#94
Next steps after TR:
  This TR will produce a new TS (together with PIN) with some CRs to 22.261 (introducing the new TS)
  If new TS, TS to be:
    80% at: SA1#95
    100 % at: SA1#96
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#96 (introduction section in 22.261)
Notes: 1

## Slide 14: FS_PIN Planning
Rapporteur: Adrian Buckley (vivo Mobile Communications)
Current completion: 50%
Study carried out in TR: 22. 859
Next steps for TR:
  TR 80% at: SA1#93
  TR 100 % at: SA1#94
Next steps after TR:
  This TR will produce a new TS (together with RESIDENT) with some CRs to 22.261 (introducing the new TS)
  If new TS, TS to be:
    80% at: SA1#95
    100 % at: SA1#96
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#96 (introduction section in 22.261)
Notes: 1

## Slide 15: FS_PALS Planning
Rapporteur: Qualcomm
Current completion: 35%
Study carried out in TR: 22.844
Next steps for TR:
  TR 100% at: SA1#94
Next steps after TR:
  This TR will produce CR(s)
  If CR(s), CR(s) to be finalised at
    SA1#96
Notes: 1

## Slide 16: FS_VMR Planning
Rapporteur: Qualcomm
Current completion: 35%
Study carried out in TR: 22.839
Next steps for TR:
  TR 80% at: SA1#94
  TR 100 % at: SA1#95
Next steps after TR:
  This TR will produce CR(s)
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#96
Notes: 1

## Slide 17: FS_eFRMCS Planning
Rapporteur: <Guillaume Gach>
Current completion: <0%> (before SA1#93e)
Study carried out in TR: <22.989>
Next steps for TR:
  TR 80% at: <SA1#95>
  TR 100 % at: <SA1#96>
Next steps after TR:
  This TR will produce CR(s) (if necessary)
  If CR(s), CR(s) to be finalised at
    CRs until: <SA1#96>
Notes: 1

## Slide 18: FS_TACMM Planning
Rapporteur: Xiaonan Shi
Current completion: 0%
Study carried out in TR: 22.847
Next steps for TR:
  TR 30% at: SA1#93
  TR 60 % at: SA1#94
  TR 80 % at: SA1#95
  TR 100 % at: SA1#96
  Next steps after TR:
  This TR will produce CR(s) to TS22.261 and TS22.263
  If CR(s), CR(s) to be finalised at
    CRs until: SA1#96/ SA1#97/ SA1#98
Notes: 1