## Slide 1: FS_DualSteer Status Update Study on Upper layer traffic steering, switching and split over dual 3GPP access
Francesco Pica
Qualcomm
FS_DualSteer Rapporteur
3GPP TSG-SA WG1 Meeting #99e
Electronic Meeting, Aug 22 – Sep 1, 2022
Notes: 1

## Slide 2: FS_ DualSteer Progress
Progress made at this meeting
  Agreed TR skeleton and 6 Use cases
Study Item Completion: 30%
Controversial issues
  Terminology
    e.g. upper layer / above-RAN, user plane / data traffic
  Other aspects
    E.g. inter-PLMN roaming scenarios, multiple dual-3GPP access sessions
Notes: 1

## Slide 3: FS_ DualSteer Planning
Planning for subsequent meetings
  SA1#100 (Nov 2022): 70%
    Updated/New Use cases and potential requirements
  SA1#100AH (Jan 2023): 80%
    Finalize Use Cases and requirements
    Start Consolidation
  SA1#101e (Feb/Mar 2023): 90%
    Consolidation
    Send TR to SA for information
  SA1#102e (May 2023): 100%
    Conclusions, TR corrections/clean-up
    Send TR to SA for Approval
Notes: 1

## Slide 4: Work plan between meetings
Email coordination
  Coordination among interested/contributing companies, about planned inputs, use cases, etc.
  To be moderated by the rapporteur
Conference calls
  Plan for 1/2 conf calls (open to all SA1 interested parties) to discuss and progress on main open issues (see slide#2)
Notes: 1

## Slide 5: FS_ DualSteer Completion Date
Current expected completion dates:
  For information: SA#99 (03/2023)
  For approval: SA#100 (06/2023)
Have these dates been changed at this meeting? n
  If yes, previous target completion dates:
    N/A
Notes: 1

## Slide 6: FS_ DualSteer History
This SI has been approved at SA#96
  SID is in Tdoc SP-220445
History of completion rates
  SA1#99 (Aug 2022): 30%
Notes: 1