## Sheet1
SA WG2 Meeting #128-bis
August 20-24, Sophia Antipolis, France | [13 empty] | S2-188953
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: This is a revision of the work planning sheet that was endorsed by SA2#127bis. Sessions accumulated per topic are updated. And the finalisation status per topic is added. Budgets for Oct and Nov are endorsed. Q3 status indicated for information and may be further updated after the meeting.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[10 empty] | Jun 17 |  | Aug 17 |  | Okt 17 |  | Nov 17 |  | Jan 18 |  | Feb 18 |  | Apr 18 |  | May 18 |  | Jul 18 |  | Aug 18 |  | Oct 18 |  | Nov 18 |  | Jan 19 |  | Feb 19 |  | Apr/May
|  | Target | status estimation (%) |  |  |  | acc./plan. | planned | accumul. | SA2#122 |  | SA2#122bis |  | SA2#123 |  | SA2#124 |  | SA2#125 |  | SA2#126 |  | SA2#127 |  | SA2#127-bis |  | SA2#128 |  | SA2#128-bis |  | SA2#129 |  | SA2#129-bis |  | SA2#130 |  | SA2#130
| Work Item | date | Q1/18 | Q2/18 | Q3/18 | Q4/18 | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | updated
| FS_5GSAT_ARCH | Mar 19 |  |  | 15 |  | 16.6667 | 12 | 2 | [16 empty] | 1 | 1 | 1 | 1 | 1 |  | 2 |  | 4 |  | 3 |  | 37 |  | 28.5.18 updated by rapporteur | 13.8.18 rapporteur confirms figures
| FS_5G_URLLC | 2018-12-17 |  | 15 | 60 |  | 53 | 10 | 5.3 | [12 empty] | 1 | 0.5 | 1 | 1.1 | 2 | 1.7 | 2 | 2 | 2 |  | 2 | [5 empty] | 28 | 2018-02-07 |  | 8.8.18 rapporteur confirms figures
| FS_CIoT_5G | 2018-09-01 | 20 | 50 | 70 |  | 61.4286 | 28 | 17.2 | [8 empty] | 3 | 2 | 4 | 1 | 3 | 3 | 3 | 3.2 | 4 | 4 | 4 | 4 | 4 |  | 3 | [5 empty] | 24 | 2018-02-16 | 31.5.18 rapporteur updated | 10.8.18 rapporteur increases by 2*0.5TU for multicast aspects
| FS_eV2XARC | 2018-09-01 | 25 | 35 | 58 |  | 62 | 20 | 12.4 | 2 | 2.3 | 2 | 1 |  |  |  |  | 2 | 1.3 | 2 | 1 | 1 | 1.3 | 1 | 1.5 | 2 | 2 | 2 | 2 | 3 |  | 3 | [5 empty] | 23 | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures
| FS_eNA | 2018-12-01 | 15 | 30 | 50 |  | 58 | 15 | 8.7 | [8 empty] | 1 | 1.3 | 2 | 1 | 1 | 1.1 | 1 | 1.3 | 2 | 2 | 2 | 2 | 3 |  | 3 | [5 empty] | 21 | 2018-02-12 | 7.5.18 rapporteur increased to 2-2-2-2 | 9.8.18 rapporteur confirms figures
| FS_eNS | 2018-12-17 |  | 10 | 50 |  | 50 | 9 | 4.5 | [12 empty] | 1 | 1 | 1 | 0.5 | 1 | 1 | 2 | 2 | 2 |  | 2 | [5 empty] | 21 | 2018-02-14 | 31.5.18 rapporteur update | 11.8.18 rapporteur confirms figures
| vertical LAN | 2018-12-17 |  |  | 25 |  | 40 | 10 | 4 | [16 empty] | 2 | 2 | 2 | 2 | 3 |  | 3 | [5 empty] | 18 |  | 7.5.18 initial estimates by rapporteur to be | 9.8.18 rapporteur increases Q4 to 2*3TU {1 per 5G-LAN, Type-a/b, TSN related}
| FS_ATSSS | 2018-09-17 | 20 | 40 | 70 |  | 66.0833 | 12 | 7.93 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1 | 2 | 1 | 1 | 1.3 | 1 | 1.3 | 1 | 1 | 1 | 1 | 2 |  | 1 | [5 empty] | 17 | 2018-02-14 | 7.5.18 rapporteur confirmed | 11.8.18 rapporteur confirms figures
| FS_eLCS | 2018-12-17 | 15 | 45 | 55 |  | 47.3333 | 15 | 7.1 | [8 empty] | 1 | 1.3 | 2 | 1 | 2 | 1.3 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 |  | 2 |  | 2 |  | 2 |  | 17 | 09.04.2018 rapporteur proposed some reduction | 07.05.2018 rapporteur proposed to go for 1TU/meeting | 6.8.18 rapporteur increases Q4 to 2*2TU and extends to Q1
| FS_eSBA | 2018-12-17 |  | 15 | 60 |  | 54.2857 | 14 | 7.6 | [12 empty] | 1 | 1 | 1 | 1.3 | 3 | 2.3 | 3 | 3 | 3 |  | 3 | [5 empty] | 17 |  | 9.5.18 rapporteur +1 for July | 8.8.18 rapporteur confirms figures
| FS_5WWC | 2018-12-17 | 25 | 35 | 60 |  | 72.0625 | 16 | 11.53 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1.3 | 1 | 1 | 1 | 1.3 | 2 | 2.3 | 2 | 2.3 | 2 | 2 | 2 |  | 3 | [5 empty] | 15 | 2018-02-12 | 16.5.18 rapporteur confirmed | 13.8.18 rapporteur increases for Nov to 2TUs anticipating more BBF interactions
| FS_ETSUN | 2018-12-01 | 25 | 40 | 66 |  | 50 | 13.6 | 6.8 | [8 empty] | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 0.5 | 2 | 1.3 | 2 | 2 | 1.3 |  | 1.3 | [5 empty] | 13 |  | 31.5.18 rapporteur extends | 8.8.18 rapporteur proposes to extend until Dec
| FS_eIMS5G | 2018-09-01 | 20 | 40 | 40 |  | 115 | 4 | 4.6 | [8 empty] | 1 | 1.3 | 1 | 1 | 1 | 1.3 | 1 | 1 | [2] |  | [2] |  |  |  | [1] |  | [1] |  | [1] |  | 7 | 2018-02-06 | 7.5.18 rapporteur confirmed | 9.8.18 rapporteur considers to un-pause in Nov
| FS_RACS | 2018-09-17 |  |  | 40 |  | 40 | 5 | 2 | [16 empty] | 1 | 1 | 1 | 1 | 2 |  | 1 | [5 empty] | 6 |  | 9.5.18 initial estimates by rapporteur to be | 9.8.18 rapporteur confirms figures
| FS_5G-SRVCC | 2018-09-17 |  | 80 | 100 |  | 107.5 | 4 | 4.3 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1 | [8 empty] | 5 | 2018-02-08 | 15.5.18 rapporteur confirmed | 10.8.18 rapporteur adds 0.5TU in Q4 assuming RAN dependencies may delay
| [5G-SRVCC] | [5 empty] | #DIV/0! | 0 | 0 | [20 empty] | [1] |  | [1] | [8 empty] | 10.8.18 rapporteur adds 2*1TU in Q4 proposing normative work
| FS_LLC_Mob | 2018-09-01 | 35 | 75 | 75 |  | 80 | 4 | 3.2 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 0.7 | 1 | 0.5 | [1] |  | [1] |  | [0.5] |  | [0.5] | [5 empty] | 4 | no change | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4 for some conclusions
| FS_FLADN | Mar 19 |  |  |  |  | 0 | 2 | 0 | [16 empty] | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | 1 |  | 1 |  | 4 |  | 9.5.18 initial estimates by rapporteur to be | 7.8.18 rapporteur shifts budget by a quarter
| FS_EPS_URACE | 2018-12-17 |  | 10 | 10 |  | 25 | 2 | 0.5 | [12 empty] | 1 | 0.3 | 1 | 0.2 | [1] |  | [1] |  | [1] |  | [1] | [5 empty] | 3 |  | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4
| xBDT | 2018-12-17 |  |  |  |  | #DIV/0! | 0 | 0 | [16 empty] | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | 3 |  |  | 10.8.18 rapporteur shifts budget by a quarter
| FS_Parlos | 2018-09-17 | 45 | 70 | 100 |  | 104.2857 | 7 | 7.3 |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1 | [8 empty] | 2 | 2018-02-13 | 16.5.18 rapporteur asked for extending by a quarter
| FS_ENTRADE | 2018-09-01 | 20 | 70 | 70 |  | 100 | 4 | 4 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [1] |  | [1] | [9 empty] | 2 | 2018-02-08 | 15.5.18 rapporteur confirmed | 10.8.18 rapporteur assumes will be considered for Q1
| FS_AAI_LTE_NR | Mar 19 |  | 30 | 30 |  | 50 | 4 | 2 | [12 empty] | 1 | 1 | 1 | 1 | [1] |  | [1] |  | [1] |  | [1] |  | 1 |  | 1 |  | 1 | 2018-02-13 | 16.5.18 rapporteur confirmed | 7.8.18 rapporteur confirms remaining budget
| FS_NG_RTC | Mar 19 |  |  |  |  | 0 | 3 | 0 | [16 empty] | [1] |  | [2] |  |  |  | [1] |  | 2 |  | 1 |  | 0 |  | 7.5.18 initial estimates by rapporteur to be | 13.8.18 rapporteur considers to un-pause in Q4; reducing earlier requested budget
| FS_UDICoM | 2018-12-17 |  |  | 30 |  | 30 | 4 | 1.2 | [16 empty] | 1 | 0.7 | 0.5 | 0.5 | 1.5 |  | 1 | [8 empty] | 8.8.18 rapporteur provides intial figures
| Maint 6.1 on 5GS |  | 98 | 100 |  |  | 83.6066 | 122 | 102 | [8 empty] | 25 | 24 | 25 | 25 | 14 | 19 | 14 | 19 | 12 | 15 | 12 |  | 10 |  | 10
| Maint 5.1 / 6.1 | [6 empty] | 30 | 28.5 | 3 | 4 | 3 | 3 | 3 | 4.5 | 3 | 2.5 | 3 | 3.5 | 3 | 3 | 2 | 3 | 2 | 3.5 | 2 | 1.5 | 2 |  | 2 |  | 2
| Maint 5.2 / 6.2 | [6 empty] | 8.25 | 2.88 | 1 | 0.5 | 1 | 0.33 | 1 | 0 | 0.25 | 0.3 | 1 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| Maint 5.3 / 6.3 | [6 empty] | 5.25 | 1.5 | 1 | 0.5 | 1 |  | 1 | 0 | 0.25 |  | 1 | 0 | 1 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Maint 5.4 / 6.4 | [6 empty] | 8.5 | 4.55 | 1 | 1 | 1 | 0.1 | 1 | 0.25 | 0.5 | 0.3 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| TEI 3GPP acc | [6 empty] | 2 | 1.8 |  |  |  |  | 1 | 1 | 1 | 0.6 | [9 empty] | 0.2
| TEI PCC/QoS | [6 empty] | 1 | 0.8 | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.3
| TEI n3GPP | [6 empty] | 0 | 0
| TEI IMS/rel. | [6 empty] | 5 | 2.1 | 1.5 | 0.5 |  |  | 0.5 | 0.5 | 1 | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.1 | 0.5 |  | 0.5
| sum | [8 empty] | 10 | 9.3 | 11 | 8.09 | 7.5 | 6.25 | 6.5 | 4.5 | 47 | 42 | 50 | 42 | 38.5 | 42.6 | 38.5 | 42.95 | 42.5 | 43.1 | 43 | 27.5 | 43.8 | 0 | 43.3 | 0 | 10 | 0 | 8 | 0
There should be not more than 42 planned TUs!