## Slide 1: FS_ID_UAS_SA2 Status Report
Stefano Faccin
Qualcomm Incorporated

## Slide 2: FS_ID_UAS_SA2 status after SA2#1401 (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 70% > 85% | Jun, 20 -> Dec, 20 | SP-181114
General
  FS_ID_UAS_SA2 TR 23.754 and v1.1.0 will be available here.
  Several solutions have been updated: #4, #5, #9, #10, #23, #24, #25
  8 conclusion P-CRs were approved
  Several solution were merged and clarified.
Key Issue 1 (UAV identification) :
  9 solutions address KI#1.
  Several new conclusions were approved
Key Issue 2 (UAV authorization by UTM)
  14 solutions address KI#2.
  Several new conclusions were approved, including to progress with a single control-plane solution based to eb derived from #5 and #23
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  6 solutions address KI#3.
  It was clarified that authentication/authorization of UAVCs is not in scope for this release.

## Slide 3: FS_ID_UAS_SA2 status after SA2#140E (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 70% > 85% | Jun, 20 -> Dec, 20 | SP-181114
Key Issue 4 (UAV and UAV Controller tracking):
  8 solutions address KI#4.
  It was clarified that networked UAVCs and UAVCs in the cloud are not identified and tracked separately from the UAV.
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  9 solutions address KI#5.
  Conclusions have been added.
Key Issue 6 (UAV Controller and UAV association):
  4 solutions address KI#6.
  Conclusions have been added.
Key Issue 7 (User Plane Connectivity for UAVs)
  8 solutions address KI#7.
  Conclusions have been added.

## Slide 4: FS_ID_UAS_SA2 status after SA2#139-e (3/3)
RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Contentious Issue:
  Selection of control-plane solution for authorization and authentication between #5 and #23.
Focus for the Next Meeting (SA2#141-e):
  Conclusions on control-plane solution.
  Further evaluations and conclusions.
Overall Plan:
  No new key issues.
  No new solutions.
  Suggest contributors to work offline to define control plane solution based on #5 and #23.
Risks:
  None identified.

## Slide 5: BACKUP SA2#140E FS_ID_UAS-SA2 Status Report (S2-2006064) for information

## Slide 6: FS_ID_UAS_SA2 Status after SA2#140e (overall)
Progress since SA#88-e:
  Minor update to architectural assumptions, several solutions merged, most solutions have detailed added to make evaluation more feasible. Five new solutions added, one being a merger of four existing ones.
  Initial set of conclusions on principles for solutions, covering KI#1 and KI#2, plus additional conclusions.
  RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Next steps:
  Final evaluation and conclusion of what to progress towards a normative phase in Q4.
  The target completion date for the study is proposed to be moved to Dec 2020.
  Submit TR 23.754 to SA#90-e plenary for approval.
  Agree a WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Dec. 20 | SP-181114

## Slide 7: FS_ID_UAS_SA2 status after SA2#140E (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Dec, 20 | SP-181114
General
  FS_ID_UAS_SA2 TR 23.754 v0.3.0 is available here.
  Architectural and reference architecture have been updated.
  Five new solutions added, one being the merger of four existing ones, for a total of 26 solutions.
  Several solution were merged and clarified.
Key Issue 1 (UAV identification) :
  9 solutions address KI#1.
  Initial principle conclusions were captured.
Key Issue 2 (UAV authorization by UTM)
  14 solutions address KI#2.
  Initial principle conclusions were captured.
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  6 solutions address KI#3.
Key Issue 4 (UAV and UAV Controller tracking):
  8 solutions address KI#4.

## Slide 8: FS_ID_UAS_SA2 status after SA2#140E (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 50% > 70% | Jun, 20 -> Dec, 20 | SP-181114
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  9 solutions address KI#5.
Key Issue 6 (UAV Controller and UAV association):
  4 solutions address KI#6.
Key Issue 7 (User Plane Connectivity for UAVs)
  8 solutions address KI#7.

## Slide 9: FS_ID_UAS_SA2 status after SA2#140e (3/3)
RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Contentious Issue:
  The extent to which SA2 can influence the features of the CAA-Level UAV ID assigned and defined in the aviation space.
Focus for the Next Meeting (SA2#141-e):
  Evaluations and conclusions.
Overall Plan:
  No new key issues.
  No new solutions.
  Coordination CC to plan on mergers, evaluations, and conclusions.
  Send LS to RAN on proposal in solution #8.
  Suggest contributors to merge solutions and complete the existing ones, instead of bringing new solutions. Focus on processing solutions (mergers, adding details), evaluation, and conclusions.
Risks:
  None identified.

## Slide 10: BACKUP Previous FS_UAS_ID Status Report (S2-2002032) for information

## Slide 11: FS_ID_UAS_SA2 status after SA2#139-e (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 25% > 50% | Jun, 20 -> Sep, 20 | SP-181114
General
  Total TUs requested for Study Phase in 2020 is 3. 1 TU is used and 2 TUs are remaining.
  Key Issue, architectural assumptions and requirements, and reference architecture have been agreed at 136AH and updated at 139-e.
  21 solutions, most spanning across multiple key issues, are in the TR after 139-e.
Key Issue 1 (UAV identification) :
  7 solutions address KI#1.
Key Issue 2 (UAV authorization by UTM)
  10 solutions address KI#2.
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  3 solutions address KI#3.
Key Issue 4 (UAV and UAV Controller tracking):
  7 solutions address KI#4.

## Slide 12: FS_ID_UAS_SA2 status after SA2#139-e (2/2)
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  7 solutions address KI#5.
Key Issue 6 (UAV Controller and UAV association):
  3 solutions address KI#6.
Key Issue 7 (User Plane Connectivity for UAVs)
  5 solutions address KI#7.
RAN impacts and dependencies:
  One solution (#8) proposes porting to NR the LTE aerial features.
Contentious Issue:
  The extent to which SA2 can influence the features of the CAA-Level UAV ID assigned and defined in the aviation space.
Focus for the Next Meeting (SA2#140-e):
  Evaluations and conclusions. New solutions have not been explicitly excluded but, with a target completion of September 2020, it is clear that new solutions would not allow for evaluation and conclusion.
Overall Plan:
  No new key issues. Suggest contributors to merge solutions and complete the existing ones, instead of bringing new solutions. Focus on processing solutions (mergers, adding details), evaluation, and conclusions.
Risks:
  Completion of the study may not be possible in Q3 if new solutions are brought to the August meeting.

## Slide 13: FS_ID_UAS_SA2 status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ID_UAS_SA2 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | 0% > 25% | Jun, 20 | SP-181114
General
  FS_ID_UAS_SA2 TR 23.754 v0.1.0 is available here.
  Total TUs requested for Study Phase in 2020 is 3. 1 TU is used and 2 TUs are remaining.
  Key Issue, architectural assumptions and requirements, and reference architecture have been agreed.
Key Issue 1 (UAV identification) :
  No contributions focused on this KI could be handled due to lack of time
  Next Steps: SA2#137 to handle solutions
Key Issue 2 (UAV authorization by UTM)
  No contributions focused on this KI could be handled due to lack of time
Key Issue 3 ( UAV Controller identification and authorization/authentication):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 4 (UAV and UAV Controller tracking):
  One (partial) solution was added to the TR

## Slide 14: FS_ID_UAS_SA2 status after SA2#136AH (2/2)
Key Issue 5 (UAV authorization revocation and (re)authorization failures):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 6 (UAV Controller and UAV association):
  No contributions focused on this KI could be handled due to lack of time
Key Issue 7 (User Plane Connectivity for UAVs)
  No contributions focused on this KI could be handled due to lack of time
RAN impacts and dependencies:
  None
Contentious Issue:
  None yet
Focus for the Next Meeting (SA2#137):
  Process new solutions
Overall Plan:
  Focus on processing solution and not adopting new key issues at next meeting, to allow May meeting to complete solutions, evaluations and conclusions.