## Slide 1: ♥ FS_eV2XARC_Ph2 Status Report ♥
LaeYoung Kim
LG Electronics

## Slide 2: FS_eV2XARC_Ph2 status after SA2#141E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC_Ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 70% > 85% | Jun, 20 -> Dec, 20 | SP-190631
General
  FS_eV2XARC_Ph2 TR 23.776 v0.3.0 is available here.
  Total TUs requested for Study Phase in 2020 are 2. SA2#141E is the third meeting that this study was handled.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  11 P-CRs agreed to update the existing solutions, i.e. Solution#1 to Solution#5. (※ Total 7 solutions in the TR)
  1 P-CR about evaluation for the level of provisioned PC5 DRX schedules agreed.
  1 P-CR agreed to capture interim conclusions for PC5 DRX operation.
  LS sent to RAN2 (Cc: RAN1) on PC5 DRX operation to request feedback for evalution and conclusion for the study.
  Next Steps:
    Updates to the existing solutions.
    Continue evaluation and conclusion.

## Slide 3: FS_eV2XARC_Ph2 status after SA2#141E (2/2)
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#142E):
  Continue evaluation and conclusion.
  Submit TR 23.776 to SA#90 plenary for one-step approval.
  Agree a WID dependent on RAN decision and agreement.
    Target Completion:
  There is risk that the study will not be finalized by Dec. 2020 due to RAN dependencies if no feedback is provided by RAN2 on time.

## Slide 4: BACKUP SA2#140E FS_eV2XARC_Ph2 Status Report (S2-2006058) for information

## Slide 5: FS_eV2XARC_Ph2 Status at SA#89-e
Progress since SA#88-e:
  Architectural Assumptions and Architectural Requirements agreed.
  KI#1 “Support of QoS aware NR PC5 power efficiency for pedestrian UEs“ updated.
  For KI#1, 6 new solutions agreed, so total 7 solutions are in TR 23.776.
RAN impacts or dependencies:
  Sidelink DRX related operation
Next steps:
  Evaluation and conclusion.
  Liaise with RAN (To: RAN2) on PC5 DRX operation to request feedback for evalution and conclusion for the study.
  Target Completion: The target completion date for the study is proposed to be moved to Dec. 2020.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC_Ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 25% -> 70% | Jun, 20 -> Dec, 20 | SP-190631

## Slide 6: FS_eV2XARC_Ph2 status after SA2#140E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC_Ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 25% > 70% | Jun, 20 -> Dec, 20 | SP-190631
General
  FS_eV2XARC_Ph2 TR 23.776 v0.2.0 is available here.
  Total TUs requested for Study Phase in 2020 are 2. SA2#140E is the second meeting that this study was handled.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  2 P-CRs agreed to update Sol#1 and 6 new solutions were agreed for inclusion in the TR. Total 7 solutions in the TR.
  Next Steps:
    Updates to the existing solutions.
      No new solution is allowed as indicated in the status report (S2-2004763) @SA2#139E.
    Start solution evaluation.
    Liaise with RAN (To: RAN2) on PC5 DRX operation to request feedback for evalution and conclusion for the study.

## Slide 7: FS_eV2XARC_Ph2 status after SA2#140E (2/2)
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#141E):
  Updates to the existing solutions.
    New key issue and new solution are not allowed as indicated in the status report (S2-2004763) @SA2#139E.
  Start solution evaluation.
  Liaise with RAN (To: RAN2) on PC5 DRX operation to request feedback for evalution and conclusion for the study.
  Focus for SA2#142E meeting (Nov):
  Final evaluation and conclusion.
  Submit TR 23.776 to SA#90 plenary for one-step approval.
  Agree a WID dependent on RAN decision and agreement.
    Target Completion:
  The target completion date for the study is proposed to be moved to Dec. 2020.
  There is risk that the study will not be concluded even by Dec. 2020 due to RAN dependencies if no feedback is provided by RAN2 on time.

## Slide 8: BACKUP SA2#139E FS_eV2XARC_Ph2 Status Report (S2-2004763) for information

## Slide 9: FS_eV2XARC_Ph2 status after SA2#139E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_eV2XARC_Ph2 | Study on architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 0% > 25% | Jun, 20 -> Sep, 20 | SP-190631
General
  FS_eV2XARC_Ph2 TR 23.776 v0.1.0 is available here.
  Total TUs requested for Study Phase in 2020 are 2. SA2#139E is the first meeting that this study was handled.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  1 new solution was agreed for inclusion in the TR.
  Next Steps:
    SA2#140E meeting should be the last meeting to propose new solution for KI#1.
    Liaise with RAN (To: RAN2) on solution impacts to request feedback (at least for Solution#1 "QoS aware power efficient PC5 communication for Pedestrian UEs") if the group agrees.

## Slide 10: FS_eV2XARC_Ph2 status after SA2#139E (2/2)
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#140E):
  For KI#1, new solution can be proposed and the last meeting for new solution.
    Newly proposed solution should be as stable as possible.
  The last meeting to propose new key issue.
    New KI can be added to the TR if it has major support and proposes any valuable aspect not covered by KI#1 because KI#1 is already generic.
  Liaise with RAN (To: RAN2) on solution impacts to request feedback for solution(s) needs RAN feedback/alignment.
Focus for SA2#141E meeting (Oct):
  If new KI added to the TR in SA2#140E meeting, new solution for the KI can be proposed in SA2#141E meeting.
    Newly proposed solution should be as stable as possible.
  Focus for SA2#142E meeting (Nov):
  Final evaluation and conclusions.
  Submit TR 23.776 to SA#90 plenary for one-step approval.
  Agree a WID.
    Target Completion:
  There is risk that study item will not be concluded by Sep, 20 or even by Dec, 20 due to RAN dependencies if no feedback is provided by RAN2 on time.
  According to the current TU allocation, RAN2 will start on Rel-17 NRSL_enh in Q4.