## Slide 1: FS_MUSIM Status Report
Sašo Stojanovski
Intel Corporation

## Slide 2: FS_MUSIM Status at SA#90-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 80% > 90% | Dec, 20 | SP-200091
Progress since SA#89-e:
  Conclusions agreed on
    Paging Cause with the meaning of “voice” for both 5GS and EPS
    NAS Busy Indication for both EPS and 5GS
    Enabling paging reception for EPS
    NAS-level leaving procedure for EPS
  Normative WID agreed
  TR 23.761 submitted for information
  RAN impacts and dependencies:
  Several potential MUSIM enablers depend on progress in RAN WGs, e.g.:
    RRC-based Busy Indication, enabling paging reception for 5GS, leaving procedure for 5GS
Next steps:
  Start normative work on concluded items and coordinate with RAN WGs on items with RAN dependencies

## Slide 3: FS_MUSIM status after SA2#142E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 84% > 90% | Dec, 20 | SP-200091
General
  FS_MUSIM TR 23.761 v1.2.0 is available here.
  Conclusions and interim conclusions have been made on all three key issues
Key Issue 1 (Handling of MT Service):
  Conclusion on a single Paging Cause with the meaning of “voice” for both 5GS and EPS
  Conclusion on NAS Busy Indication for both EPS and 5GS for UE in Idle state
  Interim conclusions agreed that no MMI interaction shall be required for the UE respond to paging (then a list of Editor’s notes)
  Next Steps: Start normative work on Paging Cause and NAS Busy Indication. Coordinate with SA3 on the security of the paging cause. Coordinate with RAN WGs on RRC-based Busy Indication.
Key Issue 2 (Enable Paging reception):
  Interim conclusion agreed (with one objection) on enabling paging reception for EPS. The conclusion needs to be confirmed in RAN plenary.
  Next Steps: Start normative work on enabling paging reception for EPS, if confirmed by RAN plenary. Coordinate with RAN WGs on enabling paging reception for 5GS.
Key Issue 3 (Co-ordinated leaving):
  Interim conclusion updated for NAS leaving (EPS case) with further clarification of assistance information content.
  Next Steps: Start normative work on NAS leaving (EPS case). Coordinate with RAN WGs on RRC-based leaving. Conclude whether AS based leaving, NAS based leaving or both are supported in 5GS.

## Slide 4: FS_MUSIM status after SA2#142E (2/2)
  RAN impacts and dependencies:
  All three key issues have remaining RAN dependency that requires RAN coordination and clarification from RAN plenary on “no-EUTRA impact”., including:
    KI#1: RRC-based Busy Indication for 5GS
    KI#2: Enabling of paging reception for 5GS
    KI#3: RRC-based leaving for 5GS
  SA3 dependencies:
  Feedback from SA3 (S2-2009125) indicated that SA3 “concluded that there are no major blocking issues. SA3 have initiated a study of the security issues involved (S3-202730), with target completion by March 2021”.
Contentious Issue:
  The conclusion on enabing paging reception for EPS requires changes in TS 36.304. RAN plenary needs to confirm that this is acceptable.
Focus for the Next Meeting (SA2#143E):
  Ahead of SA2#143E: Organize a conference call to:
    organize normative work (e.g. identify impacted clauses, call for volunteers, etc.).
    discuss coordination with other groups on the open items and their dependencies
  During SA2#143E:
    Focus on normative work on concluded items.
    Conclude the study on open items
Overall Plan:
  Normative work expected to be completed by SA#92
Risks:
  RAN progress required in 2021Q1 to allow for conclusion of items with RAN dependencies.
  SA3 progress could impact the agreed solutions in SA2.