## Slide 1: FS_ATSSS_Ph2 Status Report
Jinguo Zhu
ZTE

## Slide 2: FS_ATSSS_Ph2 status after SA2#142E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS_Ph2 | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | 85% -> 95% | Sep, 20 -> Dec, 20 | SP-200095
General
  FS_ATSSS_Ph2 is captured in TR 23.700-93 and v1.2.0 will be available here.
  Good progress on evaluation and conclusion for key issue 1 and key issue 3
  On key issue 2 there are open issues with dependency on IETF progress. An LS is agreed to send to IETF. Later on SA2 may decide whether to continue the R-17normative work on this key issue.
Key issue #1: Additional Steering Modes
  4 P-CRs agreed updating existing solutions. 3 P-CRs agreed updating the evolutions and conclusions
  Final conclusion was agreed
  Next Steps: None.
Key issue #2: Additional Steering Functionalities
  2 P-CRs agreed updating existing solutions. 1 P-CR agreed updating the conclusion
  5 open issues are identified with dependency on the IETF progress.
  Next Steps: Decides whether this key issue can be pursued in Rel-17 normative work based on feedback from IETF on whether WG WG draft for multipath QUIC extensions can be adopted by the end of March 2021
Key Issue #3: Supporting MA PDU with 3GPP access leg over EPC and Non-3GPP access leg over 5GC
  1 P-CRs agreed updating the conclusions
  Final conclusion was agreed
  Next Steps: None.

## Slide 3: FS_ATSSS_Ph2 status after SA2#142E (2/2)
  IETF dependencies:
  QUIC multipath extension, which will need to be specified by IETF
  Applicability of other IETF protocols, such as the MASQUE protocol or the tunnel protocol.
SA3 dependencies
  Study of QUIC with NULL encryption.
Contentious Issue:
  None
Focus for the Next Meeting (SA2#143E):
  Finalize the conclusions for the KIs with open issues (pending IETF feedback).
  Start normative work for the concluded key issues.
Overall Plan:
  SA2#143E (Mar 2021): Start normative work for concluded KI#1 and KI#3 and finalize the evaluation and conclusion of KI#2.
Risks:
  KI#2 may be left out of Rel-17 normative work if IETF feedback is not received by SA#143E

## Slide 4: 2.4) Rel-17 Study/Work (12/12) For SA#90
Progress since SA#89-e:
  Solutions update and final conclusion are agreed for key issue 1 and key issue 3.
  Agree to use MP-QUIC based solutions for UDP/IP traffic for key issue 2 (pending IETF feedback)
RAN impacts or dependencies:
    None identified.
Next steps:
  Start normative work for key issue 1 and key issue 3..
  Decide whether key issue 2 can be pursued in Rel-17 normative work after receiving feedback from IETF on whether WG WG draft for multipath QUIC extensions can be adopted by the end of March 2021
WI Code | Work Item Title | WP | Target Date | WID#
FS_ATSSS_Ph2 | Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | 70% -> 95% | Sep, 20 -> Dec, 20 | SP-200095