## Slide 1: FS_REDCAP_Ph2 Status Report
Qian Chen
Ericsson

## Slide 2: FS_REDCAP_Ph2 status after SA2#150E (1/2)
  General:
  Total 6 pCRs are agreed, including:
    3 solution update papers (S2-2203278, S2-2203279, S2-2203280)
    2 new solution papers (S2-2203281, S2-2203599)
    1 evaluation paper (S2-2203282)
  TR 23.700-68 v0.2.0 is generated based on above agreed contributions
  Total TUs requested for Study Phase in 2022 is 3. 1 TU is used and 2 TUs are remaining
  RAN impacts and dependencies:
  Key issue 1 requires coordination with RAN WGs
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 30% -> 50 % | September, 22 | SP-220074

## Slide 3: FS_REDCAP_Ph2 status after SA2#150E (2/2)
Focus for the Next Meeting (SA2#151E):
  Solving ENs/Improvement of existing solutions
  Evaluation, initial conclusion
  Potential further discussion on NF selection function (depends on Rel-17 CR outcome)
Overall Plan:
  50% progress on the study. Continue the study based on following overall time plan
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval