## Slide 1: SA2 Work Planning
Puneet Jain
SA2 Chair
SA WG2 Meeting #152E (e-meeting) S2-2205668
Aug 17 – 26, 2022

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
153
(5)
152
(5)
TSG
Planned as E-meetings
June
2022
30-3
6-10
20-24
13-17
T
S
G
#
9
6
July
2022
27-1
4-8
18-29
11-15
Aug
2022
1-5
8-12
22-26
15-19
Sep
2022
29-2
5-9
19-23
12-16
T
S
G
#
9
7
Oct
2022
26-30
3-7
17-21
10-14
Nov
2022
24-28
31-4
7-11
SA2
152-E
(3+5)
SA2
153-E
(5)
14-18
Planned as F2F
154
(5)
January
2023
February
2023
16-20
23-27
30-03
06-10
13-17
20-24
March
2023
27-03
06-10
13-17
T
S
G
#
9
9
WG
TSG
S
P
R
I
N
G
F
E
S
T
I
V
A
L
20-24
SA2
155-E
(5)
E-meetings
F2F -meetings
December
2022
21-25
28-02
05-08
12-16
19-30
02-06
09-13
T
S
G
#
9
8
T
H
A
N
K
S
G
I
V
I
N
G
X
M
A
S
&
N
E
W
Y
E
A
R
SA2
154-AH
(5)
Planned as E-Meetings
TBD

## Slide 4: SA2 meeting dates for 2H, 2022
SA2 F2F meeting calendar for 2H, 2022
  SA2 #152-E (17 – 26 Aug, 2022) – Electronic ordinary meeting
  SA2 #153-E (10 – 14 Oct, 2022) – Electronic ordinary meeting
  SA2 #154 (14 – 18 Nov, 2022) – F2F ordinary meeting in Canada

## Slide 5
SA2#152E Dates/Agenda
Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 (Input Doc control applies – Max 2)
  AI 9.X: Rel-18 (TU allocation as per endorsed work plan)
  TEI18 mini WIDs for approval. NOTE: SA2#152E will be the last meeting to handle any new TEI18 proposals
Exceptions for Rel-17 (from Quota):
  5MBS
  NR Slicing
Docs request | 10 Aug 2022 (Wednesday) | 2359 UTC
Docs submission | 10 Aug 2022 (Wednesday) | 2359 UTC
Registration (see clause 3, bullet #3) | 15 Aug 2022 (Monday) | 2359 UTC
Start of e-meeting | 17 Aug 2022 (Wednesday) | 0000 UTC
CC#1 | 17 Aug 2022 (Wednesday) | 1300 – 1500 UTC
Revisions (AI# 4.X, 5.X, 6.X, 7.X, 8.X) | 19 Aug 2022 (Friday) | 1600 UTC
Final Comments (AI# 4.X, 5.X, 6.X, 7.X, 8.X) | 22 Aug 2022 (Monday) | 1600 UTC
CC#2 | 22 Aug 2022 (Monday) | 1300 – 1500 UTC
CC#3 | 23 Aug 2022 (Tuesday) | 1230 – 1530 UTC
Revisions (AI# 9.X, 10.X) | 24 Aug 2022 (Wednesday) | 1600 UTC
Final Comments (AI# 9.X, 10.X) | 25 Aug 2022 (Thursday) | 1600 UTC
CC#4 | 25 Aug 2022 (Thursday) | 1300 – 1500 UTC
CC#5 | 26 Aug 2022 (Friday) | 1230 – 1530 UTC
Close of e-meeting | 26 Aug 2022 (Friday) | 1700 UTC
Upload Approved docs | 29 Aug 2022 (Monday) | 1700 UTC
Upload Rapporteur Status Reports | 30 Aug 2022 (Tuesday) | 1700 UTC

## Slide 6
SA2#153E Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 (Input Doc control applies – Max 2)
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Extend e-meeting by one day.
    Monday (17-Oct) will only handle Rel-18 controversial issues.
    If at CC#3 it is felt that we don’t need an extra day, then the e-meeting cab be closed on 14-Oct.
Docs request | 30 Sep 2022 (Friday) | 2359 UTC
Docs submission | 30 Sep 2022 (Friday) | 2359 UTC
Registration | 07 Oct 2022 (Friday) | 2359 UTC
Start of e-meeting | 10 Oct 2022 (Monday) | 0000 UTC
CC#1 | 10 Oct 2022 (Monday) | 1300 – 1500 UTC
Revisions | 12 Oct 2022 (Wednesday) | 1600 UTC
Final Comments | 13 Oct 2022 (Thursday) | 1600 UTC
CC#2 | 13 Oct 2022 (Thursday) | 1300 – 1500 UTC
CC#3 | 14 Oct 2022 (Friday) | 1230 – 1530 UTC
CC#4 (for Agenda 9.X, 10.X, only) | 17 Oct 2022 (Monday) | 1230 – 1530 UTC
Close of e-meeting | 17 Oct 2022 (Monday) | 1700 UTC
Upload Approved docs | 18 Oct 2022 (Tuesday) | 1700 UTC
Upload Rapporteur Status Reports | 19 Oct 2022 (Wednesday) | 1700 UTC

## Slide 7
SA2#154 Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (CRs only if there any incoming LS)
  AI 8.X: Rel-17 (CRs only if there any incoming LS)
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Meeting closing time to be 6:00PM local time, may close early.
Open
  Email Approval – TBD.
Docs request | 04 Nov 2022 (Friday) | 2359 UTC
Docs submission | 04 Nov 2022 (Friday) | 2359 UTC
Registration | 11 Nov 2022 (Friday) | 2359 UTC
Start of meeting | 14 Nov 2022 (Monday) | 0900 Local Time
Close of meeting | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Approved docs | 18 Nov 2022 (Friday) | 1800 Local Time
Upload Rapporteur Status Reports | 22 Nov 2022 (Tuesday) | 1700 UTC

## Slide 8
SA2#154-Ad-Hoc (Jan) Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Urgent LS and associated CRs
  AI 9.X: Rel-18 (TU allocation as per NEW work plan)
Proposal
  Agree to have SA2#154 Ad-hoc meeting as electronic ad-hoc meeting.
  5 days
  Only Rel-18 topics will be on agenda + Urgent LS
  TEI18 will be on agenda.
Docs request | 09 Jan 2023 (Monday) | 2359 UTC
Docs submission | 09 Jan 2023 (Monday) | 2359 UTC
Registration | 13 Jan 2022 (Friday) | 2359 UTC
Start of e-meeting | 16 Jan 2023 (Monday) | 0000 UTC
CC#1 | 16 Jan 2023 (Monday) | TBD
Revisions | 18 Jan 2023 (Wednesday) | 1600 UTC
Final Comments | 19 Jan 2023 (Thursday) | 1600 UTC
CC#2 | 19 Jan 2023 (Thursday) | TBD
CC#3 | 20 Jan 2023 (Friday) | TBD
Close of e-meeting | 20 Jan 2023 (Friday) | 1700 UTC
Upload Approved docs | 23 Jan 2023 (Monday) | 1700 UTC
Upload Rapporteur Status Reports | 24 Jan 2023 (Tuesday) | 1700 UTC

## Slide 9
SA2#155 Dates/Agenda
It is TBD whether SA2#155 will be F2F or Electronic meeting
If SA2#155 is decided as Electronic meeting, It is proposed to move the dates by a week : 27 Feb – 03 Mar? -TBD
  This is to allow more time for meeting preparation.
Preliminary Agenda (subjected to changes):
  Full agenda

## Slide 10: TEI18 Handling
TEI18 proposals will be on agenda in Aug e-meeting.
SA2#152E will be the last meeting for TEI18 proposals. No TEI18 proposals will be considered after SA2#152E (Aug) e-meeting.
TEI18 proposals can be Approval at Q3, 22 (Aug meeting).
  7 - 9 TU available from the buffer (0.5 min TU).
  Prioritization within SA2, if necessary, in Q4, 22
Scheduling in Q1, 23

## Slide 11: Rel-18 TU Update for SA2#154
SA2#154 is planned as F2F meeting.
Need to reduce the sessions that can run in parallel.
Proposal: Move topics with 0.5 TUs allocation from SA2#154 to either SA2#153-e or 1H 2023 meetings.
  NOTE: Please see S2-2205667 (or latest revision) for the updated SA2 work planning sheet.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0.25
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1
FS_TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.25
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 0.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.75
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.5
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 1 | 1.5 | 1.5
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 1.25
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 2
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.25
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0.5 | 0.5 | 0.5
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.25 | 14 | 26 | 27

## Slide 12: Tracking of TU for Rel-18 SIDs & WIDs
During F2F, one TU (Time Unit) corresponds to 1.5 hours slot in which roughly 10-15 contributions can be handled.
For SA2#149E e-meeting onwards, TU were tracked as per the following mechanism.
  Maximum of 30 TDocs (P-CRs) per 1 TU will be handled. If a Rel-18 SID is assigned 0.5 TU then maximum of 15 TDocs (P-CR) will be handled. If a Rel-18 SID is assigned .25 TU then maximum of 7 TDocs (P-CRs) will be handled.
  If the SID is assigned 1 TU in SA2#149-E and it receives more than 30 papers then only 30 will be picked based on sorting (after submission deadline but before start of the e-meeting) by the SA2 leadership. Fairness criterion will be applied, and Rapporteur input will be required on such sorting.
  Rapporteur are required to provide the sorting order to SA2 leadership as soon as possible (after the TD submission deadline).
  Rapporteur’s input papers on TR skeleton, TR scope etc. will be exempted.
  Discussion Paper (for Information) will be exempted.
  LS IN/OUT will be exempted
It was motioned that if this mechanism hinders progress, then can be revisited in the future e-meeting.
This process has worked out well in terms of limiting the workload therefore it will be continued to apply to Rel-18 SID & WIDs in the future e-meetings.

## Slide 13: Guidance to Rel-18 Rapporteurs
Previous Guidance:
  Rel-18 Rapporteurs should put together a work plan for their SID and how they plan to utilize the assigned TU for each meeting. Update the Work Plan after each meeting. Can be part of the status report. For e.g. - SA2#152-E, 1 TU assigned, solution evaluation and conclusion, normative WID creation, etc.
  Rel-18 Rapporteurs shall provide the status report after each (e-)meeting on the progress, any controversial issue, RAN dependency, etc. Please use template defined for Rel-17 SIDs/WIDs.
Additional Guidance:
  Rel-18 Rapporteurs should prepare for conclusion the SIDs on time.
    Prioritize conclusions papers for offline CCs. Where consensus could not be achieved bring meaningful proposals for SoH (or utilize offline moderated email discussion).
  Rel-18 WID should be based on the conclusions agreed in the TR. WID can be further updated if new conclusions can be agreed. No blanket WIDs for plenary, please.
  Avoid pushing issues requiring further Study (SID) to the Normative phase (WID).

## Slide 14: Proposals (to be Endorsed at SA2#152E)
It is proposed to endorse SA2 work Plan for 2022 (all previous slides).
It is proposed to endorse that SA2 Ad-Hoc in Jan 2023 will be scheduled as e-meeting.