## Slide 1: FS_5GSATB Status Report
CATT

## Slide 2: FS_5GSATB status after SA2#153E (1/2)
General
  TR 23.700-27 v.1.1.0 is created based on approved contributions.
  5 contributions agreed (including 1 LS out, 1 solution update and 3 evaluation plus conclusion update).
  Study phase is closed.
KI#1: PCC/QoS control enhancement considering dynamic satellite backhaul
  1 LS out is approved
  1 updated evaluation plus conclusion is approved
  KI#2: Support of Satellite Edge Computing via UPF on board
  1 solution updates are approved
  1 updated evaluation plus conclusion is approved
  KI#3: Support of Local Data Switching via UPF on-board
  1 updated evaluation plus conclusion is approved
  Next steps:
  Update the conclusion for KI#1 to remove the NOTE for packet out of order according to the result of SoH during the CC#4 in SA2#153E.
  Send TR to SA#98 for Approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 80% > 98% | October, 22 | SP-211639

## Slide 3
  RAN impacts and dependencies:
  None
  Contentious Issue:
  None
Focus for the Next Meeting (SA2#154):
  TR sent to SA for Approval.
  Start normative work.
FS_5GSATB status after SA2#153E (2/2)

## Slide 4: FS_5GSATB status at SA#97
  Progress since SA#97-e
  TR 23.700-27 v.1.1.0 is created.
  5 contributions agreed (including 1 LS out, 1 solution update and 3 evaluation plus conclusion update).
  Study is complete and 1.5 TU left for the normative Phase.
  RAN impacts and dependencies:
  None.
Next steps:
  TR sent to SA for Approval.
  Start normative work.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 80% > 98% | October, 22 | SP-211639

## Slide 5
Overall Plan:
  SA2#149: discuss TR skeleton, TR scope, assumptions and Key Issues, start the solution discussion.
  SA2#150: last meeting for Key Issues, continue the solution discussions .
  SA2#151: continue the solution discussions.
  SA2#152: last meeting for solutions, start the solution evaluation, and send the TR for information. Approve the WID (for concluded KIs)
  SA2#153: complete the evaluation and conclusion. Revise and Approve the WID.
  SA2#154 and #154AH: normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Norm TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 5
Work Plan