## Slide 1: FS_5MBS_Ph2 status report
Li, Meng
Huawei

## Slide 2: FS_5MBS_Ph2 status after SA2#153E (1/2)
General
  TR 23.700-47 v1.1.0 is available.
  Total TUs requested for Study phase in 2022 is 7.5, 7 TU used until SA2#153E and 0.5 TUs remaining.
  10 solution updates agreed for the existing KIs, 8 papers related to evaluations and conclusions agreed.
  LSs have been sent to CT/RAN WGs to seek their feedback for feasibilities for some certain solutions.
Key Issue 1 (RRC Inactive for Multicast)
  5 solutions updated.
  Evaluation and conclusion updated.
  Next step: Do some evaluation within the SA2 scope and wait the RAN feedback to complete the final conclusion, and start the normative work per conclusion.
Key Issue 2 (MOCN for broadcast)
  1 solution update agreed.
  Evaluation updated.
  Next step: Do some evaluation within the SA2 scope and wait the RAN feedback to complete the final conclusion, and start the normative work per conclusion.
Key Issue 3 (AF triggered MBS session management)
  2 solutions updated.
  Evaluation was updated.
  Next step : Complete the final conclusion and start the normative work per conclusion.
Key Issue 4 (Group message delivery)
  1 solution update agreed.
  Evaluation updated and final conclusion agreed.
  Next step : Start the normative work per conclusion.
Key Issue 5 (Power Saving mechanisms)
  1 solution update was agreed.
  Evaluation updated but no conclusion agreed.
  Next step : Complete the final conclusion and start the normative work per conclusion.
Key Issue 6 (Public safety)
  1 solution update agreed.
  Evaluation was updated and final conclusion reached.
  Next step : As per the conclusion, there is no work to be done in SA2.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 75% → 85% | Dec 2022 | SP-220072

## Slide 3: FS_5MBS_Ph2 status after SA2#153E (2/2)
  RAN impacts and dependencies:
  Pending 2 KIs (KI#1, KI#2) have RAN WGs coordination requirement as per agreed pCR.
  The on time RAN feedback is necessary for completing final conclusion.
  It is requested related RAN WG prioritize the related LS handling.
Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#154):
  Complete the evaluation and final conclusion for the KIs with RAN dependency as per the feedback.
  Start the normative work for KI#4.
  TR to be sent for approval.
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): Solution updates (No new Solutions), evaluations, conclusions: Approval of MBS_Ph2 WID.
  SA2#154, Nov (0.5 TU): final conclusions: Adjustment/issues depends on RAN progress, update of the WID.
    NOTE: In SA2#154 meeting, we have to re-arrange the TU allocated for study/normative phase, so 0.5 TU is not the exact number.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12

## Slide 4: FS_5MBS_Ph2 Status at SA#98e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 75% → 85% | Dec 2022 | SP-220072
  Progress since SA#97-e:
  Total TUs requested for Study phase in 2022 is 7.5, 7 TU used until SA2#153E and 0.5 TUs remaining.
  1 LS was sent to CT WGs to seek their feedback for feasibilities for some certain solutions.
  Totally 18 documents agreed for all KIs, in which 10 solution updates and 8 evaluations and conclusions.
  No considerable progress on the RAN dependent KIs.
  RAN impacts and dependencies:
  Pending 2 KIs (KI#1, KI#2) have RAN WGs coordination requirement as per agreed pCR.
  The on time RAN feedback is necessary for completing final conclusion.
  It is requested related RAN WG prioritize the related LS handling.
Other WG dependencies
  KIs have potential SA6 (KI#6)/SA4 (KI#3-5)/SA3 (KI#2) coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Next steps:
  Complete the evaluation and final conclusion for the KIs with RAN dependency as per the feedback.
  TR to be sent for approval.
To be updated in SA2#154 meeting