## Slide 1: FS_PIN Status Report
vivo
S2-2209225

## Slide 2: FS_PIN status after SA2#153E (1/2)
General
  TR 23.700-88 v.1.1.0 was created based on approved contributions.
  8 contributions agreed (6 conclusions update, 1 conclusions addition, and 1 evaluation update).
New key issue agreed:
  No
New solutions captured:
  No
Conclusions update/addition (total 7 KIs):
  Conclusions on KI#1 Architecture
  Conclusions on KI#2 Discovery
  Conclusions on KI#3 PIN management
  Conclusions on KI#4 PIN communication
  Conclusions on KI#5 PIN authorization
  Conclusions on KI#6 Policy provisioning
  Conclusions on KI#7 Identificatoin
WI Code | Work Item Title | WP | Target Date | WID#
FS_PIN | Study on Personal IoT Networks | 75% > 95% | Dec., 22 | SP-211643

## Slide 3
RAN impacts and dependencies:
  No
Other WG dependencies
  Potential SA6 coordination
  Potential SA3 coordination
Contentious Issue:
  No
Focus of the Next Meeting:
  Resolve remain outstanding issues
  Start normative work
Risks:
  No
FS_PIN status after SA2#153E (2/2)

## Slide 4: FS_PIN status at SA#98e
Progress since SA#97e:
  Final conclusions captured
  TR 23.700-88 v1.1.0 generated based on the agreed contributions
RAN impacts and dependencies:
  none
Next steps:
  Resolve remain outstanding issues in TR conclusions
  Start normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_PIN | Study on Personal IoT Networks | 75% > 95% | Dec., 22 | SP-211643

## Slide 5: Annex

## Slide 6: Work Plan
Overall Plan: (study phase)
  SA2#149 (0.5TU): TR skeleton, scope, arch assumptions; new KIs, new solutions
  SA2#150 (0.5TU): New solutions, (new/updated) KIs, KI with solution
  SA2#151 (1TU): Solutions, initial evaluations
  SA2#152 (1TU): Solutions, evaluations, Interim conclusions
  SA2#153 (0.5TU): Finalize conclusions, evaluation updates; WID approval
  SA2#154AH: start normative work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1