## Slide 1
FS_SUECR/SUECR Status Report
Lalith Kumar
Samsung (Rapporteur)
3GPP TSG SA WG2 Meeting #153E
E-Meeting, 10 – 17 October 2022
Agenda 10.4
S2-2209229

## Slide 2: FS_SUECR status after SA2#153E
General
  Normative work has progressed in SA2#153e as part of SUECR WI.
  RAN impacts and dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting (SA2#153e):
  None.
WI Code | Work Item Title | WP | Target Date | WID#
FS_SUECR | Study on Seamless UE context recovery | 100% > 100 % | May, 22 | SP-211654

## Slide 3: SUECR status after SA2#153E
General
  Two CRs were agreed each for TS 23.501(S2-2209666) and TS 23.502(S2-2209667). WID is 100% completed.
  RAN impacts and dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting (SA2#154):
  None.
WI Code | Work Item Title | WP | Target Date | WID#
SUECR | Seamless UE context recovery | 0% > 100 % | Dec, 22 | SP-220810

## Slide 4: SUECR Status at SA#98
WI Code | Work Item Title | WP | Target Date | WID#
SUECR | Seamless UE context recovery | 0% > 100 % | Dec, 22 | SP-220810
Progress since SA#97:
  Two CRs were agreed each for TS 23.501(S2-2209666) and TS 23.502(S2-2209667). WID is 100% completed.
  RAN impacts and dependencies:
  None.
Next steps:
  None.

## Slide 5: Backup slides

## Slide 6: Overall Plan:
  SA2#149E Feb(0.5 TU): TR Skeleton, Scope, architecture assumptions, new KI(s) approval, last meeting for new KI(s) approval.
  SA2#150E Apr(0.5 TU): Start of new solutions approval, continuing the discussion and possible updates to architecture requirements, assumptions, terminology and KI.
  SA2#151E May(0.5 TU): TR solution clean-up, solution evaluation and conclusions.
  SA2#152E Aug(0 TU): Approve WID based on conclusions of the TR.
  SA2#153e : Complete normative work.