## Slide 1: SFC/FS_SFC Status Report
Meghashree D Kedalagudde Intel (Rapporteur)

## Slide 2: SFC status after SA#154AHE
Progress since SA#98e:
  Total TUs requested for Normative Phase is 1.5 TUs, 0.5 TU remaining.
  15 CRs were submitted to SA2#154AHEe meeting corresponding conclusions in TR 23.700-18.
  2 CRs for TS 23.501, 1 CR for TS 23.502 and 2 CRs for TS 23.503 were approved. 1 CR was noted and 9 CRs were marked as merged .
Next steps:
  SA#156 meeting, April 2023
    Complete the remaining normative work based on the agreed WID for SFC.
WI Code | Work Item Title | WP | Target Date | WID#
SFC | System Enabler for Service Function Chaining | 60%> 0% | June, 2023 | SP-221336

## Slide 3: FS_SFC status after SA#98e
Progress since SA#97:
  TR 23.700-18 v1.1.0 generated based on the agreed contributions.
  Total TUs requested for Study Phase is 2.5 TUs, 0 TU remaining.
  Total TUs requested for Normative Phase is 1.5 TUs, 0.5 TU remaining
  The study for SFC is 100% complete.
WI Code | Work Item Title | WP | Target Date | WID#
FS_SFC | Study on System Enabler for Service Function Chaining | 100% | Oct, 22 | SP-211594

## Slide 4: FS_SFC/SFC Work Plan
Contentious Issue:
  N/A
Focus for the Next Meeting (SA2#156):
  Total TU allocated for SA2#156 meeting is 0.5 TU.
  Discuss CRs for remaining normative work implementing study conclusions for KI#1 and KI#2.
  This is the last meeting to discussion remaining normative work for SFC.
Overall Plan:
  SA2#149-E: TR Skeleton, TR Scope, Architectural Assumption, Key Issues, solutions for KIs related to WT#2 and WT#3 (low priority if exceeding 30 papers limits)
  SA2#150-E: any new Key Issue (last meeting), new/revised solutions for all Key Issues/WTs
  SA2#151-E: any new/revised solution (last e-meeting), initial evaluation and potential conclusion.
  SA2#152-E: Solution evaluation and conclusion completion, normative WID, TR for information at SA#97e.
  SA2#153: Complete conclusion for KI#1, Send TR for approval at SA#98. Update of normative WID if needed, and normative works.
  SA2#154AH,SA2#156: Normative work implementing study conclusions for KI#1 and KI#2.
Risks:
  -
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | April, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #156 | Total TU
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5 | 4