## Slide 1: WI Status Report: Study on Phase 2 for UAS, UAV and UAM (FS_UAS_Ph2)
Qualcomm Incorporated
S2-2211373

## Slide 2: FS_UAS_Ph2 status after SA2#154 (1/2)
General
  TR 23.700-58 v1.1.0 was created based on approved contributions.
  TR 23.700-58 v1.1.0 is being submitted for approval at SA#98e.
  WID approved at SA2#153e.
  No time slot at SA2#154 thus no further progress.
Next steps:
  Start normative work at SA2#154AH.
  Address existing Editor‘s Notes based on progress in RAN work and during normative phase.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% | Sept, 22 | SP-211636

## Slide 3: FS_UAS_Ph2 status after SA2#154 (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None left.
Focus for the Next Meeting (SA2#155e):
  Begin normative work.
Overall Plan:
  2023 Q1: progress normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 5.5

## Slide 4: Appendix

## Slide 5: FS_UAS_Ph2 status after SA2#153E (1/2)
General
  TR 23.700-58 v.1.1.0 was created based on approved contributions.
  8 contributions agreed (no new solutions, no new key issues).
    Existing solutions were updated, ENs removed
    Conclusions for KI#1 were updated and finalized
    Conclusions for KI#2 and KI#3 were finalized
  0.75 TU left for the Study Phase.
  WID approved.
Next steps:
  TR sent to SA for Approval at SA2#154
  Start normative work at SA2#154AH
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 80% > 98% | Sept, 22 | SP-211636

## Slide 6: FS_UAS_Ph2 status after SA2#153E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None left.
Focus for the Next Meeting (SA2#154):
  TR sent to SA for Approval.
Overall Plan:
  2023 Q1: progress normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 5.5

## Slide 7: FS_UAS_Ph2 status after SA2#152E (1/2)
General
  TR 23.700-58 v.0.4.0 was created based on approved contributions.
  8 contributions agreed (no new solutions, no new key issues).
    Existing solutions were updated, ENs removed
    Conclusions for KI#1 were captured
  1.5 TU used and 1.75 TU left for the Study Phase.
Next steps:
  Complete evaluations.
  Complete conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 50% > 80% | Sept, 22 | SP-211636

## Slide 8: FS_UAS_Ph2 status after SA2#152E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  Co-existence of PC5 and network based DAA solutions.
  Some technical details of network-based DAA solutions.
Focus for the Next Meeting (SA2#152e):
  Focus on evaluation and conclusions of KI#2 and KI#3.
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions and solution updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 9: FS_UAS_Ph2 status after SA2#151E (1/2)
General
  TR 23.700-58 v.0.3.0 was created based on approved contributions.
  9 contributions agreed (2 new solutions, no new key issues).
  1.5 TU used and 1.75 TU left for the Study Phase.
3 Solutions agreed for the study:
  Sol. #1: C2 communication over PC5
  Sol. #2: Network assisted DAA
  Sol. #3: MBS-based UAV remote ID broadcast
  Sol. #4: Direct C2 communication over PC5
  Sol. #5: U2X for support of Broadcast Remote ID and Direct DAA via PC5
  Sol. #6: Handling C2 connection over PC5
  Sol. #7: Ground-based DAA for location such as Arena.
Next steps:
  Capture new solutions for all KIs, expand details on existing KI, start evaluations.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 35% > 50% | Sept, 22 | SP-211636

## Slide 10: FS_UAS_Ph2 status after SA2#151E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#152e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions and solution updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 11: FS_UAS_Ph2 status after SA2#150E (1/2)
General
  TR 23.700-58 v.0.2.0 was created based on approved contributions.
  5 contributions agreed (5 new solutions, no new key issues).
  1 TU used and 2.25 TU left for the Study Phase.
3 Solutions agreed for the study:
  Sol. #1: C2 communication over PC5
  Sol. #2: Network assisted DAA
  Sol. #3: MBS-based UAV remote ID broadcast
  Sol. #4: Direct C2 communication over PC5
  Sol. #5: U2X for support of Broadcast Remote ID and Direct DAA via PC5
Next steps:
  Capture new solutions for all KIs, expand details on existing KI, start evaluations.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 20% > 35% | Sept, 22 | SP-211636

## Slide 12: FS_UAS_Ph2 status after SA2#150E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#151e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues. LAST CHANCE FOR NEW SOLUTIONS
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (last chance for new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 13: FS_UAS_Ph2 status after SA2#149E (1/2)
General
  TR 23.700-58 v.0.1.0 was created based on approved contributions.
  8 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, and key issues).
  0.5 TU used and 2.75 TU left for the Study Phase.
3 Key Issues agreed for the study:
  KI#1: Transport C2 communication over PC5 interface
  KI#2: Support of Broadcast Remote ID
  KI#3: Support of Detect and Avoid Mechanism in 3GPP system
Next steps:
  Capture new solutions for all KIs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 0% > 20% | Sept, 22 | SP-211636

## Slide 14: FS_UAS_Ph2 status after SA2#149E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#150e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues.
Overall Plan: (study phase)
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (last chance for new KIs; solutions)
  SA2#151 May’22: 0.5 (last chance for new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5