## Slide 1: FS_5GSATB status report 5GSATB status report
Hucheng Wang
CATT

## Slide 2: FS_5GSATB status after SA2#154
  Progress since SA2#153-e:
  2 contributions approved (including 1 evaluation, 1 conclusion update).
  Extra 0.25 TU is used, Study phase is closed.
  RAN impacts and dependencies:
  None
  Next steps:
  Send TR to SA#98 for Approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 98% > 100% | October, 22 | SP-211639

## Slide 3: 5GSATB status after SA2#154
WI Code | Work Item Title | WP | Target Date | WID#
5GSATB | 5G System with Satellite Backhaul | 0 -> 30% | Mar. 2023 | SP-220808
  Progress since SA2#153-e:
  This is the first quarter for the Work Item.
  Total TUs for the work item: 1.5 TUs. 0.75 TUs used, Remaining TUs: 0.75 TUs.
  3 objectives have been discussed in this meeting, with 6 CRs approved:
    KI#1: 2 CRs
    KI#3: 3 CRs
    KI#4: 1 CR
  RAN impacts and dependencies:
  None
Next steps:
  Continue the normative work.

## Slide 4: FS_5GSATB status at SA#98
  Progress since SA#97-e:
  TR 23.700-27 v.1.2.0 is created.
  7 contributions agreed (including 1 LS out, 1 solution update and 5 evaluation plus conclusion update).
  Study is completed, extra 0.25 TU is used for the study Phase.
  RAN impacts and dependencies:
  None
  Next steps:
  Send TR to SA#98 for Approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSATB | Study on Support of Satellite Backhauling in 5GS | 80% > 100% | October, 22 | SP-211639

## Slide 5: 5GSATB status after SA#98
WI Code | Work Item Title | WP | Target Date | WID#
5GSATB | 5G System with Satellite Backhaul | 0 -> 30% | Mar. 2023 | SP-220808
  Progress since SA#97-e:
  This is the first quarter for the Work Item.
  Total TUs for the work item is 1.5 TUs, 1TU is used (0.5 TU is remained), including 0.25 borrowed for study.
  3 objectives have been discussed in this meeting, with 6 CRs approved:
    KI#1: 2 CRs
    KI#2: 3 CRs
    KI#3: 1 CR
  RAN impacts and dependencies:
  None
Next steps:
  Continue the normative work.

## Slide 6
Study Phase:
  SA2#149: discuss TR skeleton, TR scope, assumptions and Key Issues, start the solution discussion.
  SA2#150: last meeting for Key Issues, continue the solution discussions .
  SA2#151: continue the solution discussions.
  SA2#152: last meeting for solutions, start the solution evaluation, and send the TR for information. Approve the WID (for concluded KIs)
  SA2#153: evaluation and conclusion.
  SA2#154: complete the evaluation and conclusion
  Normative Phase:
  SA2#154 : normative work
  SA2#154AH : continue the normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Norm TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_SATB | 3.75 | 1.25 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0.25/0.75 | 0.5 | 0 | 5
Work Plan