## Slide 1: FS_UPEAS/UPEAS Status Report
Yan Han
China Mobile
S2-2211393

## Slide 2: FS_UPEAS/UPEAS status after SA2#153/154 (1/2)
  General
  No TU is allocated for FS_UPEAS/UPEAS at SA2#154. Status Information below is the same as after SA2#153e.
  TR 23.700-62 v.1.1.0 was created based on approved contributions.
  Total TUs requested for Study phase in 2022 is 3.25, and 0 TU remaining.
  TR 23.700-62 will be sent to plenary for approval.
Key Issue1: Study UPF event exposure service registration and discovery
  Evaluation&conclusion on KI#1 was complete.
Key Issue2: Support UPF expose information to other NFs
  one EN left in the conclusion to be resolved.
  RAN impacts and dependencies:
  None.
Other WG dependencies
  None.
Contentious Issue:
  None.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS | Study on UPF enhancement for Exposure And SBA | 80% > 98% | Dec, 22 | SP-211652 -> SP-220417

## Slide 3: FS_UPEAS/UPEAS status after SA2#153/154 (2/2)
  General
  5 CRs are agreed corresponding to the conclusions in TR (2 for TS 23.501, 2 for TS 23.502, 1 for TS 23.288).
  Total TUs requested for Normative phase is 2.25, 0.75 TU used in SA2#153E and 1.5 TUs remaining.
Focus of the Next Meeting (SA2#154AH):
  Solve the EN in the TR conclusion.
  Continue normative work for KI#1 and KI#2 based on the agreed WID for UPEAS.
Overall Plan:
  SA2#149e, Feb (0.5TU): TR skeleton, scope, Arch assumptions and requirements, and KIs
  SA2#150e, Apr (0.5TU): last chance for new KIs; solutions discussion
  SA2#151e, May (1TU): solutions discussion
  SA2#152e, Aug (1TU): solutions discussion, start solution evaluation and conclusion; send TR for information; potential WID discussion and approval (if possible)
  SA2#153e, Oct (1TU): Solution update (No new solutions); finalize the conclusion; start normative work; Send TR for approval at SA#98e
  SA2#154AH, Jan (1TU); SA2#155e, Feb (0.5TU): : normative work
WI Code | Work Item Title | WP | Target Date | WID#
UPEAS | UPF enhancement for Exposure And SBA | 0% > 20% | March, 23 | SP-220809
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 (0.25+0.75) | 0 | 1 | 0.5 | 5.5

## Slide 4: FS_UPEAS status at SA#98e
  Progress since SA#97e:
  6 pCRs for solution update and evaluation&conclusion are agreed.
  TR 23.700-62 v1.1.0 generated based on the agreed contributions.
  Total TUs requested for Study Phase is 3.25 TUs, 0 TU remaining.
RAN impacts and dependencies:
  None.
Next steps:
  TR to be sent for approval.
  Solve the EN in the TR conclusion on KI#2.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS | Study on UPF enhancement for Exposure And SBA | 80% > 98% | Dec, 22 | SP-211652 -> SP-220417

## Slide 5: UPEAS status at SA#98e
  Progress since SA#97e:
  5 CRs are agreed corresponding to the conclusions in TR.
  Total TUs requested for Normative Phase is 2.25 TUs, 1.5 TUs remaining.
RAN impacts and dependencies:
  None.
Next steps:
  SA#154AH meeting, January 2023: Continue normative work for KI#1 and KI#2 based on the agreed WID for UPEAS.
WI Code | Work Item Title | WP | Target Date | WID#
UPEAS | UPF enhancement for Exposure And SBA | 0%> 20% | March, 23 | SP-220809