## Slide 1: WI Status Report: Study on Vehicle Mounted Relays (FS_VMR)
Qualcomm Incorporated
S2-2211394

## Slide 2: FS_VMR status after SA2#154 (1/2)
General
  TR 23.700-05 v.1.2.0 was created based on approved contributions and was sent to SA#98 for approval.
  Study Phase has completed and exhausted all the allocated TUs (2.75).
  Normative Phase has started with 0.75 TU used, and 1.5 TU is left.
  RAN impacts and dependencies:
  A reply LS (S2-2211437) has been sent to RAN WGs on the required support for certain features based on SA2 conclusions.
Other WG dependencies
  Charging support is expected to be handled by SA5, and alignment work in SA2 may be required
  Secure and trusted access to OAM server for a MBSR would require coordination with SA3 and SA5 in normative phase.
WID was approved in SA2#154 (S2-2211467).
Normative work progress:
  1 CR (S2-2211224) to TS 23.501 and 1 CR (S2-2211225) to TS 23.273 were approved for general MBSR support introduction.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 80% > 100% | Nov, 22 | SP-211636
VMR_ARCH | Architecture Enhancements for Vehicle Mounted Relays | 0% > 20% | TBD | SP-22xxxx

## Slide 3: FS_VMR status after SA2#154 (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#154-AH):
  Normative work based on the objectives of the WID.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (Resolve RAN dependent open issues for selected solutions); start normative work 0.75.
  SA2#154AH Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 1 (Normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 (0.25+0.75) | 0.5 | 1 | 5

## Slide 4: FS_VMR status at SA#98
Progress since SA#97:
  The study phase has been completed.
  TR 23.700-05 v2.0.0 is sent for SA#98 for approval.
  WID has been agreed in SA2 (S2-2211467) and sent for SA#98 for approval.
  2 CRs (to TS 23.501 and 23.273) have been agreed in SA2 and sent for SA#98 for approval.
RAN impacts and dependencies:
  A reply LS (S2-2211437) has been sent to RAN WGs on the required support for certain features based on SA2 conclusions.
Next steps:
  Normative work based on approved WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 80% > 100% | Nov, 22 | SP-211636
VMR_ARCH | Architecture Enhancements for Vehicle Mounted Relays | 0% > 20% | TBD | SP-22xxxx