## Slide 1: WI Status Report for eNA_Ph3
Aihua Li (China Mobile), Xiaobo Wu(Vivo)

## Slide 2: eNA_Ph3 status after SA2#155 (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | 45% -> 65% | June 2023 | SP-220678
General
  28 CRs are agreed, 2 CRs are noted, and 7 CRs are postponed.
  2 LS out are agreed.
  58 contributions could not be handled within the TUs allocated for eNA_Ph3.
  Normative work is continued.
KI#1: How to improve correctness of NWDAF analytics:
    7 CRs are agreed, 1 CR is postponed.
    Next steps: Continue normative work.
    KI#2: NWDAF-assisted application detection:
    2 CRs are agreed.
    Next steps: Continue normative work.
    KI#3: Data and analytics exchange in roaming case:
    1 LS out to SA3 is agreed, 1 LS out to GSMA NRG, DESS, WAS is agreed.
    Next steps: Continue normative work.

## Slide 3: eNA_Ph3 status after SA2#155 (2/3)
    KI#4: How to Enhance Data collection and Storage:
    6 CRs are agreed and 1 CR is postponed.
    Next steps: Continue normative work.
    KI#5: Enhance trained ML Model sharing:
    1 CR is agreed.
    Next steps: Continue normative work.
    KI#6: NWDAF-assisted URSP:
    3 CRs are agreed and 1 CR is noted.
    Next steps: Continue normative work.
    KI#7: Enhancements on QoS Sustainability analytics:
    2 CRs are agreed.
    Next steps: Continue normative work.
    KI#8: Supporting Federated Learning in 5GC:
    6 CRs are agreed, 1 CR is noted, and 2 CRs are postponed.
    Next steps: Continue normative work.
    KI#9: Enhancement of NWDAF with finer granularity of location information:
    1 CR is agreed and 3 CRs are postponed.
    Next steps: Continue normative work.
    KI#10: Interactions with MDAS/MDAF:
    Next steps: Continue normative work.

## Slide 4: eNA_Ph3 status after SA2#155 (3/3)
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  No contentious Issue.
Focus for the Next Meeting (SA2 #156 e-meeting):
  Continue normative work.
  And the following issue need further discussion in future meetings:
  For KI#3, S2-2303548 LS out to GSMA NRG, DESS, WAS, SA2 may need further discusssion taking the feedback on UE specific data and/or analytics exchange between HPLMN and VPLMN into account.
    Risk:
  None.

## Slide 5: eNA_Ph3 status after SA2#154AH-e (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
eNA_Ph3 | Enablers for Network Automation for 5G - phase 3 | 25% -> 45% | June 2023 | SP-220678
General
  44 CR are agreed, 5 CR are noted, and 11 CR are postponed.
  1 LS in is postponed, 1 LS out is noted, and 4 discussion are noted.
  54 contributions exceeding TU Budget.
  Normative work is continued.
KI#1: How to improve correctness of NWDAF analytics:
    8 CR are agreed, 1 CR is postponed, and 2 discussion are noted.
    Next steps: Continue normative work.
    KI#2: NWDAF-assisted application detection:
    3 CR are agreed.
    Next steps: Continue normative work.
    KI#3: Data and analytics exchange in roaming case:
    1 LS in from SA3 is postponed and 4 CR are agreed.
    Next steps: Continue normative work.

## Slide 6: eNA_Ph3 status after SA2#154AH-e (2/3)
    KI#4: How to Enhance Data collection and Storage:
    7 CR are agreed, 4 CR are noted, and 3 CR are postponed.
    Next steps: Continue normative work.
    KI#5: Enhance trained ML Model sharing:
    4 CR are agreed.
    Next steps: Continue normative work.
    KI#6: NWDAF-assisted URSP:
    4 CR are agreed, 1 CR is noted, and 1 CR is postponed.
    Next steps: Continue normative work.
    KI#7: Enhancements on QoS Sustainability analytics:
    1 CR is agreed and 1 CR is postponed.
    Next steps: Continue normative work.
    KI#8: Supporting Federated Learning in 5GC:
    5 CR are agreed, 3 CR are noted, and 1 discussion is postponed.
    Next steps: Continue normative work.
    KI#9: Enhancement of NWDAF with finer granularity of location information:
    1 LS OUT to SA4 is noted, 7 CR are agreed, 1 CR is postponed, and 1 discussion is noted.
    Next steps: Continue normative work.
    KI#10: Interactions with MDAS/MDAF:
    1 CR is agreed and 1 CR is postponed.
    Next steps: Continue normative work.

## Slide 7: eNA_Ph3 status after SA2#154AH-e (3/3)
  RAN impacts and dependencies:
  No RAN impact.
Contentious Issue:
  No contentious Issue.
Focus for the Next Meeting (SA2 #155 meeting):
  Continue normative work.
  And the following issue need further discussion in future meetings:
  For KI#3, S2-2300014 LS IN, SA3 would like to take the opportunity of LS to ask SA2 on two related aspects within roaming case in the eNA context:
    SA3 is interested in knowing what type of UE-specific data and/or analytics is foreseen to be exchanged between VPLMN and HPLMN in the context of eNA.
    SA3 is also interested in understanding whether the UE-specific data and/or analytics to be exchanged is essentially required to provide the service.
    Risk:
  None.

## Slide 8
Backup Slide for eNA_Ph3 Study Phase Work Plan
#149 meeting: focus on TR skeleton, scope, assumptions and KIs, no solution will be discussed;
#150 meeting: solutions discussions, and KIs. Finalize the KIs (Last chance for new KI proposal);
#151 meeting: continue the solution discussions and capture new solutions;
#152 meeting: solution updates/merging and last chance for new solution(s) (1 supporting companies required) and start to evaluate/conclude solution(s) and send TR for information;
#153 meeting: continue the evalutaion&conclusion, disusss the WID proposal.
#154 meeting: finalize the conclusion and approve the WID for 1 TU, and start normative work;
#154AH and #155 meeting: continue normative work.
#156 and #157 meeting: finalize normative work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 | 
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Total TU
FS_eNA_Ph3 | 9 | 8 | 14 | 1 | 1 | 2 | 2 | 2 | 1+1 | 2 | 3 | 2 | 2 | 17