## Slide 1: FS_REDCAP_Ph2, NR_REDCAP_Ph2 Status Report
Qian Chen
Ericsson

## Slide 2: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#156E (1/2)
  General:
  Total 7 papers are agreed, including:
    3 normative CRs for SA2 NR_REDCAP_Ph2(S2-2305618/S2-2305625/S2-2305626)
    2 normative CRs related to RAN SDT work in relation with NR_REDCAP_Ph2(S2-2305620/S2-2305621)
    2 LS (S2-2305617/S2-2305619) to CT4/RAN3/RAN2 for alignment
  Total TUs planed for normative work is 1 TU. And it is used up
  Additional 0.25TU is used in SA2#156E. Additional 0.25TU for SA2#157 is planned
  WID was update in SA#99 (SP-230171) with target completion date changed to June-2023
  RAN impacts and dependencies:
  Further response from RAN WGs is needed to remove ENs
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 100% -> 100 % | September, 22 | SP-220074
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | 95%->98% | June, 23 | SP-230171

## Slide 3: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#154AHE (2/2)
Focus for the Next Meeting (SA2#157):
  Continue to work on remaining issues (e.g. as indicated in the ENs), considering the responses from RAN WGs
  Details of the UE reachability request handling in AMF.
Overall Plan:
  100% progress on the study
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval
  98% progress on the normative work
    SA2#153E Oct(0.5 TU): Start of the normative work
    SA2#155 Feb (0.5 TU): Solving remaining issues -> changed to SA2#154AHE Jan (0.5 TU)
    SA2#156 Apr (0.25 TU): solving remaining issues, e.g. including new LSs from CT4 and RAN2.
    SA2#157 May (0.25): solving remaining issues related to RAN WGs responses.