## Slide 1: EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: EDGE Ph2 status after SA2#157
  Progress since SA2#156e:
  2 TUs used in SA2#157.
  54 documents were submitted and handled.
  All remaining objectives have been completed, with 25 CRs approved:
    KI#1: 13 CRs approved
    KI#4: 8 CRs approved
    KI#5: 1 CR approved
    KI#7: 1 CR approved
    General: 1 CR approved
  RAN impacts and dependencies:
  None
Next steps:
  The work is functionally completed. Some further clarifications and corrections are to be expected as usual (maintenance).
WI Code | Work Item Title | WP | Target Date | WID#
EDGE_Ph2 | Edge Computing Phase 2 | 90% →100% | Jun 2023 | SP-230112

## Slide 3: EDGE Ph2 status after SA2#157— work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Updates to KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of first version of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Completion of conclusions, Edge ph2 WID based on remaining conclusions
  SA2#154, Nov (0,25 TU): final conclusions
    TR sent for approval
Normative phase
  SA2#154, Nov (0,75+1 TU): Initiated discussions on KIs #1/3/4.
    First CRs discussed and approved
  SA2#154ah, Jan (1,5 TU): Discussions progressed on all KIs in the WID
    Further CRs approved, some KIs almost concluded (KI#3/7)
  SA2#155, Feb (2 TU): Discussions on all KIs, resolution of pain points
    KI#3, KI#5 resolved. Good progress on KI#1, KI#4 and KI#7. Major issues are resolved, some aspects still open.
  SA2#156e, Apr (1,5 TU): Progress and completion of all KIs
  SA2#157, May (2 TU): Completion of all KIs
  Work item is completed
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | Apr. 23 | May 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154ah | #155 | #156 | #157 | Total TU
EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/ 1,75 | 1,5 | 2 | 1,5 | 2 | 16

## Slide 4: EDGE Ph2 status at SA#100
  Progress since SA#99:
  Very good progress on all objectives, all objectives are completed.
  All remaining objectives have been completed, with 40 CRs approved:
    KI#1: 24 CRs approved
    KI#4: 10 CRs approved
    KI#5: 1 CR approved
    KI#7: 3 CRs approved
    General: 2 CRs approved
  RAN impacts and dependencies:
  None
Next steps:
  The work is functionally completed. Some further clarifications and corrections are to be expected as usual (maintenance).
WI Code | Work Item Title | WP | Target Date | WID#
EDGE_Ph2 | Edge Computing Phase 2 | 80% →100% | Jun 2023 | SP-230112