## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #160 Ad Hoc-e S2-2400001
January 22 – 29, 2024

## Slide 2: Rel-19 timelines
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…)
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
100%
SA1 Stage 1 80%
SP-230390 - 3GPP TSG#99, 20 -24 March 2023, Rotterdam, The Netherlands

## Slide 3: SA2 and SA meeting dates for 2024
Q1 | SA2-Ad Hoc | Monday, January 22, 2024 | Monday, January 29, 2024 | Electronic
 | SA2#161 | Monday, February 26, 2024 | Friday, March 1, 2024 | Athens, Greece
 | SA#103 | Tuesday, March 19, 2024 | Friday, March 22, 2024 | Maastricht, NL
Q2 | SA2#162 | Monday, April 15, 2024 | Friday, April 19, 2024 | China (TBC)
 | SA2#163 | Monday, May 27, 2024 | Friday, May 31, 2024 | Jeju, Korea
 | SA#104 | Tuesday, June 18, 2024 | Friday, June 21, 2024 | China (TBC)
Q3 | SA2#164 | Monday, August 19, 2024 | Friday, August 23, 2024 | EU (TBC)
 | SA#105 | Tuesday, September 10, 2024 | Friday, September 13, 2024 | Melbourne, Aus
Q4 | SA2#165 | Monday, October 14, 2024 | Friday, October 18, 2024 | India (TBC0
 | SA2#166 | Monday, November 18, 2024 | Friday, November 22, 2024 | Orlando, USA
 | SA#106 | Tuesday, December 10, 2024 | Friday, December 13, 2024 | Madrid (TBC)

## Slide 4: Rel-19 planning for SA2 - General
Rel-19 studies to complete no later than SA2#163 (May 2024)
  In general it is not expected that study work on any KI’s will continue beyond this date, but there will be some exceptions to this due to dependencies on other TSGs/WGs
  WIDs based on the outcomes of the studies to be agreed by SA2 in SA2#163 (May 2024) and submitted to SA#104 (June 2024)
  Study-only items will not follow these targets
Some checkpoints have been identified related to RAN dependencies
  FS_AmbientIoT: Check in TSG#106 (December 2024) for further Ambient IOT work taking into account RAN progress
  FS_AIML_CN: Check in TSG#105 (September 2024) related to WT1.1, 1.2, 1.3
  FS_ISAC_ARC: Check in TSG#105 (September 2024) to determine the scope, and when to start
Normative work to complete by SA2#166 (November 2024)
  Exception sheets (for submission to SA) to request continuation of Work Items beyond the end of 2024 will be discussed in November

## Slide 5: Rel-19 planning for SA2 – TU overview
Pre-Rel-17 | Rel-19 content discussion
Rel-17 | Rel-19
Rel-18 | Buffer
Feb, 24 | Mar, 24 | Apr, 24 | May, 24 | Jun, 24 | Aug, 24 | Sep, 24 | Oct, 24 | Nov, 24 | Dec, 24
#161 | SA#103 | #162 | #163 | SA#104 | #164 | SA#105 | #165 | #166 | SA#106
36 |  | 36 | 36 |  | 36 |  | 36 | 36 | 
1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 
1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 
 |  |  |  |  |  |  | 6 | 6 | 
 |  |  | 8 |  | 8 |  |  |  | 
 |  | 10 |  |  |  |  |  |  | 
14 |  |  |  |  |  |  |  |  | 
14 |  | 18 | 20 |  | 20 |  | 22 | 22 | 
 |  | 2 (TEI19) | 2 (TEI19) |  | 2 (TEI19) |  |  |  | 
3 |  |  |  |  |  |  | 3 (TEI19) | 3 (TEI19) | 
3 |  | 4 | 4 |  | 4 |  | 3 | 3 | 
The transition to great TU allocation for Rel-19 is expected to be gradual
Allocations in the table right are as currently set out in S2-2400767
The plan will be re-assessed after each meeting to see whether the transition to Rel-19 can be accelerated
Some buffer remains in the plan to handle alignment with other WG’s, late additional work, drafting, etc

## Slide 6: Rel-19 planning for SA2 – TEI19
The planned total budget for TEI19 items is 12 TU’s
Proposed plan for TEI19 items in table
Note that SA (in SP-231760) endorsed the following:
  FS_INSS: Move to TEI19. SA recommend SA2 to discuss this as TEI19 poposal and bring for approval to future TSG meetings
  RVAS_ARCH: Move to TEI19. SA recommend SA2 to discuss this as TEI19 poposal and bring for approval to future TSG meetings
  TEI19_Netshare: SA recommend SA2 to discuss this as TEI19 proposal and bring for approval to future TSG meetings
 |  | TEI19 preparation | TEI119 technical work
Q1 | Jan 24 | Endorse some TEI19 items (must have WID, draft CR’s, > 4 supporters) Items not endorsed are noted | None
 | Feb 24 | Agree <= 8 TU’s of TEI19 items – these will be scheduled in Q2 – Q4 Items endorsed in January but not agreed in February can be considered again in April | None
Q2 | Apr 24 | Agree <= 4 TU’s of TEI19 items – these will be scheduled in Q3 – Q4 Items not agreed are noted | 2 TU’s
 | May 24 | None planned | 2 TU’s
Q3 | Aug 24 | None planned | 2 TU’s
Q4 | Oct 24 | None planned | 3 TU’s
 | Nov 24 | None planned | 3 TU’s

## Slide 7
SA2#161 Dates/Agenda
SA2#161 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 Maintenance
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study/work items
  AI 30.X: Rel-19 TEI-19 proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 16 February 2024 |  | 2359 UTC
Doc submission deadline | Friday 16 February 2024 |  | 2359 UTC
Registration | Monday 19 February 2024 |  | 0800 UTC
Start of meeting | Monday 26 February 2024 | 0900 Local time | 1500 UTC
Close of meeting | Friday 1 March 2024 | 1630 Local time (or earlier) | 2200 UTC
Upload approved documents | Friday 1 March 2024 | 1700 Local time | 2300 UTC