## Work planning for SA2
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 1 | 6
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 26 | 29.5
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_ARCH_Ph3 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 2 |  | 1 | 1
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 2.5 |  | 1 | 1.5
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 2 |  | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 2 |  | 1 | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 0.75
Robert Streijl | Study TU's used |  | 0.75 |  |  | 0.75
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 0
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 0
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 0
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 0
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0
| Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 0
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 0
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 0
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of item plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 16.5 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0