## Slide 1: FS_NG_RTC_Ph2 SI Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC_Ph2 work plan
  The initial TU allocation
    The total TU is currently 11.5, 6 for study and 5.5 for normative work
    3.5 TUs have been used after #160AHE, 2.5 TUs are left for next 3 meetings till #163 for study
    TU allocation for normative work is TBD
  The initial work plan
  #160 meeting: agree all KIs, start discussions on solutions
  #160AH to #161 meetings: discussion on new solutions and solution updates; send TR for information after #161 if possible;
  #162 meeting: Update solutions only, exempt to new solutions of KI#5; start evaluation and conclusion; send TR for information if possible
  #163 meeting: update solutions; evaluation and conclusion; send TR for approval
  #164 meeting onwards: normative work for concluded KIs, may continue to study on KIs not yet concluded
 |  |  |  | Oct. 23 | Nov. 23 | Jan. 24 | Feb. 24 | Apr. 24 | May 24 | Aug. 24 | Oct. 24 |  | 
 |  |  |  | #159 | #160 | #160AH | #161 | #162 | #163 | #164 | #165 |  | 
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  |  |  | 
FS_NG_RTC_Ph2 | 6 | 5.5 | 11.5 | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 1 | 1 |  | 

## Slide 3: FS_NG_RTC_ph2 status after SA2#160AHE
General
  33 contributions were submitted to #160AHE and 30 contributions were handled
  Achievements:
    Updates to KI#1, KI#6 and KI#8 were agreed
    Solution 1 was updated and 16 new solutions were agreed and captured
      KI#1: 5 solutions
      KI#2: 2 solutions
      KI#3: 2 solutions
    No progress on KI#5 on PS data off since SA2 is still waiting for reply from SA1
  Controversial issues
    None
  RAN impacts and dependencies:
  None
Next steps:
  Continue to bring new solutions and update captured solutions in SA2#161
  Sending TR for information if possible
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 15%->30% | June, 2024 | 1010030
      KI#4: 4 solutions
      KI#6: 3 solutions
      KI#8: 1 solutions