## Work planning for SA2
SA2#160
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 0
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 25
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 35
Rel-19 SID/WID detailed plan |  | TU estimates (from SID) | Planned/used
FS_5GSAT_ARCH_Ph3 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1.5; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 1 |  | 1
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 0.5; #162: 1; #163: 1
Yi Jiang | Study TU's used |  | 1 |  | 1
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7.5 | 7.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 1 |  | 1
Curt Wong | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1.5 | bar: #161 to #163
Junshin Park | Study TU's used |  | 1 |  | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0.25; #163: 0.5
Robert Streijl | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
Total planned for Rel-19 |  |  |  |  | 4 | 5.25 | 5 | #161: 5.5; #162: 4.75; #163: 5.5
|  | Planned | Used
Total for Rel-19 Studies |  | 30 | 4 |  | 4 | 0 | 0 | #161: 0; #162: 0; #163: 0
Total for Rel-19 Normative |  | 27 | 0 |  | 0 | 0 | 0 | #161: 0; #162: 0; #163: 0
Total for Rel-19 SID/WID |  | 57 | 4 |  | 4 | 0 | 0 | #161: 0; #162: 0; #163: 0
Rel-18 planned maintenance TU's
FS_SATB / SATB |  |  |  |  | 1 |  | Y | #161: TBD
FS_5GSAT_Ph2 / 5GSAT_Ph2 |  |  |  | 1 |  | 1 | Y | #161: TBD
FS_PIN / PIN |  |  |  | 1 |  | 1 | Y | #161: TBD
FS_UAS_Ph2 / UAS_Ph2 |  |  |  |  | 1 | 1 | Y | #161: TBD
FS_Ranging_SL / Ranging_SL |  |  |  | 1 |  | 2 | Y | #161: TBD
FS_eLCS_Ph3 /eLCS_Ph3 |  |  |  | 2 |  | 1 | Y | #161: TBD
FS_5G_ProSe_Ph2 / 5G_Prose_Ph2 |  |  |  | 1 | 2 |  | Y | #161: TBD
FS_GMEC / GMEC |  |  |  |  | 1 |  | Y | #161: TBD
FS_AIMLsys / AIMLsys |  |  |  | 1 |  | 2 | Y | #161: TBD
FS_5MBS_Ph2 / 5MBS_Ph2 |  |  |  | 2 | 1 |  | Y | #161: TBD
FS_eNS_Ph3 / eNS_Ph3 |  |  |  | 1 | 1 | 1 | Y | #161: TBD
FS_XRM / XRM |  |  |  | 2 | 1 | 1 | Y | #161: TBD
FS_REDCAP_Ph2 / REDCAP_Ph2 |  |  |  |  | 1 |  | Y | #161: TBD
FS_NG_RTC / NG_RTC |  |  |  | 1 |  | 1 | Y | #161: TBD
FS_ATSSS_Ph3 / ATSSS_Ph3 |  |  |  | 1 |  | 0.5 | Y | #161: TBD
FS_UPEAS / UPEAS |  |  |  |  | 1 |  | Y | #161: TBD
FS_EDGE_Ph2 / EDGE_Ph2 |  |  |  | 2 |  | 1 | Y | #161: TBD
FS_5TRS_URLLC / TRS_URLLC |  |  |  | 1 |  | 1 | Y | #161: TBD
FS_VMR / VMR |  |  |  |  | 1 | 1 | Y | #161: TBD
FS_5WWC_Ph2 / 5WWC_Ph2 |  |  |  |  | 1 |  | Y | #161: TBD
MPS_WLAN |  |  |  |  | 1 |  | Y | #161: TBD
FS_AMP / AMP | [5 empty] | 0.5 | Y | #161: TBD
FS_eNA_Ph3 / eNA_Ph3 |  |  |  | 2 |  | 2 | Y | #161: TBD
FS_eNPN_Ph2 / eNPN_Ph2 |  |  |  | 1 | 2 |  | Y | #161: TBD
FS_eUEPO / eUEPO |  |  |  | 1 |  | 1 | Y | #161: TBD
FS_SFC / SFC |  |  |  | 1 |  |  | Y | #161: TBD
FS_DetNet / DetNet |  |  |  |  | 1 |  | Y | #161: TBD
FS_SUECR / SUECR |  |  |  |  | 1 |  | Y | #161: TBD
Total for Rel-18 SID/WID |  |  |  | 22 | 17 | 18
TEI-18 mini WIDs
TEI18_MLR |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_SDNAEPC |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_MBS4V2X |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_SLAMUP |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_ADEE |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_IPv6PD |  |  |  | Y |  | Y | Y | #161: TBD
TEI18_DCAMP_Ph2 |  |  |  | Y |  | Y | Y | #161: TBD
eNSAC |  |  |  | Y |  | Y | Y | #161: TBD