## Slide 1: FS_NG_RTC_Ph2 SI Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC_Ph2 work plan
  The initial TU allocation
    The total TU is currently 11.5, 6 for study and 5.5 for normative work
    2.5 TUs have been used after #160
    3.5 TUs were allocated to next 4 meetings till #163 for study
    TU allocation for normative work is TBD
  The initial work plan
  #160 meeting: agree all KIs, start discussions on solutions
  #160AH to #163 meetings: continue discussions on solutions; send TR for information after #161; send TR for approval after #163
  #164 meeting onwards: normative work for concluded KIs, may continue to study on KIs not yet concluded
 |  |  |  | Oct. 23 | Nov. 23 | Jan. 24 | Feb. 24 | Apr. 24 | May 24 | Aug. 24 | Oct. 24 |  | 
 |  |  |  | #159 | #160 | #160AH | #161 | #162 | #163 | #164 | #165 |  | 
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  |  |  | 
FS_NG_RTC_Ph2 | 6 | 5.5 | 11.5 | 1 | 1.5 | 1 | 1 | 1 | 0.5 | 1 | 1 |  | 

## Slide 3: FS_NG_RTC_ph2 status after SA2#160
General
  43 contributions were submitted to #160 and 30 contributions were handled
  Achievements:
    3 new key issues were agreed
    4 key issues were updated
    1 contribution for KI#1 was agreed to be captured
  Controversial issues
    None
  RAN impacts and dependencies:
  None
Next steps:
  Updates KIs in #160AH, especially for PS data off, and focus on solutions afterwords
  Continue discussions on solutions to the agreed KIs
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 10%->15% | June, 2024 | 1010030

## Slide 4: FS_NG_RTC_ph2 status at SA#102
General
  The SID progress well with totally 71 contributions submitted in two meetings and 48 contributions handled
  TR skeleton, scope and achitectural assumptions were agreed
  Totally 8 Key Issues which covered all WTs were agreed or updated
  1 contribution for KI#1 was agreed to be captured
  A LS is sent to SA1 for clarification on “DC service”, however SA1 postponed the reply LS, which may continue to delay the discussion of KI and solutions to DC service PS data off
  Controversial issues
  None
  RAN impacts and dependencies:
  None
Next steps:
  Updates KIs in #160AH, especially for PS data off, and focus on solutions afterwords
  Continue discussions on solutions to the agreed KIs
  Solutions to DC service PS data off may be deprioritized due to delay of reply LS
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 0%->15% | June, 2024 | 1010030