## Slide 1: FS_5G_ProSe_Ph3 Status Report
Hugh Shieh (AT&T)
Nassima Toumi (KPN)
S2-2401913

## Slide 2: FS_5G_ProSe_Ph3 status after SA2#161
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 20% | SP-231798 | 45% | Study in progress
  General
  TR 23.700-03 v.0.2.0 was created based on approved contributions.
  6 contributions agreed (including solution proposals for both KI#1 and KI#2).
  Progress in SA2#161
  2 solutions are documented for KI#1: UE to Network Relay
  4 solutions are documented for KI#2: UE to UE Relay
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN
Next steps
  Handle new solutions/solution updates for KI#1 & KI#2.
  Solution evaluation and conclusions
  Plan LS to RAN WGs based on agreed solutions.

## Slide 3: FS_5G_ProSe_Ph3 status at SA#103
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 0% | SP-231798 | 45% | Study in progress
  Progress in SA#103
  TR 23.700-03 v.0.2.0 was created based on approved contributions.
  11 contributions agreed (including Scope, Architecture requirements, Key issues and solution proposals for both KI#1 and KI#2).
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN
Next steps
  Handle new solutions/solution updates for KI#1 & KI#2, and solution evaluation and conclusions
  Send TR to SA#104 for information and potentially approval
  Plan LS to RAN WGs based on agreed solutions.

## Slide 4
Total 3.5 TUs
  2 TUs for Study Phase
  1.5 TUs for Normative Work
FS_5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 |  | TR Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 |  | Solutions
SA2#162 | Apr 2024 | 0.5 |  | New solution aspects/Solution Updates, Evaluations, Conclusions
SA2#163 | May 2024 | 0.5 |  | Evaluations, Conclusions
 | Total | 2 |  | 

## Slide 5: BACKUP

## Slide 6: FS_5G_ProSe_Ph3 status after SA2#160AH-e
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 0% | SP-231798 | 20% | Study in progress
  General
  Discussions on Scope, Architecture requirements and Key Issues
  Total 22 TDocs are submitted to SA#160AH-e, and 16 TDocs are handled
  Progress in SA2#160AH-e
  3 pCRs on scope and architecture requirements are agreed
  2 pCRs have been agreed for new Key Issues (related to Work Task #1.1 and #1.2)
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN
Next steps
  Progress solution discussions for agreed Key Issues in next meeting