## Slide 1: 🛩🛩 FS_UAS_Ph3 Status Report 🛩🛩
LaeYoung Kim (LG Electronics), Shabnam Sultana (Ericsson)
(Rapporteurs)

## Slide 2: FS_UAS_Ph3 Status after SA2#162
  Progress since SA2#162
  TR 23.700-59 v0.3.0 is available.
  33 Tdocs submitted: 20 Tdocs for new solution, 10 Tdocs for solution updates, 1 Tdoc for Architectural Assumptions, 1 Tdoc is for new terms and 1 Tdoc for LS Out.
  20 Tdocs handled mainly about new solutions and KI#3 related Architectural Assumptions/Requirements.
    New solutions agreed regarding: KI#1 on C2 reliability (3 solutions), KI#1 on multiple USS (2 solutions), KI#3 (3 solutions).
    Solution update agreed regarding KI#1 on flight planning/monitoring (1 solution).
    For KI#3, updates to KI description and Architectural Assumptions/Requirements agreed based on the Reply LSs from TSG RAN and ETSITC MSG/TFES.
  Due to TU budget/quota, 10 Tdocs for solution updates could not be handled.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency: RAN aspects require RAN input to be able to make progress on normative work in SA2.
Contentious issues
  Regarding aerial UEs not supporting 3GPP Rel-19 NTZ mechanism, requirement to 3GPP system and how to handle them need to be addressed during the study and conclusion of KI#3 and coordination with RAN WGs.
Next steps
  Solution Updates (Prioritize KI#3 to address LS feedback & contentious aspects), Evaluations and Conclusions (※ Conclusions are prioritized).
  TR 23.700-59 sent to SA for one-step Approval.
  LS to RAN WGs to check/get feedback on KI#3 solutions.
  Propose WI to start normative work in Q3 for KI#1&2 and normative work for KI#3 in Q4.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 50% -> 73% | June 2024 | SP-231801

## Slide 3
Total 6.5 TUs
  3.5 TUs for Study Phase
  3 TUs for Normative Work
FS_UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-59 Skeleton, Scope, Arch Assumptions, Key Issues
SA2#161 | Feb 2024 | 1 | 1 | Start solutions discussion, Attempt to close new Key Issue
SA2#162 | Apr 2024 | 1 | 1 | Solution Updates, Final meeting for new solutions, if time permits resolve ENs considered critical, prioritize new solutions for issues not yet addressed or not covered by the existing solutions, Start evaluations (if possible); For KI#3, attempt to send LS to RAN WGs to check/get feedback on solutions
SA2#163 | May 2024 | 1 |  | Solution Updates (focus on KI#3), Evaluations and Conclusions (※ Conclusions are prioritized: For KI#3, attempt to conclude aspects/principles without RAN dependency) TR 23.700-59 sent to SA for one-step Approval For KI#3, attempt to send LS to RAN WGs to check/get feedback on solutions
 | Total | 3.5 |  | 

## Slide 4: BACKUP

## Slide 5: FS_UAS_Ph3 Status at SA#103
Progress since SA#102
  Study started with SA2#160AH-e.
  TR 23.700-59 v0.2.0 is available.
  At SA2#160AH-e: TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID and Annex including background information about No-Transmit Zones agreed.
  At SA2#161: New solutions agreed (3 solutions for KI#1 on flight planning/monitoring, 3 solutions for KI#2, 3 solutions for KI#3).
  Outgoing LSs
    Reply LS sent to SA6 on Coordination of work for UAS_Ph3.
    LS sent to ETSI TC MSG/TFES on No-Transmit Zones according to ECC decision 22(07).
    LS sent to RAN and RAN2 to clarify the requirements for No-Transmit Zones.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency, timely feedback/input needed to resolve differing views
Contentious issues
  KI#3 may be at risk not to complete by May, 2024 if common understanding cannot be reached
Next steps
  Solution discussions, Evaluations, Conclusions, TR sent to SA for one-step Approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 0% -> 50% | June 2024 | SP-231801

## Slide 6: FS_UAS_Ph3 Status after SA2#161
  Progress since SA2#161
  TR 23.700-59 v0.2.0 is available.
  25 Tdocs were submitted: 24 Tdocs are for new solution and 1 Tdoc is for new terms.
  12 Tdocs were handled about: KI#1 on flight planning/monitoring, KI#1 on C2 reliability, KI#2 and KI#3.
    New solutions agreed regarding KI#1 on flight planning/monitoring (3 solutions), KI#2 (3 solutions), KI#3 (3 solutions).
    Cf.) No solution yet regarding KI#1 on C2 reliability, KI#1 on multiple USS.
  Due to TU budget/quota, 13 Tdocs could not be handled about KI#1 on multiple USS and KI#3.
  LS sent to RAN and RAN2 to clarify the requirements for No-Transmit Zones.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency/requires RAN input to be able to make progress/finalization in SA2.
Contentious issues
  KI#3 needs clarification in regards to scope and some technical aspects, without common understanding, this KI may be at risk not to complete by May, 2024.
Next steps
  At SA2#162, continue solution discussions and start evaluations (if possible).
    Tdocs unhandled at SA2#161 will be prioritized (if not covered by the existing solutions) for handling if re-submitted.
    New solutions and resolving ENs considered critical will be prioritized than solution updates.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 15% -> 50% | June 2024 | SP-231801

## Slide 7: FS_UAS_Ph3 Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-59 v0.1.0 is available.
  22 TDocs were submitted and 2 Tdocs proposing new KIs could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs were also considered when discussing the related new Key Issues.
  pCRs for TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID and Annex including background information about No-Transmit Zones have been agreed.
  Key Issue related to No-Transmit Zones has pending EN to be resolved.
  Reply LS sent to SA6 on Coordination of work for UAS_Ph3.
  LS sent to ETSI TC MSG/TFES on No-Transmit Zones according to ECC decision 22(07).
  RAN impacts and dependencies
  RAN dependency is expected related to No-Transmit Zones
Contentious issues
  None
Next steps
  Start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 0% -> 15% | June 2024 | SP-231801