## Slide 1: FS_5G_ProSe_Ph3 Status Report
Hugh Shieh (AT&T)
Nassima Toumi (KPN)

## Slide 2: FS_5G_ProSe_Ph3 status after SA2#163
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 45% | SP-231798 | 90% | 
  General
  TR 23.700-03 v.0.4.0 was created based on approved contributions.
  Progress in SA2#163
  Solution principles are agreed and documented for KI#1: UE to Network Relay
  Solution principles are agreed and documented for KI#2: UE to UE Relay
  TR conclusion has been achieved and solution agreed to normative work
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN
  LS to SA3 seeking their inputs on security related questions for different solutions
Next steps
  Send TR to SA plenary for approval
  Start normative work at SA2#164 based in the conclusions in TR 23.700-03 (clause 8)

## Slide 3
Total 3.5 TUs
  2 TUs for Study Phase
  1.5 TUs for Normative Work
FS_5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 |  | TR Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 |  | Solutions
SA2#162 | Apr 2024 | 0.5 |  | New solution aspects/Solution Updates, Evaluations, Conclusions
SA2#163 | May 2024 | 0.5 |  | Evaluations, Conclusions
SA2#164 | Aug 2024 | 0.5 |  | Normative work, coordination with SA3, finalize the TR conclusions
SA2#165 | Oct 2024 | 0.5 |  | Normative work, coordination with RAN and SA3 if needed
SA2#166 | Nov 2024 | 0.5 |  | Normative work, coordination with RAN and SA3 if needed
 | Total | 3.5 |  | 

## Slide 4: FS_5G_ProSe_Ph3 status at SA#104
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 45% | SP-231798 | 90% | 
  Progress since SA#103
  TR 23.700-03 v.0.4.0 was created based on approved contributions.
  9 contributions agreed (including solution updates and new proposals and conclusions for both KI#1 and KI#2).
  TR conclusion has been achieved and solution agreed to normative work
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN
  LS to SA3 seeking their inputs on security related questions for different solutions
Next steps
  Send TR and new WID to SA plenary for approval
  Start normative work at SA2#164 based in the conclusions in TR 23.700-03 (clause 8)

## Slide 5: BACKUP

## Slide 6: FS_5G_ProSe_Ph3 status after SA2#162
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 45% | SP-231798 | 70% | Study in progress
  General
  TR 23.700-03 v.0.3.0 was created based on approved contributions.
  7 contributions agreed (including solution updates and new proposals for both KI#1 and KI#2).
  Progress in SA2#162
  2 new solutions are documented for KI#1: UE to Network Relay.
  2 new solutions are documented for KI#2: UE to UE Relay.
  Solution updates.
  KI#2 update to support Public Safety requirements.
  RAN impacts and dependencies
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
Next steps
  Solution evaluation and conclusions – based on NWM discussion of the principles
  WID draft discussion
  Plan LS to RAN WGs based on agreed solution principles.