## Slide 1: FS_UIA_ARC Status Report
Mike Starsinic (Rapporteur)
InterDigital

## Slide 2: FS_UIA_ARC Status after SA2#163
  Progress since SA2 #162
  At SA2 #163, the focus was on Conclusions.
  77 contributions were submitted to SA2 #163 and 10 were handled.
  Key Issue #4 was concluded.
  Key Issues #1 thru #3 have not been concluded. Key Issues #2 and #3 depend on Key Issue #1.
  TR 23.700-32 v0.4.0 is available.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  How to handle the case when the UE moves between 4G and 5G. An LS has been sent to SA WG1 to ask about requirements on this scenario (S2-2407219).
  Whether the HPLMN will be able to trust the user identifier and credentials. An LS has been sent to SA WG3 to ask about requirements on this scenario (S2-2407236).
  Whether or not LI is applicable to User Identities. An LS has been sent to SA WG3-LI to ask about requirements on this scenario (S2-2407236).
  Roaming scenarios.
  The WID proposal for Key Issue #4 was noted. The contentious issue for the WID was the name of the WID.
Next steps
  Send TR 23.700-32 V0.4.0 to SA #104 for information.
  Work to conclude Key Issues #1 thru #3 at SA2 #164. Hold offline discussions before SA2 #164.
  At SA2 #164: Complete Study Conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 70% -> 90% | June 2024 | SP-231804

## Slide 3: FS_UIA_ARC Status at SA#104
  Progress since SA #103
  48 contributions were submitted to SA2 #162 and 21 were handled.
  77 contributions were submitted to SA2 #163 and 10 were handled.
  Key Issue #4 was concluded.
  Key Issues #1 thru #3 have not been concluded. Key Issues #2 and #3 depend on Key Issue #1.
  TR is sent for information to SA #104.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  How to handle the case when the UE moves between 4G and 5G. An LS has been sent to SA WG1 to ask about requirements on this scenario (S2-2407219).
  Whether the HPLMN will be able to trust the user identifier and credentials. An LS has been sent to SA WG3 to ask about requirements on this scenario (S2-2407236).
  Whether or not LI is applicable to User Identities. An LS has been sent to SA WG3-LI to ask about requirements on this scenario (S2-2407236).
  Roaming scenarios.
  The WID proposal for Key Issue #4 was noted. The contentious issue for the WID was the name of the WID.
Next steps
  Work to conclude Key Issues #1 thru #3 at SA2 #164. Hold offline discussions before SA2 #164.
  At SA2 #164: Complete Study Conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 35% -> 90% | June 2024 | SP-231804

## Slide 4
FS_UIA_ARC Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 1.5 | 1.5 | Key Issue Updates (e.g. KI#4 editor’s note), Solutions
SA2#162 | Apr 2024 | 1.75 | 1.75 | Solutions that apply to a KI with no/few existing solutions in the TR (i.e. FS_UIA_ARC Key Issue #4), New solutions significantly different to existing one and proposed in a previous meeting but not handled, Solution Updates will be lower priority than KI#4 solutions and new solutions that are significantly different to existing one and proposed in a previous meeting but not handled. Time needs also to be given to papers that propose conclusions/solution principles. NOTE: During the meeting, no solution updates were handled.
SA2#163 | May 2024 | 1.5 | 1.5 | Critical Solution Updates, Complete Study Conclusions NOTE: During the meeting, no solution updates were handled.
SA2#164 | Aug 2024 | X | X | Request to allocate 1 TU for FS_UIA_ARC (Key Issues #1, #2, and #3).
 | Total | 5.25 | 5.25 | 
Total 9.5 TUs were planned
  5.25 TUs were planned for the Study Phase
  4.25 TUs were planned for Normative Work
Request to allocate 1 TU during SA2 #164 for FS_UIA_ARC Key Issues #1, #2, and #3.

## Slide 5: Backup

## Slide 6: FS_UIA_ARC Status after SA2#162
  Progress since SA2 #161
  Focus was on New Solutions and Conclusions.
  TR 23.700-32 v0.3.0 is available.
  68 TDocs were submitted to SA2 #162:
    13 New Key Solutions for Key Issues #1, #2, and #3. (All agreed)
    23 New Key Issue #4 Solutions (5 were agreed and 18 were not handled)
    1 Architectural Assumptions (1 was Noted)
    1 Draft LS Out (1 was Noted)
    1 Summary of Company Feedback (For Information)
    13 Conclusion / Evaluation Paper (2 were agreed, 1 was postponed, and 10 were not handled)
    16 Solution Updates (none were handled)
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  Send TR 23.700-32 to SA for one-step approval.
  Propose WI to start normative work in Q3.
  In the next meeting: Critical Solution Updates, Complete Study Conclusions
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 35% -> 70% | June 2024 | SP-231804

## Slide 7: FS_UIA_ARC Status at SA#103
  Progress since SA #102
  TR skeleton, Scope, Terms, and Architectural Assumptions/Requirements, are agreed.
  4 key issues to cover all 3 work tasks are agreed.
  16 New Solutions were agreed and document in the TR (for Key Issues #1, #2, and #3).
  No solutions for Key Issue #4 were handled.
  TR 23.700-32 v0.2.0 is available.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  In the next meeting: Solution Updates, New Solutions, Partial Evaluations
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 0% -> 35% | June 2024 | 1020063

## Slide 8: FS_UIA_ARC Status after SA2#161
  Progress since SA2 #160AH-e
  Focus was on New Solutions and resolving the EN in KI#4.
  TR 23.700-32 v0.2.0 is available.
  48 TDocs were submitted to SA2 #161: 6 Key Issue Updates and 42 New Solutions
  2 Key Issue #4 Updates were agreed.
  16 New Solutions were agreed (for Key Issues #1, #2, and #3).
  27 papers were not handled.
    8 KI#1 Solutions were not handled.
    3 KI#2 Solutions were not handled.
    3 KI#3 Solutions were not handled.
    13 KI#4 Solutions were not handled.
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  In the next meeting: Solution Updates, New Solutions, Partial Evaluations
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 15% -> 35% | June 2024 | 1020063

## Slide 9: FS_UIA_ARC Status after SA2#160AH-e
  Progress since SA#102
  Study started in SA2#160AH-e.
  TR 23.700-32 v0.1.0 is available.
  13 TDocs were submitted:
    TR skeleton, Scope, Term, and Architectural Assumptions/Requirements (6 Documents)
    7 Key Issue Proposals.
  TR skeleton, Scope, Terms, and Architectural Assumptions/Requirements, and 4 key issues to cover all 3 work tasks from the SID were approved. (1 KI for WT#1, 2 KI’s for WT#2, and 1 KI for WT#3)
  Impacts and Dependencies on other WGs
  Key Issue #2 has some SA3 dependency; e.g., authentication aspects.
  Key Issue #3 has some SA3 dependency; e.g., privacy/exposure aspects.
  Key Issue #3 may have some SA6 dependency; e.g., exposure aspects.
  No RAN dependency
Contentious issues
  None
Next steps
  In the next meeting: Address EN in KI#4 and start solution discussions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UIA_ARC | Study on User Identities and Authentication Architecture | 0% -> 15% | June 2024 | 1020063