## Slide 1: Status report for Study on Energy Efficiency and Energy Saving (FS_EnergySys)
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: FS_EnergySys Status at SA#104
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 55% | SP-231192 | 100% | Study has been completed
  Progress since SA#103
  TR 23.700-66 v0.7.0 is submitted to TSG SA for information and approval
  13 pCRs has been accepted for new solutions and study conclusions
  Impacts and dependencies on other WGs:
  RAN dependent solutions require feedback from RAN WGs for normative work alignments.
  Contentious issues
  The decision on whether new functionality to collect and calculate and the energy related information to be exposed will be defined by SA2 or SA5 will need coordination in SA plenary.
  Next Steps
  Start the normative work based on the agreed conclusions for key issues (depending on the outcome from SA plenary discussion and related approved WID)

## Slide 3: FS_EnergySys Status after SA2#163
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 75% | SP-231192 | 100% | Study has been completed
  General
  Total 80 TDocs were submitted for 1 TU session
  Only 42 pCRs on Key Issue Conclusions are handled by merging to 3 selected baseline Tdocs
  3 Tdocs for conclusions are accepted, 2 LSs are noted
  TR 23.700-66 v0.7.0 is available and submitted to TSG SA for information and approval
  Progress since SA2#162
  Conclusions for all 3 Key Issues have been agreed
  Many details are postponed to and need to be defined in the normative phase

## Slide 4: FS_EnergySys Status after SA2#162
  RAN impacts and dependencies
  RAN dependent solutions require feedback from RAN WGs for normative work alignments.
  Contentious issues
  The decision on whether new functionality to collect and calculate and the energy related information to be exposed will be defined by SA2 or SA5 will need coordination in SA plenary.
  Plans for upcoming meetings
  SA2#164: Start the normative work based on conclusions for key issues (depending on the outcome from SA plenary discussion and related approved WID)

## Slide 5: FS_EnergySys Status after SA2#162
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 65% | SP-231192 | 75% | Study in progress
  General
  Total 86 TDocs were submitted, and 18 Tdocs were handled during 1 TU session
  10 pCRs have been agreed, and 1 LS has been postponed
  Unhandled new solution proposals and interim conclusions were prioritized, based on leadership guidance
  Solutions updates could not allocate time, and had to defer the discussion to next meetings
  TR 23.700-66 v0.6.0 is available
  Progress since SA2#161
  Total 7 new solutions have been accepted in the meeting
    2 new solutions have been added for KI#2
    5 new solutions have been added for KI#3
  Interim conclusions have been formed to facilitate further discussion before/at May meeting
  1 LS from TSG RAN on ‘per-UE energy consumption in RAN’ has been postponed

## Slide 6: FS_EnergySys Status after SA2#162
  RAN impacts and dependencies
  RAN impacts/dependencies are possible based on proposed solutions documented in TR
  Other WG dependencies
  SA5 dependencies are possible based on proposed solutions documented in TR
  Contentious issues
  None
  Plans for upcoming meetings (1 TU remaining)
  SA2#163: Critical solution updates only, Complete study conclusion, Prepare a WID proposal
  for normative work based on conclusion

## Slide 7: FS_EnergySys Work Plan
Total 13 TUs
  6.5 TUs for Study Phase
  6.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 | 1 | Focus on solution updates, only unhandled new solution proposals from #161, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 |  | Critical solution updates only, Complete study conclusion, Prepare a WID proposal for normative work based on conclusion
 | Total | 6.5 |  |