## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #164 Maastricht
August 19 – August 23, 2024

## Slide 2: Rel-19 timelines
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…)
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
100%
SA1 Stage 1 80%
SP-230390 - 3GPP TSG#99, 20 -24 March 2023, Rotterdam, The Netherlands

## Slide 3: SA2 and SA meeting dates for 2024
Q1 | SA2-Ad Hoc | Monday, January 22, 2024 | Monday, January 29, 2024 | Electronic
 | SA2#161 | Monday, February 26, 2024 | Friday, March 1, 2024 | Athens, Greece
 | SA#103 | Tuesday, March 19, 2024 | Friday, March 22, 2024 | Maastricht, NL
Q2 | SA2#162 | Monday, April 15, 2024 | Friday, April 19, 2024 | Changsha, China
 | SA2#163 | Monday, May 27, 2024 | Friday, May 31, 2024 | Jeju, Korea
 | SA#104 | Tuesday, June 18, 2024 | Friday, June 21, 2024 | China (TBC)
Q3 | SA2#164 | Monday, August 19, 2024 | Friday, August 23, 2024 | Maastricht, NL
 | SA#105 | Tuesday, September 10, 2024 | Friday, September 13, 2024 | Melbourne, Aus
Q4 | SA2#165 | Monday, October 14, 2024 | Friday, October 18, 2024 | India (TBC)
 | SA2#166 | Monday, November 18, 2024 | Friday, November 22, 2024 | Orlando, USA
 | SA#106 | Tuesday, December 10, 2024 | Friday, December 13, 2024 | Madrid (TBC)

## Slide 4: Rel-19 planning for SA2 - General
Some checkpoints have been identified related to RAN dependencies
  FS_AmbientIoT: Check in TSG#106 (December 2024) for further Ambient IOT work taking into account RAN progress
  FS_AIML_CN: Check in TSG#105 (September 2024) related to WT1.1, 1.2, 1.3
  FS_ISAC_ARC: Check in TSG#105 (September 2024) to determine the scope, and when to start
Normative work to complete in SA2#166 (November 2024)
  Exception sheets (for submission to SA) to request continuation of Work Items beyond the end of 2024 will be discussed in November

## Slide 5: Rel-19 planning for SA2 – TEI19
We allocated a total of 12 TU’s in the release planning for TEI19
  We do not have to fill this allocation
The approved TEI19 items total 8.75 TU’s
So there is the possibility of allocating a maximum of 12 – 8.75 = 3.25 TUs
I said previously that at some point we can expect the Network Controlled Network Slice Selection item that SA recommended SA2 should look at
I do not want to re-open previous proposals that didn’t get agreed
Priority will be given to items that address issues in deployed networks and that have strong support

## Slide 6: Rel-20 planning
(See SP-240458 endorsed in SA#103 Maastricht)
Studies for 6G in 3GPP are expected to start from Release 20
  First TSG-wide 6G workshop is expected to be in March 2025
  SA1 SID is expected to be approved in Sept 2024
  SA2 SID is expected to be approved in June 2025
  SA2 6G SI completion: Dec. 2026 or Mar 2027 (To be confirmed at future TSG meeting)
For 5G-Advanced
  18-month. Assuming no delay of Rel-19
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
  5G-Advance SID proposals in SA2
    For information in November 2024
    Discussion of SIDs will start in Q1 2025

## Slide 7: Meetings in Q4 2024

## Slide 8
SA2#165 (Hyderabad) Dates/Agenda
SA2#165 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota (2 tdocs per company per AI)) applied to 9.x
  AI 19.X: Rel-19 study/work items (including TEI19)
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 04 October 2024 |  | 2359 UTC
Doc submission deadline | Friday 04 October 2024 |  | 2359 UTC
Registration | Monday 07 October 2024 |  | 0800 UTC
Start of meeting | Monday 14 October 2024 | 0900 Local time | 0530 UTC
Close of meeting | Friday 18 October 2024 | 1630 Local time (or earlier) | 1300 UTC
Upload approved documents | Friday 18 October 2024 | 1730 Local time | 1400 UTC

## Slide 9
SA2#165 (Orlando) Dates/Agenda
SA2#165 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Only related to incoming LS’s
  AI 19.X: Rel-19 study/work items (including TEI19)
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 08 November 2024 |  | 2359 UTC
Doc submission deadline | Friday 08 November 2024 |  | 2359 UTC
Registration | Monday 11 November 2024 |  | 0800 UTC
Start of meeting | Monday 18 November 2024 | 0900 Local time | 1400 UTC
Close of meeting | Friday 22 November 2024 | 1630 Local time (or earlier) | 1130 UTC
Upload approved documents | Friday 22 November 2024 | 1730 Local time | 1230 UTC