## Slide 1: AIML_CN Status Report
vivo (Rapporteur) MediaTek Inc. (Rapporteur)

## Slide 2: AIML_CN status after SA2#164 (1/2)
General
  144 CRs were submitted, 18 CRs were handled, 2 CRs were NOTED, 4 CRs were merged, 5 CRs were postponed, 1 open and 6 CRs were agreed.
  KI#1: 3 CRs agreed.
    TS 23.288: MTLF supporting ML model provisioning with LMF.
    TS 23.273: general feature description of LMF supporting AI/ML based positioning, Data collection at LMF.
  KI#2: 3 CRs agreed.
    TS 23.288: General inference procedure, High level feature description for VFL, Registration and Discovery procedure for VFL.
    One CR for VFL training procedure reached offline agreement but was postponed due to the lack of time in Friday plenary.
  KI#3:No CR agreed. The majority companies prefer to have a new analytics ID but more discussion is needed.
  KI#4:The CR for New analytics ID to support Signalling storm Mitigation and Prevention reached offline agreement but was kept open due to the lack of time in Friday plenary and will be handled next meeting.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
Other WG dependencies
  Security aspects, will be addressed by SA3.
  OAM aspects, if any, will be addressed by SA5.
WI Code | Work Item Title | WP | Target Date | WID#
AIML_CN | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 0% > 15% | Dec, 24 | SP-240991

## Slide 3
AIML_CN status after SA2#164 (2/2)
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-84 TR Skeleton, Arch Assumptions, scope, Initial KIs use case(s)
SA2#161 | Feb 2024 | 1.5 | 1.5 | Final KI/use case updates + Initial Solutions, Attempt to close new Key Issue and new UC.
SA2#162* | Apr 2024 | 1 | 1 | Solution updates and new solution(s)
SA2#163 | May 2024 | 1 | 1 | Final solution updates and final Evaluations + Conclusions
SA2#164 | Aug 2024 | 1.5 | 1 | Normative work per KI conclusion
SA2#165 | Oct 2024 | 1.5 |  | Normative work per KI conclusion
SA2#166 | Nov 2024 | 1 |  | Normative work per KI conclusion
Total 8 TUs
  4 TUs for Study Phase
  4 TUs for Normative Work
Note1: The current work plan does not apply to WT#1.1/1.2/1.3, which will be discussed at SA#105 (Sep. 2024) based on the outcome of the related work in the involved RAN WGs(s).
Note2: It is anticipated that drafting sessions is required for normative work in Q4 subject to planning.
Note3: Rapporteurs will figure out the contribution plan in October SA2 meeting, considering the situation in August SA2 meeting (large number of input papers in August SA2 meeting) and the discussion outcome at SA#105 (Sep. 2024)

## Slide 4: AIML_CN status for SA#105
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 12/12/2024 | 0% | SP-240991 | 15% | 
Progress since SA#104:
  KI#1: 3 CRs agreed.
    TS 23.288: MTLF supporting ML model provisioning with LMF.
    TS 23.273: general feature description of LMF supporting AI/ML based positioning, Data collection at LMF.
  KI#2: 3 CRs agreed.
    TS 23.288: General inference procedure, High level feature description for VFL, Registration and Discovery procedure for VFL.
    One CR for VFL training procedure reached offline agreement but was postponed due to the lack of time in Friday plenary.
  KI#3:No CR agreed. The majority companies prefer to have a new analytics ID but more discussion is needed.
  KI#4:The CR for New analytics ID to support Signalling storm Mitigation and Prevention reached offline agreement but was kept open due to the lack of time in Friday plenary and will be handled next meeting.
Impacts and dependencies on other WGs:
  Any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
  Security aspects, will be addressed by SA3.
  OAM aspects, if any, will be addressed by SA5.
Next steps:
  Finalize the normative work based on the approved WID (SP-240991) and conclusions in TR 23.700-84 (clause 8), considering responses from RAN WGs.

## Slide 5: Annex
Status report for SA2#162/163

## Slide 6: FS_AIML_CN status after SA2#163
General
  95 PCRs were submitted, 10 PCRs were approved, 1 PCR was merged, 84 PCRs were not handled and draft TR 23.700-84 v1.0.0 will be submitted to SA plenary for information.
  The WID will be approved
  KI#1: Final conclusion is agreed.
  KI#2: Final conclusion is agreed, and terminology definition and 4 solution update are agreed.
  KI#3: Final conclusion is agreed, and use cases mapping is agreed.
  KI#4: Final conclusion is agreed.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
Other WG dependencies
  Security aspects, will be addressed by SA3.
  Charging aspects, will be addressed by SA5. OAM aspects, if any, will be addressed by SA5.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIML_CN | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 65% >100% | Jun, 24 | SP-231800

## Slide 7: FS_AIML_CN status after SA2#162
General
  79 papers were received and 39 papers were not handled.
  36 PCRs and 1 LS OUT were approved in total:
    1 LS OUT to RAN WGs related to KI#1;
    8 PCRs papers for key issue #1 new solutions and solution update;
    14 PCRs for key issue #2 solutions and terminologies;
    9 PCRs for key issue #3 solutions;
    5 PCR for key issue #4 solutions.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs.
Other WG dependencies
  None at this stage
Contentious issues
  None (note several ENs need to be addressed across the solutions.)
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIML_CN | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 25% > 65% | Jun, 24 | SP-231800

## Slide 8
FS_AIML_CN Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-84 TR Skeleton, Arch Assumptions, scope, Initial KIs use case(s)
SA2#161 | Feb 2024 | 1.5 | 1.5 | Final KI/use case updates + Initial Solutions, Attempt to close new Key Issue and new UC.
SA2#162* | Apr 2024 | 1 | 1 | Solution updates and new solution(s)
SA2#163 | May 2024 | 1 | 1 | Final solution updates and final Evaluations + Conclusions
SA2#164 | Aug 2024 | 1.5 |  | Normative work per KI conclusion
SA2#165 | Oct 2024 | 1.5 |  | Normative work per KI conclusion
SA2#166 | Nov 2024 | 1 |  | Normative work per KI conclusion
Total 8 TUs
  4 TUs for Study Phase
  4 TUs for Normative Work
Note1: the current work plan does not apply to WT#1.1/1.2/1.3, which will be discussed at SA#105 (Sep. 2024) based on the outcome of the related work in the involved RAN WGs(s).
Note2: It is anticipated that more TUs than planned or more drafting sessions is required for normative work in Q3/Q4 subject to planning. One value suggested is 1.5 extra TUs(either normal sessions or draft sessions ) but this is TBC until August planning.