## Slide 1: FS_5G_ProSe_Ph3, 5G_ProSe_Ph3 Status Report
Nassima Toumi (KPN N.V.) Hugh Shieh (AT&T)

## Slide 2: FS_5G_ProSe_Ph3 status after SA2#164
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020066 | Study on Proximity-based Services in 5GS – Phase 3 | FS_5G_ProSe_Ph3 | 18/06/2024 | 90% | SP-231798 | 100% | Progressed
  Progress in SA2#164
  2 pCRs were approved to update the KI#2 conclusion.
  TR 23.700-03 v.1.1.0 was created based on approved contributions.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
  Input required from SA3 on security related questions for different solutions.
Next steps
  Send TR to SA plenary for approval.

## Slide 3: 5G_ProSe_Ph3 status after SA2#164
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040030 | Proximity-based Services in 5GS – Phase 3 | 5G_ProSe_Ph3 | 18/12/2024 | 0% | SP-240988 | 70% | Progressed
  Progress since SA2#164
  10 CRs agreed.
  Normative text has been added to support multi-hop UE-to-Network and UE-to-UE relay.
  Impacts and dependencies on other WGs
  Layer 2 UE-to-Network Relay has dependencies in related work item in RAN.
  Input required from SA3 on security related questions.
Next steps
  Continue normative work.

## Slide 4
Total 3.5 TUs
  2 TUs for Study Phase
  1.5 TUs for Normative Work
5G_ProSe_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 | 0.5 | Solutions
SA2#162 | Apr 2024 | 0.5 | 0.5 | New solution aspects/Solution Updates, Evaluations, Conclusions
SA2#163 | May 2024 | 0.5 | 0.5 | Evaluations, Conclusions
SA2#164 | Aug 2024 | 1 | 1 | Normative work, finalize the TR conclusions
SA2#165 | Oct 2024 | 0 |  | -
SA2#166 | Nov 2024 | 0.5 |  | Normative work, coordination with RAN and SA3 if needed
 | Total | 3.5 |  |