## Slide 1: FS_UPEAS_Ph2 Status Report
Jinguo Zhu(ZTE)
Susana Sabater(Vodafone)

## Slide 2: FS_UPEAS_Ph2 Status after SA2#164
  Progress since SA2#164
  15 CRs are handled and 12 CRs were approved.
  KI#1: 5 CRs were approved.
  KI#2: 7 CRs were approved
  KI#3: 3 CRs were discussed and in good shape. Further work at next meeting
  RAN impacts and dependencies
  No RAN dependency
Contentious issues
  None
Next steps(SA2#165)
  Continue normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS_Ph2 | Study on UPF enhancement for Exposure and SBA Phase 2 | 100% -> 100% | June 2024 | 10210003
UPEAS_Ph2 | UPF enhancement for Exposure and SBA Phase 2 | 0% -> 65% | Dec 2024 | 1040035

## Slide 3: FS_UPEAS_Ph2 Status after SA#104
  Progress since SA#104
  Start normative work at SA2#164
  15 CRs are handled and 12 CRs were approved.
  All key issues were in good shape. Continue the normative work at next meeting
  RAN impacts and dependencies
  No RAN dependency
Contentious issues
  None
Next steps(SA2#165)
  Continue normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS_Ph2 | Study on UPF enhancement for Exposure and SBA Phase 2 | 100% -> 100% | June 2024 | 10210003
UPEAS_Ph2 | UPF enhancement for Exposure and SBA Phase 2 | 0% -> 65% | Dec 2024 | 1040035

## Slide 4
FS_UPEAS_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.25 | 0.25 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 | 0.5 | Solutions
SA2#162 | Apr 2024 | 1 | 1 | Solution Updates, new solutions, Evaluations
SA2#163 | May 2024 | 0.5 | 1 | Evaluations, Conclusions
SA2#164 | Aug 2024 | 1 | 1 | Start Normative work
SA2#165 | Oct 2024 | 0.75 |  | Continue normative work
SA2#166 | Nov 2024 | 0.5 |  | Complete the normative work
 | Total | 4.5 |  | 
Total 4.5 TUs
  2.25 TUs for Study Phase
  2.25 TUs for Normative Work