## Slide 1: Status report for Study on Energy Efficiency and Energy Saving (FS_EnergySys)
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: FS_EnergySys Status at SA#105
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 99% | SP-231192 | 100% | Study has been completed
  Progress since SA#104
  TR 23.700-66 v1.1.0 is submitted to TSG SA for approval
  1 pCR has been accepted for the update of study conclusion on KI#1
  Working Agreement on KI#1 has been established
  Impacts and dependencies on other WGs:
  Potential RAN support for UE Energy Consumption report requires feedback from RAN WGs for normative work alignment
  Contentious issues
  The content of the study conclusion for KI#1 was subject to the Working Assumption at SA2#164. If the WA is challenged this may be a contentious issue for TSG SA to resolve.
  Next Steps
  Start the normative work based on the study conclusions and the WID

## Slide 3: FS_EnergySys Status after SA2#164
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 99% | SP-231192 | 100% | Study has been completed
  General
  Total 51 TDocs were submitted for 2 TU sessions
  The meeting focused on the TR conclusions updates to prepare submission to SA plenary for approval
  5 pCRs on Key Issue Conclusions, 2 DRAFTCR on EC consumption information collection and 3 LSs were handled
  1 pCR for update of KI#1 conclusion was approved, 2 LS in/out were postponed, and 1 LS out is under email approval
  TR 23.700-66 v1.1.0 is available and submitted to TSG SA for information and approval

## Slide 4: FS_EnergySys Status after SA2#164
  Progress since SA2#163
  Conclusion for Key Issue #1 has been updated based on the Working Agreement established during the meeting
  SA2/SA5 Work Split was discussed in the NWM before the SA2#164 meeting
  2 DRAFT CRs on ECF-based (SA2) and CHF-based (SA5) solutions were reviewed in the meeting to make decision on the SA2/SA5 work split
  RAN impacts and dependencies
  Whether the NG-RAN will provide per-UE level energy consumption and energy state information in this release depends on RAN WGs decision
  Contentious issues
  The content of the study conclusion for KI#1 was subject to the Working Assumption at SA2#164. If the WA is challenged this may be a contentious issue for TSG SA to resolve.
  Plans for upcoming meetings
  SA2#165: Start the normative work

## Slide 5: FS_EnergySys Work Plan
Total 13 TUs
  8.5 TUs for Study Phase
  4.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 | 1 | Focus on solution updates, only unhandled new solution proposals from #161, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 | 1 | Critical solution updates only, Complete study conclusion, Prepare a WID proposal for normative work based on conclusion
SA2#164 | Aug 2024 | 2 | 2 | Complete study conclusions, Submit a WID proposal to SA#105
 | Total | 8.5 |  |