## Slide 1: TEI19_ MINPA WI Status Report
Belen Pancorbo - Ericsson (Rapporteur)

## Slide 2: TEI19_ MINPA WI Status after SA2#164
  Progress since SA#104
  2 CRs were submitted to TS 23.503 and 1 CR was submitted to TS 23.502.
  All submitted CRs were agreed/
  RAN impacts and dependencies
  No RAN dependency
Contentious issues
  None
Next steps
  This WID is completed
WI Code | Work Item Title | WP | Target Date | WID#
TEI19_MINPA | Minimize the Number of Policy Associations | 0 -> 100% | Dec, 2024 | SP-240118

## Slide 3
Overall Plan
TEI19_MINPA status after SA2#163
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#161 | Feb 2024 | --- | --- | WID approved.
SA2#162 | April 2024 | 0.5 | 0.5 | Start normative work. CRs to 23.502 and 23.503 agreed.
SA2#163 | May 2024 | 0.5 | 0.25 | Complete normative work. Updated CR to 23.503 agreed.
 | Total | 1 | 0.75 |