## Slide 1
FS_UIA_ARC, UIA_ARC
Status Report
A.I. 19.8.1 and 19.8.2
Mike Starsinic (Rapporteur)
InterDigital
S2-2411125 - 3GPP SA2#165, October 14-18 2024, Hyderabad, India
© 3GPP 2024

## Slide 2: FS_UIA_ARC/UIA_ARC after SA2 #165
FS_UIA_ARC Progress since SA #105
  Based on the guidance that SA Plenary endorsed in SP-241401, 1 p-CR was approved which concludes that no normative work will take place in Rel-19 for Key Issues 1, 2, and 3.
  TR 23.700-32 was sent to SA for approval.
UIA_ARC Progress since SA #105
  48 documents were submitted to SA2 #165. 11 were handled, 8 were Approved, and 3 were postponed.
Impacts and dependencies on other WGs: none identified
  None identified
Contentious Issues
  Whether the URSP Rule should be updated to include the Non-3GPP Device Identifier as a Traffic Descriptor
Issues that Require More Discussion
  Whether the PDU Session Establishment Request can include a User Plane Address.
  The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
  Some questions about the using DHCPv6 to associate the Non-3GPP Device Identifier with a User Plane Address.
Next Steps
  Continue to progress CRs.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 30/06/2024 | 93% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 30/12/2024 | 15% | SP-240971 | 45% | 

## Slide 3: FS_UIA_ARC Work Plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 1.5 | 1.5 | Key Issue Updates (e.g. KI#4 editor’s note), Solutions
SA2#162 | Apr 2024 | 1.75 | 1.75 | Solutions that apply to a KI with no/few existing solutions in the TR (i.e. FS_UIA_ARC Key Issue #4), New solutions significantly different to existing one and proposed in a previous meeting but not handled, Solution Updates will be lower priority than KI#4 solutions and new solutions that are significantly different to existing one and proposed in a previous meeting but not handled. Time needs also to be given to papers that propose conclusions/solution principles. NOTE: During the meeting, no solution updates were handled.
SA2#163 | May 2024 | 1.5 | 1.5 | Critical Solution Updates, Complete Study Conclusions NOTE: During the meeting, no solution updates were handled.
SA2#164 | Aug 2024 | X | 1 | Request to allocate 1 TU for FS_UIA_ARC (Key Issues #1, #2, and #3).
SA2#165 | Oct 2024 | X | 0 | 1 p-CR was agreed to conclude that there will be no normative work for key issues 1, 2, and 3.
 | Total | 5.25 | 6.25 | 

## Slide 4: UIA_ARC Work Plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 0.5 | 0.5 | Handle CRs
SA2#165 | Oct 2024 | 0.5 | 1 | Handle CRs
SA2#166 | Nov 2024 | 0.5 |  | Continue to progress CRs: Progress postponed CRs. Resolve Editor’s Notes in Approved CRs. The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
 | Total | 1.5 | 1.5 |