## Slide 1: Rel-19 FS_eEDGE_5GC_Ph3/ eEDGE_5GC_Ph3 Status Report
Intel (Rapporteur)

## Slide 2
Progress since SA#105
  eEDGE_5GC_Ph3:
    47 papers were received, 13 CRs were approved, 4 CRs were postponed due to controversy.
  Impacts and dependencies on other WGs:
  None.
Controversial issues:
  KI#1: I-SMF selection, AF traffic influence information usage at I-SMF.
Next steps:
  Process the CRs for KI#1 and #2.
  Resolve the controversial issue for KI#1.
FS_eEDGE_5GC_Ph3/ eEDGE_5GC_Ph3
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 100% | 100% | Sep. 2024 | SP-231796 | 
1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 30% | 70% | Dec. 2024 | SP-240996 | 

## Slide 3
Total 7.5 TUs
  4.5 TUs for Study Phase
  3 TUs for Normative Work, 1 TU for each meeting in 2nd half of 2024.
FS_eEDGE_5GC_Ph3/ eEDGE_5GC_Ph3 Work plan
Meeting# | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 1.5 | 1.5 | New solutions
SA2#162 | Apr 2024 | 1.5 | 1.5 | New solutions, solution update, evaluation if possible, conclusion if possible
SA2#163 | May 2024 | 1 | 1 | Evaluation, conclusion
SA2#164 | Aug. 2024 | 1 | 1 | Final conclusion for KI#3, process CRs for normative work
SA2#165 | Oct. 2024 | 1 |  | Process CRs for normative work
SA2#166 | Nov. 2024 | 1 |  | Process CRs for normative work

## Slide 4
Backup slides

## Slide 5: FS_eEDGE_5GC_Ph3 status report to SA#103
WI Code | Work Item Title | WP | Target Date | WID#
FS_eEDGE_5GC_Ph3 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | 50% | June 2024 | SP-231796
Progress since SA#102:
  57 papers were received, 15 papers were not handled due to TU budget/quota limitation or lack of session time.
  31 papers were approved in total:
    1 paper for TR skeleton and 1 paper for scope;
    1 paper for Architecture assumption and 1 paper for Architecture requirements;
    3 Key Issues papers;
    1 Key Issue update paper;
    7 solution papers for key issue #1;
    9 Solution papers for key issue #2;
    7 solution papers for key issue #3.
  Impacts and dependencies on other WGs
  None
Contentious issue:
  None.
Plan for SA2#162:
  Process the unhanded papers at SA2#161, new solution papers and solution update papers.
  Kick off the early evaluation and conclusion for some stable key issues if possible.

## Slide 6: FS_eEDGE_5GC_Ph3 status report to SA#104
WI Code | Work Item Title | WP | Target Date | WID#
FS_eEDGE_5GC_Ph3 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | 75%->90% | June 2024 -> Sep. 2024 | SP-231796
General
  Since SA2#161, 64 papers were received, 33 papers were approved.
  WID is approved, TR Coversheet for 23.700-49 is sent to SA Plenary for information.
  Key Issue #1 and #2 are completely concluded, interim conclusion is reached for KI#3:
    For key issue #1, final conclusion is made to move forward with I-SMF based solution.
    For key issue #2, final conclusion is made to move forward with SMF collecting N6 delay from UPF in normative phase; EAS load aspect and NWDAF analytics aspect will not be pursued in normative phase.
    For key issue #3, interim conclusion is made, further discussion on solution principle is needed at SA2#164.
Contentious issue
  Solution principle for KI#3 conclusion, potential SoH on KI#3 conclusion may be needed.
Plan for SA2#164
  Process the CRs for KI#1 and #2.
  Reach final conclusion for key issue#3.

## Slide 7: FS_eEDGE_5GC_Ph3/eEDGE_5GC_Ph3 Status Report to SA#105
Progress since SA#104
  FS_eEDGE_5GC_Ph3:
    2 papers were approved including 1 evaluation paper and 1 conclusion paper for KI#3.
    TR 23.700-49 is sent to SA Plenary for approval.
  eEDGE_5GC_Ph3:
    71 papers were received, 7 CRs were approved, 11 CRs were postponed due to lack of revision session time, all other CRs were merged into selected baseline CRs.
    The WID was revised to remove the justification for KI#3.
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  Finalize the normative work in accordance with the conclusions drawn by the TR and as specified in the WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eEDGE_5GC_Ph3 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | 90%->100% | Sep. 2024 | SP-231796
eEDGE_5GC_Ph3 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | 0%->30% | Dec. 2024 | SP-240996