## Slide 1: FS_MASSS & MASSS Status Report
Krisztian Kiss (Primary Rapporteur)
Apple
Zhuoyi Chen (Secondary Rapporteur)
China Telecom

## Slide 2: FS_MASSS / MASSS status after SA2#166
  Progress since SA#105:
  MASSS: Focus was on normative CRs for KI#2.1
    19 Tdocs (18 CRs and 1 discussion paper) were submitted and 6 CRs were approved (TS 23.501/23.502/23.503)
  Impacts and dependencies on other WGs:
  None
Controversial Issues:
  None
Next steps:
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-231802 | 100% | 
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 80% | SP-240994 | 100% | 

## Slide 3
Total 11.5 TUs
  7.5 TUs for Study Phase and 4 TUs for Normative Work
FS_MASSS / MASSS Work plan
Meeting | Date | Planned TUs | Actual TUs | Action plan
SA2 #160AH-e | Jan. 2024 | 1.5 | 1.5 | TR skeleton, TR scope, Terms, Architectural assumptions Key Issues for all WTs.
SA2#161 | Feb 2024 | 2 | 2 | Terms, Architectural assumptions/requirements for DualSteer, Postponed Key Issues for WT#1.3, Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#162 | Apr 2024 | 2 | 2 | In priority order: New solutions for DualSteer, Architectural assumptions/requirements & Terms and definitions for DualSteer, Evaluation and conclusion for ATSSS_Ph4 (conclusion on SA3 dependencies need to wait for SA3 feedback), Solution updates for ATSSS_Ph4, New solutions for ATSSS_Ph4. No new KI is allowed.
SA2#163 | May 2024 | 2 | 2 | In priority order: Conclusions, Solution updates (see NOTE), Architectural assumptions/requirements and terms and definitions for DualSteer. Send TR for Information. WID approval. NOTE: For DualSteer, contributors should target one of the existing 19 solutions with updates. New solutions for DualSteer may be treated only if no existing solutions could serve as "framework" for the contribution.
SA2#164 | Aug 2024 | 2 | 2 | Allocate 2 TUs during SA2#164 for FS_MASS & MASSS DualSteer conclusions, Normative work on KI#2.1, confirm final conclusion for KI#2.2
SA2#165 | Oct 2024 | 0.5 | 1 | Allocate 1 TU during SA2#165 for MASSS KI#2.1 work
SA2#166 | Nov 2024 | 0.5 | 1 | Allocate 1 TU during SA2#166 to complete the normative work for KI#2.1.
 | Total | 10.5 | 11.5 | 

## Slide 4: FS_MASSS / MASSS status at SA#106
  Progress since SA#105
  FS_MASSS: Based on the guidance that SA Plenary endorsed in SP-241401, 1 pCR was approved which updates “interim conclusion” to final “conclusion” for KI#2.2
  MASSS: Focus was on normative work for KI#2.1. 40 Tdocs were submitted and 7 CRs were approved for TS 23.501/502/503
  RAN impacts and dependencies
  None
Contentious issues:
  None
Next steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-231802 | 100% | 
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 50% | SP-240994 | 100% | 

## Slide 5: Backup

## Slide 6: FS_MASSS / MASSS status after SA2#165
  Progress since SA#105:
  FS_MASSS: Based on the guidance that SA Plenary endorsed in SP-241401, 1 pCR was approved which updates “interim conclusion” to final “conclusion” for KI#2.2
    TR 23.700-54 was sent to SA for approval
  MASSS: Focus was on normative CRs for KI#2.1
    20 Tdocs (17 CRs and 3 discussion papers) were submitted and 6 CRs were approved (TS 23.501/23.502/23.503)
  Impacts and dependencies on other WGs:
  None
Controversial Issues:
  Whether MPQUIC-IP should be bundled with support for ATSSS-LL with Active-Standby
  Whether ATSSS-LL with any Steering mode should remain mandatory in Rel-19 or ATSSS-LL with any Steering mode should be optional and MPQUIC-E can also be supported as only Steering Functionality
  Whether both ATSSS-LL and MPQUIC-E functionalities can be supported for the same MA PDU Session
Next steps:
  Agree the remaining CRs on UE-network capability negotiation
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 09/09/2024 | 100% | SP-231802 | 100% | 
1040034 | Multi-Access (ATSSS_Ph4) | MASSS | 12/12/2024 | 50% | SP-240994 | 80% | 

## Slide 7: FS_MASSS status at SA#105
  Progress since SA2#163
  Focus was on Conclusions
  65 TDocs were submitted and 10 TDocs on Conclusions were handled
  SA2 will not proceed with normative work for KI#1.x and KI#2.2
  RAN impacts and dependencies
  None
Contentious issues:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 70% -> 100% | September 2024 | 1020070

## Slide 8: MASSS status at SA#105
  Progress since SA2#163
  SA2#164 was the first meeting where CRs were handled
  21 contributions were submitted, all were handled
    6 CRs were postponed
    2 CR was noted
    13 CRs were merged
  The focus of the meeting was on CRs for TS 23.501, TS 23.502 and TS 23.503
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Continue to progress CRs
WI Code | Work Item Title | WP | Target Date | WID#
MASSS | Multi-Access (ATSSS_Ph4) | 0% -> 50% | December 2024 | 1040034

## Slide 9: FS_MASSS Status after SA2#164
  Progress since SA2#163
  Focus was on Conclusions
  65 TDocs were submitted and 10 TDocs on Conclusions were handled
  SA2 will not proceed with normative work for KI#1.x and KI#2.2
  RAN impacts and dependencies
  None
Contentious issues:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 70% -> 100% | September 2024 | 1020070

## Slide 10: MASSS Status after SA2#164
  Progress since SA2#163
  SA2#164 was the first meeting where CRs were handled
  21 contributions were submitted, all were handled
    6 CRs were postponed
    2 CR was noted
    13 CRs were merged
  The focus of the meeting was on CRs for TS 23.501, TS 23.502 and TS 23.503
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Continue to progress CRs
WI Code | Work Item Title | WP | Target Date | WID#
MASSS | Multi-Access (ATSSS_Ph4) | 0% -> 50% | December 2024 | 1040034

## Slide 11: FS_MASSS status at SA#104
Progress since SA#103:
  TR 23.700-54 v0.4.0 is available, sent to SA#104 for Information.
  29 contributions agreed including New/updated solutions for DualSteer, New/updated solutions and Conclusions for ATSSS_Ph4
  All TUs are used for the Study Phase
  ATSSS_Ph4 KI#2.1 conclusions agreed, WID approved including this KI
  ATSSS_Ph4 KI#2.2 interim conclusion agreed: no consensus to move to normative phase
  DualSteer KI#1.3 solution principles are discussed but not agreed. Other open issues for DualSteer KIs (KI#1.1, KI#1.2, KI#1.4) were discussed in NWM discussion and drafting sessions but no time to handle conclusion proposals during online sessions
Impacts and dependencies on other WGs:
  Key Issue #1.x have SA3 dependencies to handle security aspects.
Contentious issues:
  Principles of DualSteer, e.g. Session Management, how to correlate the 2 PDU Sessions by the 2 SUPIs, etc.
  Whether to define primary and secondary SUPI concept and if yes, whether it is part of subscription data
Next steps:
  Start normative work based on KI#2.1
  Confirm final conclusion for KI#2.2 during SA2#164
  Complete KI#1.x conclusions during SA2#164
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 30% -> 70% | June 2024 | 1020070

## Slide 12: FS_MASSS Status after SA2#163
  Progress since SA2#162
  Focus was on Conclusions. TR 23.700-54 v0.4.0 is available, sent to SA#104 for Information
  105 TDocs were submitted and 101 tdocs could not be handled. The handled documents included:
    DualSteer solution update: KI#1.4 (1 tdoc)
    ATSSS_Ph4 KI#2.x conclusions: 2 tdocs Agreed
    SoH questions (Noted)
  KI#2.1 conclusions agreed, WID approved including this KI
  KI#2.2 interim conclusion agreed: no consensus to move to normative phase
  KI#1.3 solution principles are discussed but not agreed. KI#1.1, KI#1.2, KI#1.4 open issues were discussed in NWM discussion and drafting session but no time to handle conclusion proposals on solution principles during online sessions
  RAN impacts and dependencies
  Key Issue #1.x have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues:
  Principles of DualSteer, e.g. Session Management, how to correlate the 2 PDU Sessions by the 2 SUPIs, etc.
  Whether to define primary and secondary SUPI concept and if yes, whether it is part of subscription data
Next steps
  Start normative work based on KI#2.1
  Confirm final conclusion for KI#2.2 during SA2#164
  Organize offline discussion before SA2#164 for DualSteer Key Issues
  Complete KI#1.x conclusions during SA2#164
  Send TR 23.700-54 to SA for approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 60% -> 70% | June 2024 | 1020070

## Slide 13: FS_MASSS Status after SA2#162
  Progress since SA2#161
  Focus was on New Solutions for DualSteer, New/updated solutions for ATSSS_Ph4 and Conclusions for ATSSS_Ph4 KI#2.1
  TR 23.700-54 v0.3.0 is available
  94 TDocs were submitted and 64 tdocs could not be handled. The handled documents included:
    DualSteer new solutions: KI#1.x (7 tdocs), KI#1.1 & 1.2 (4 tdocs), KI#1.3 (3 tdocs), KI#1.4 (5 tdocs), KI#1.3 & 1.4 (1 tdoc): 19 tdocs Agreed, 1 Merged
    ATSSS_Ph4 solution updates: KI#2.1 (3 tdocs): All (3) tdocs Agreed
    ATSSS_Ph4 new solutions: KI#2.1 (3 tdocs) KI#2.2 (3 tdocs): 5 tdocs Agreed, 1 tdoc Noted
    ATSSS_Ph4 KI#2.1 conclusions: 1 tdoc Postponed
  All KIs have solutions after this meeting
  RAN impacts and dependencies
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues:
  Issues identified during SA2#160AH-e/#161 remain unresolved (see slide 6)
  Whether to support CONNECT-TCP as part of KI#2.1 conclusions
Next steps
  Send TR 23.700-54 to SA for information
  Propose WI to start normative work in Q3
  In the next meeting: Complete Study Conclusions, Solution Updates (see NOTE on slide 3), Architectural assumptions/requirements & terms and definitions for DualSteer
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 30% -> 60% | June 2024 | 1020070

## Slide 14: FS_MASSS status at SA#103
Progress since SA#102:
  TR 23.700-54 v.0.2.0 was created based on approved contributions.
  20 contributions agreed including TR skeleton, Scope, Architectural Assumptions and Requirements for ATSSS_Ph4, 6 key issues and 8 solutions addressing KI#2.1 & KI#2.2 (ATSSS_Ph4).
  Terms and Architectural Assumptions and Requirements for DualSteer were not approved after 2 meetings due to disagreement whether SA1 definitions require any Stage-2 alignments or not.
  3.5 TUs are used and 4 TUs are left for the Study Phase.
Impacts and dependencies on other WGs:
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects.
Contentious issues:
  DualSteer KIs may be at risk not to be completed by May 2024 if common understanding on DualSteer Device definition cannot be reached.
Next steps:
  New solutions for DualSteer Key Issues.
  Agree Architectural assumptions/requirements and terms and definitions for DualSteer.
  Solution evaluation and conclusions, prepare sending TR for approval. Plan LS to SA3 based on agreed solutions.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 06/03/2024 | 0% | SP-231802 | 30% | SID to be updated by S2-2401315

## Slide 15: FS_MASSS Status after SA2#161
  Progress since SA2#160AH-e
  TR 23.700-54 v0.2.0 is available.
  72 TDocs were submitted and 25 tdocs could not be handled. The handled documents included:
    Terms and Architectural Assumptions/Requirements (12 tdocs)
    Key Issue for WT#1.3 (13 tdocs), updates to KIs (2 tdocs)
    ATSSS_Ph4 solutions: KI#2.1 (7 tdocs) & KI#2.2 (13 tdocs), DualSteer solution to KI#1.1 (1 tdoc)
  Updated Architectural Assumptions/Requirements for ATSSS_Ph4, 2 key issues for WT1.3, Updated KI#2.2, 4 new solutions to KI#2.1 and 4 new solutions to KI#2.2 were approved
  Terms and Architectural Assumptions and Requirements for DualSteer were noted
  RAN impacts and dependencies
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues:
  DualSteer Device definition by SA1 has been challenged by some companies. Disagreement whether it requires any Stage-2 alignments
  Whether both traffic steering and switching requires anchoring in 5GC or only traffic switching
  Whether two registered accesses are required to initiate traffic steering or switching in DualSteer, or whether traffic steering or switching could trigger second RAT/PLMN registration
Next steps
  In the next meeting: Agree new solutions for DualSteer Key Issues, Architectural assumptions/requirements and terms and definitions for DualSteer, Evaluation and conclusion of ATSSS_Ph4, Solution updates & new solutions for ATSSS_Ph4 Key Issues.
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 9% -> 30% | June 2024 | 1020070

## Slide 16: FS_MASSS Status after SA2#160AH-e
  Progress since SA#102
  Study started in SA2#160AH-e, TR 23.700-54 v0.1.0 is available.
  71 TDocs were submitted and 24 tdocs could not be handled due to TU budget. The handled documents included:
    TR skeleton, Scope (2 tdocs)
    Terms, and Architectural Assumptions/Requirements (5 tdocs)
    40 Key Issue Proposals
  TR skeleton, Scope, Architectural Assumptions/Requirements for ATSSS_Ph4, and 4 key issues were approved (1 KI for WT#1.1, 1 KI for WT#1.2, 1 KI for WT#2 and 1 KI for WT#3)
  Terms, Architectural Assumptions and Requirements for DualSteer and 2 key issues were postponed (2 KIs for WT#1.3)
  RAN impacts and dependencies
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues
  DualSteer Device definition by SA1 has been challenged by some companies. Disagreement whether it requires any Stage-2 alignments
  Whether both traffic steering and switching requires anchoring in 5GC or only traffic switching
  Whether two registered accesses are required to initiate traffic steering or switching in DualSteer, or whether traffic steering or switching could trigger second RAT/PLMN registration
Next steps
  In the next meeting: Agree terms, Architectural assumptions/requirements for DualSteer, Postponed Key Issues for WT#1.3, New solutions for approved Key Issues.
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 0% -> 9% | June 2024 | 1020070