## Slide 1: FS_NG_RTC_Ph2/NG_RTC_Ph2 Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC_Ph2/NG_RTC_ph2 status after SA2#165
General
  38 contributions were submitted to #165 and 20 contributions were handled, with 11 CRs agreed
  Achievements:
    The way forward of controversial IMS AS service issue of KI#1 has been agreed after SoH, with which the architecture and service design of event exposure has been agreed
    Contributions related to KI#4 and 5 were handled and the basis contributions were agreed
    A starting point for the architecture to support avatar communication was agreed
    Updates on KI#2, 3 and 6 were agreed
  Controversial issues
    Procedures of Avatar communication need further discussion and coordination with SA4
    Support of authentication and authorization check at IMS AS and/or S-CSCF and how to provision RCD info needs further discussion
  RAN impacts and dependencies:
  None
Next steps:
  Remove the remianing EN of KI#6 in the TR and send the TR for approval
  Continue normative work and try to complete KIs as much as possible
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 95% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 10% | SP-241384 | 40% | 

## Slide 3: FS_NG_RTC_Ph2/NG_RTC_ph2 status after SA2#166
General
  46 contributions were submitted to #166 and 25 contributions were handled, with 15 CRs agreed
  Achievements:
    Controversial issues of KI#4 have been solved and the related CRs were agreed
    Functional descriptions and procedures of KI#7 supporting DC multipelxing were agreed
    Basic architecture and procedures of KI#8 Avatar communication were agreed
    CRs from #165 on KI#1, 2, 3 and 6 were further updated and agreed to solve ENs
  TR 23.700-77 was sent for approval after EN in KI#6 was removed
  An exception sheet to extend the completion time to March 2025 was sent to SA#106, with remaining issues below
    WT8
      Usage of URL of DC AS for downloading the avatar ID list
      How the MF interacts with BAR for direclty downloading avatar representation
      Whether and how to download Avatar representation via bootstrap DC
    WT7:
      Whether and how the originating network handles the scenario of standalone IMS DC session when the terminating network rejects the session due to not supporting DC multiplexing
      Updates on services of IMS AS and MF
    WT5
      How IMS AS reports PS data off status to DCSF
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 100% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 40% | SP-241384 | 70% | An exeption is to sent to SA#106 to request an extendion of completion

## Slide 4: FS_NG_RTC_Ph2/NG_RTC_ph2 status after SA2#166
  An exception sheet to extend the completion time to March 2025 was sent to SA#106, with remaining issues below (cont’)
    WT2
      Detailed call flows for the IMS AS behavior when updating and deleting an IMS session
  Controversial issues
    None
  RAN impacts and dependencies:
  None
Next steps:
  If the exception is granted from SA plenary, continue normative work and complete all remaining issues for all KIs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 100% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 40% | SP-241384 | 70% | An exeption is to sent to SA#106 to request an extendion of completion

## Slide 5: FS_NG_RTC_Ph2/NG_RTC_ph2 status at SA#106
General
  In SA2 #165/166 meetings 84 contributions were submitted and 45 contributions were handled with 26 CRs agreed
  Achievements:
    Controvarsial issues of KI#1, KI#2, KI#4 and KI#6 were solved with SoH and offline discussions
    Archiectures and basic procedures of all KIs were discussed and agreed
    TR 23.700-77 was sent for approval after EN in KI#6 was removed
  An exception sheet to extend the completion time to March 2025 was sent to SA#106, with no controversial issue
    WT8
      Usage of URL of DC AS for downloading the avatar ID list
      How the MF interacts with BAR for direclty downloading avatar representation
      Whether and how to download Avatar representation via bootstrap DC
    WT7:
      Whether and how the originating network handles the scenario of standalone IMS DC session when the terminating network rejects the session due to not supporting DC multiplexing
      Updates on services of IMS AS and MF
    WT5
      How IMS AS reports PS data off status to DCSF
    WT2
      Detailed call flows for the IMS AS behavior when updating and deleting an IMS session
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 100% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 10% | SP-240985 | 70% | An exception is to sent to SA#106 to request an extention of completion

## Slide 6: FS_NG_RTC_Ph2/NG_RTC_ph2 status at SA#106
  Controversial issues
    Remaining issues as listed in exception sheet
  RAN impacts and dependencies:
  None
Next steps:
  If the exception is granted from SA plenary, continue normative work and complete all remaining issues for all KIs
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 12/12/2024 | 95% | SP-231196 | 100% | Completion target chenges to December 2024 to remove the remaining EN in KI#6
1040026 | System architecture for next generation real time communication services phase 2 | NG_RTC_Ph2 | 12/12/2024 | 10% | SP-240985 | 70% | An exception is to sent to SA#106 to request an extention of completion

## Slide 7
FS_NG_RTC_Ph2&NG_RTC_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #159 | Oct. 2023 | 1 | 1 | TR skeleton, scope and achitectural assumptions were agreed; 5 Key Issues were agreed.
SA2 #160 | Nov. 2023 | 1.5 | 1.5 | All 8 KIs were agreed; Started discussions on solutions.
SA2 #160AH-e | Jan. 2024 | 1 | 1 | Discussions on solutions
SA2 #161 | Feb 2024 | 1 | 1 | Discussions on solutions;
SA2 #162 | Apr 2024 | 1 | 1 | Discussions on solutions; Last meeting for new solution proposals; Start discussion on evaluation and conclusion;
SA2 #163 | May 2024 | 0.5 | 0.5 | Complete conclusions; Send TR for approval or for information.
SA2 #164 | Aug. 2024 | 2 | 2 | Start normative work
SA2 #165 | Oct. 2024 | 1.5 | 1.5 | Continue normative work
SA2 #166 | Nov. 2024 | 2 | 2 | Continue normative work
 | Total | 11.5 | 11.5 | 
Total 11.5 TUs
  6 TUs for study phase
  5.5 Tus for normative work

## Slide 8
Backup

## Slide 9: FS_NG_RTC_ph2 status after SA2#164
General
  10 contributions were submitted to #164 and 8 contributions were handled
  Achievements:
    Two reply LS on data channel application related capability exposure and SA6 new WI were sent out to SA6
  The TR 23.700-77 was not udpated and thus was not sent for approval in this meeting
  Controversial issues
    None
  RAN impacts and dependencies:
  None
Next steps:
  send the TR for approval at SA#106
  continue normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 95% | June, 2024 | 1010030

## Slide 10: NG_RTC_ph2 status after SA2#164
General
  45 contributions were submitted to #164 and 20 contributions were handled
  Achievements:
    Contributions on 5 KIs (KI#1, 2, 6, 8 and 3) were handled
    Procedures for KI#2, #3 and #6 were agreed
  Controversial issues
    Wether IMS AS event exposure is defined as a new service or extension of exisiting service needs further discussion and decision before next SA2 meeting
    Architecture of Avatar communication needs further discussion and coordination with SA4
  RAN impacts and dependencies:
  None
Next steps:
  continue normative work, covering all the KIs
WI Code | Work Item Title | WP | Target Date | WID#
NG_RTC_Ph2 | System architecture for next generation real time communication services phase 2 | 0%->10% | December, 2024 | 1040026

## Slide 11: FS_NG_RTC_Ph2/NG_RTC_ph2 status at SA#105
General
  55 contributions were submitted to #164 and 28 contributions were handled
  Achievements:
    Contributions on 5 KIs (KI#1, 2, 6, 8 and 3) were handled
    Procedures for KI#2, #3 and #6 were agreed
    Two reply LS on data channel application related capability exposure and SA6 new WI were sent out to SA6
  Controversial issues
    Wether IMS AS event exposure is defined as a new service or extension of exisiting service needs further discussion and decision before next SA2 meeting
    Architecture of Avatar communication needs further discussion and coordination with SA4
  RAN impacts and dependencies:
  None
Next steps:
  send the TR for approval at SA#106
  continue normative work, covering all the KIs
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC_Ph2 | Study on system architecture for next generation real time communication services phase 2 | 95% | June, 2024 | 1010030
NG_RTC_Ph2 | System architecture for next generation real time communication services phase 2 | 0%->10% | December, 2024 | 1040026