## Slide 1: Summary of TU plan
SA2 | #167 | #168 | #169 | #170 | #171 | #172 | #173 | #174 | #175 | #176 | #177 | #178
Date | Feb-25 | Apr-25 | May-25 | Aug-25 | Oct-25 | Nov-25 | Feb-26 | Apr-26 | May-26 | Aug-26 | Oct-26 | Nov-26
Milestones and deadlines |  | Start some 5GA |  | Start all 5GA and 6G |  | Complete some 5GA studies | Complete all 5GA studies |  | 5GA Stage 2 80% | 5GA Stage 2 100% |  | 
Pre-Rel-19 maint | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Rel-19 maint | 15 | 11 | 11 | 9 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2
Rel-19 exceptions | 8 |  |  |  |  |  |  |  |  |  |  | 
Rel-20 | 3 | 12 | 12 | 15 | 18 | 18 | 20 | 20 | 20 | 22 | 15 | 15
Rel-20 maint |  |  |  |  |  |  |  |  |  |  | 7 | 7
Total | 31 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
 |  | Duration of 5GA work in Rel-20 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Duration of 6G study work in Rel-20 (tbc) |  |  |  |  |  |  |  | 
 |  | Total TU's for Rel-20 March 25 - September 26 |  |  |  |  | 157 |  |  |  |  | 
 |  | Additional TU's for 6G after September 26 |  |  |  |  | 30 |  |  |  |  | 

## Slide 2: SA2 Rel-20 capacity summary
SA2 capacity (March 2025 – September 2026):
  Max TU’s for release planning purposes: 157
    For 5G Advanced SIDs and WIDs, and 6G SID
  Max number of SIs/WIs: 7- 9 (5G Advanced) – Note: this doesn’t have consensus
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 2 TU’s per meeting (excluding the 6G study)
  Max TU’s overall per feature: 14 TU (excluding the 6G study)
Additional TU’s for 6G study after September 2026: 30 (if study is to complete by December 2026)
Assumptions
  Number of meetings: 9
  Expected total TUs per meeting (for all releases): 30
  Total TUs (for all releases): 270
  TUs for maintenance of past releases: 86
  TUs for additional buffer: 27