## Slide 1: Release 19 MPS4msg Status Report
Robert Streijl
(Rapporteur)

## Slide 2: MPS4msg Status at SA#106
Progress since SA#105
  Continued normative phase.
  10 CRs submitted: 9 agreed, 1 merged.
  Normative work is 100% complete
RAN impacts and dependencies
  None.
Contentious issues
  None.
Next steps
  Maintenance.
WI Code | Work Item Title | WP | Target Date | WID#
1040029 | MPS for IMS Messaging and SMS services | 100% | Dec 2024 | SP-240987

## Slide 3: MPS4msg Status after SA2#166
Progress since SA#105
  Continued normative phase.
  10 CRs submitted - 9 agreed, 1 merged.
  All work tasks in TR 23.700-75 were captured in normative specifications.
    WT#1: Support MPS priority treatment for SIP MESSAGE and SIP sessions-based solutions
    WT#2: Support MPS priority treatment in EPC and 5GC for messaging services using MO/MT SMS over IP; and MO/MT SMS over NAS
    WT#3: Support setting and clearing of MPS for messaging via SCEF and NEF
  Impacts and dependencies on other WGs
  None.
Outstanding issues
  None.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | - | SP-231672 | 100% | 
1040029 | MPS for IMS Messaging and SMS services | MPS4msg | 12/13/2024 | 80% | SP-240987 | 100% | 

## Slide 4: MPS4msg Work Plan
Total 6 TUs
  3 TUs for Study Phase – used 2.25
  3 TUs for Normative Work – used 2
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 1 | 1 | Start normative phase with CRs against all planned TSs as per WID.
SA2#165 | Oct 2024 | 1 | 0 | 
SA2#166 | Nov 2024 | 1 | 1 | Corrections and add support for RAN Paging Priority
 | Total | 3 | 2 | 

## Slide 5: Annex MPS4msg

## Slide 6: MPS4msg Status at SA#105
Progress since SA#104
  Started normative phase.
  15 Normative Change Requests submitted: 10 agreed (including content of 3 merged), and 2 noted (alternative solutions identified).
RAN impacts and dependencies
  None
Contentious issues
  None
WI Code | Work Item Title | WP | Target Date | WID#
1040029 | MPS for IMS Messaging and SMS services | 80% | Dec 2024 | SP-240987

## Slide 7: MPS4msg Status after SA2#164
  General
  Study (FS_MPS4msg) and WID (MPS4msg) were approved at SA#104 (Jun 24).
  Started normative phase in SA2#164 (Aug 24).
  15 normative CRs submitted. 10 agreed, 3 merged, 2 noted.
  Agreed CRs will be sent to SA#105 for approval
  RAN or Other WG impacts and dependencies
  None
  Contentious issues
  None
Next steps
  Outstanding topics will be identified before next meeting.
  1 TU used, 2 TUs left
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | - | SP-231672 | 100% | 
1040029 | MPS for IMS Messaging and SMS services | MPS4msg | 10/12/2024 | 0% | SP-240987 | 80% |