## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #167 Athens
February 17 – February 21, 2025

## Slide 2: Rel-19 timelines
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…)
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
100%
SA1 Stage 1 80%
SP-230390 - 3GPP TSG#99, 20 -24 March 2023, Rotterdam, The Netherlands

## Slide 3: SA2 and SA meeting dates for 2025
Q1 | SA2-Ad Hoc | Monday, January 20, 2025 | Friday, January 24, 2025 | Electronic
 | SA2#167 | Monday, February 17, 2024 | Friday, February 21, 2025 | Athens, Greece
 | SA#107 | Tuesday, March 12, 2024 | Friday, March 14, 2025 | Incheon, Korea
Q2 | SA2#168 | Monday, April 07, 2024 | Friday, April 11, 2025 | Goteborg, Sweden
 | SA2#169 | Monday, May 19, 2024 | Friday, May 23, 2025 | Fukuoka, Japan
 | SA#108 | Tuesday, June 10, 2024 | Friday, June 13, 2025 | Prague, Czech Republic
Q3 | SA2#170 | Monday, August 25, 2024 | Friday, August 29, 2025 | Goteborg, Sweden
 | SA#109 | Tuesday, September 16, 2024 | Friday, September 19, 2025 | China
Q4 | SA2#171 | Monday, October 13, 2024 | Friday, October 17, 2025 | China (TBC)
 | SA2#172 | Monday, November 17, 2024 | Friday, November 21, 2025 | Dallas, USA
 | SA#110 | Tuesday, December 09, 2024 | Friday, December 12, 2025 | Baltimore, USA

## Slide 4: Rel-19 planning for SA2 - General
Normative work to complete in SA2#168 (February 2025) for the following
  AIML_CN
  XRM_Ph2
  NG_RTC_Ph2
  5GSAT_Ph3-ARC
Exceptions were granted by SA for continuation of normative work on these items
FS_AmbientIoT
  This was discussed in TSG#106 (December 2024)
    A WID was endorsed and SA2 asked to submit an updated WID to SA#107
    SA2 was asked to complete the study in Q1 2025 with the focus on device 1 and D1T1, and if TU’s allow proceed in 2025 Q1 with PCRs for a new TS and draft CRs on the already concluded aspects

## Slide 5: Rel-20 planning
(See SP-240458 endorsed in SA#103 Maastricht)
Studies for 6G in 3GPP are expected to start from Release 20
  First TSG-wide 6G workshop will be in March 2025
  SA1 SID was approved in Sept 2024
  SA2 SID is expected to be approved in June 2025
  SA2 6G SI completion: Dec. 2026 or Mar 2027 (To be confirmed at a future TSG meeting)
For 5G-Advanced
  18-month. Assuming no delay of Rel-19
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
  5G-Advanced workshop held in December 2024

## Slide 6: Rel-20 planning – 5G Advanced
TSG SA endorsed Core Topics and Miscellaneous Topics for 5G-A for SA2 (see SP-241989)
S.No. | Rel-20 Core Topics | Rel-20 Miscellaneous Topics
1 | Integration of satellite components in the 5G architecture Phase 4 | XR and Media Services
2 | AI/ML Enhancements | Indirect Network Sharing Phase 2
3 | Ambient IoT | User Identities and Authentication Architecture - Phase 2
4 | Integrated Sensing and Communication | Enhancements for ePDG based access to 5GC
5 | Energy Efficiency Enhancements | Mission Critical Services, Multimedia Priority Services
6 |  | Industrial network enhancements
7 |  | SMS to emergency centre
8 |  | NG_RTC continuation

## Slide 7: Rel-20 planning – 5G Advanced
The following guidance was given
  SA2 should target a maximum number of 7 Rel-20 5GA SIDs
    NOTE: This limit may be revisited at SA#107 after SA2 reaches an agreement on the 5GA and 6G TU split.
  SA2 shall allocate the TU budget for TEI20 at a level no less than the TEI19 budget in Rel-19.
  SA2 should prioritize following “core” topics for Q1 2025 and should aim to submit SIDs at SA#107 for approval (as per normal consensus). Remaining topics may also be discussed if time permits. If SA2 cannot come to an agreement on these items for SA#107 then they can come for approval at SA#108.
      Integration of satellite components in the 5G architecture Phase 4
      AI/ML enhancements
      Integrated Sensing and Communication
      Energy Efficiency Enhancements
      NOTE: A topic may result in one or more SIDs.
  The “Brief Description and Key Objectives” in SP-241972 should serve as a starting point for the moderated discussion on the candidate topics (as shown in slide#2) and objectives of the candidate topics can be updated during the process.
  Any miscellaneous topics that could not be handled in Q1 2025 will be a candidate for moderated discussion during Q2 2025.
  Any new normative stage-1 requirements from SA1 approved by SA are not precluded from Rel-20 5GA scope. This needs to be discussed at TSG#107/TSG#108.
  The final decision on the complete set of SIDs for Rel-20 5GA (and the work tasks and TU budget of each SID) will be taken in SA#108.
  For topic SMS to emergency centre, no SA2 moderated discussion expected in Q1 2025.
  For topic User Identities and Authentication, whether moderated discussion can take place in Q2 2025 will be determined in TSG#107.
  Checkpoint in TSG#108 to check SA3 status on Rel-20 UIA and discussion on related SA2 aspects for Rel-20 UIA

## Slide 8: Rel-20 planning – 5G Advanced
Topic | Moderator | Set
Integration of satellite components in the 5G architecture Phase 4 | Hucheng Wang (CATT) | A
AI/ML Enhancements | Xiaobo Wu (vivo) | A
Ambient IoT | Runze Zhou (Huawei) | -
Integrated Sensing and Communication | Jianing Liu (Xiaomi) | A
Energy Efficiency Enhancements | Jungshin Park (Samsung) | A
XR and Media Services | Georgios Gkellas (Nokia) | B
Indirect Network Sharing Phase 2 | TianQi Xing (China Unicom) | B
User Identities and Authentication Architecture – Phase 2 | Mike Starsinic (interdigital) | -
Enhancements for ePDG based access to 5GC | Stefano Faccin (Qualcomm) | A
Mission Critical Services, Multimedia Priority Services | Robert Streijl (Peraton) | B
Industrial network enhancements | Shabnam Sultana (Ericsson) | A
SMS to Emergency Centre | Krisztian Kiss (Apple) | -
NG_RTC continuation | Yi Jiang (China Mobile) | B
09 – 13 Dec | SA#106 | 
16 – 20 Dec |  | NWM discussion process announced and moderators assigned
23 – 27 Dec |  | 
30 Dec – 03 Jan |  | 
06 – 10 Jan |  | 
13 – 17 Jan |  | Kick off NWM discussion for Set A (13 Jan)
20 – 24 Jan | SA2#166AHE | No Rel-20 WID discussion planned Focus is on exceptions and maintenance
27 – 31 Jan | Lunar New Year | 
03 – 07 Feb |  | Complete NWM discussion for Set A (05 Feb)
10 – 14 Feb |  | Kick off NWM discussion for Set B (10 Feb)
17 – 21 Feb | SA2#167 | Discussion and agreement of at least the 5GA WIDs identified by SA for approval in March
24 – 28 Feb |  | Complete NWM discussion for Set B (28 Feb)
03 – 07 Mar |  | 
10 – 14 Mar | SA#107 | 6G Workshop
Plan for approval of the 5G Advanced studies for Rel-20
SIDs/WIDs for topics in Set A should be submitted to SA2#167 for face to face discussion. The focus of SA2#167 will be to try to approve at least the four Core Topics. Any SIDs/WIDs approved in SA2#167 will be submitted to SA#107.
Any SIDs/WIDs for topics in Set A that are not approved in SA2#167 or SA#107 will be further discussed with the aim approving them in SA2#168 or SA2#169 for submission to SA#108.
SIDs/WIDs for topics in Set B should be submitted to SA2#168 or SA2#169 for face to face discussion. Any SIDs/WIDs approved in SA2#168 or SA2#169 will be submitted to SA#108.

## Slide 9: Meetings in Q2 2025

## Slide 10
SA2#168 (Goteborg) Dates/Agenda
SA2#168 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 work item (AmbientIoT)
  AI 19.X: Rel-19 maintenance
  AI 30.X: 5G Advanced proposals for Rel-20 from Set A and Set B topics (excluding TEI20)
  AI 30.X: 6G Study Item proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 28 March 2025 |  | 2359 UTC
Doc submission deadline | Friday 28 March 2025 |  | 2359 UTC
Registration | Monday 31 March 2025 |  | 0800 UTC
Start of meeting | Monday 07 April 2025 | 0900 Local time | 0700 UTC
Close of meeting | Friday 11 April 2025 | 1630 Local time (or earlier) | 1430 UTC
Upload approved documents | Friday 11 April 2025 | 1730 Local time | 1530 UTC

## Slide 11
SA2#169 (Fukuoka) Dates/Agenda
SA2#169 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 work item (AmbientIoT)
  AI 19.X: Rel-19 maintenance
  AI 30.X: 5G Advanced proposals for Rel-20 from Set A and Set B topics (excluding TEI20)
  AI 30.X: TEI20 proposals (for information)
  AI 30.X: 6G Study Item proposals
  SA2 leadership elections
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 09 May 2025 |  | 2359 UTC
Doc submission deadline | Friday 09 May 2025 |  | 2359 UTC
Registration | Monday 12 May 2025 |  | 0800 UTC
Start of meeting | Monday 19 May 2025 | 0900 Local time | 0000 UTC
Close of meeting | Friday 23 May 2025 | 1630 Local time (or earlier) | 1730 UTC
Upload approved documents | Friday 23 May 2025 | 1730 Local time | 1830 UTC