## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #168 Goteborg
April 07 – April 11, 2025

## Slide 2: SA2 and SA meeting dates for 2025
Q1 | SA2-Ad Hoc | Monday, January 20, 2025 | Friday, January 24, 2025 | Electronic
 | SA2#167 | Monday, February 17, 2025 | Friday, February 21, 2025 | Athens, Greece
 | SA#107 | Wednesday, March 12, 2025 | Friday, March 14, 2025 | Incheon, Korea
Q2 | SA2#168 | Monday, April 07, 2025 | Friday, April 11, 2025 | Goteborg, Sweden
 | SA2#169 | Monday, May 19, 2025 | Friday, May 23, 2025 | Fukuoka, Japan
 | SA#108 | Tuesday, June 10, 2025 | Friday, June 13, 2025 | Prague, Czech Republic
Q3 | SA2#170 | Monday, August 25, 2025 | Friday, August 29, 2025 | Goteborg, Sweden
 | SA#109 | Tuesday, September 16, 2025 | Friday, September 19, 2025 | China
Q4 | SA2#171 | Monday, October 13, 2025 | Friday, October 17, 2025 | China (TBC)
 | SA2#172 | Monday, November 17, 2025 | Friday, November 21, 2025 | Dallas, USA
 | SA#110 | Tuesday, December 09, 2025 | Friday, December 12, 2025 | Baltimore, USA

## Slide 3: Rel-19 planning for SA2 - General
FS_AmbientIoT-ARC
  The WID was approved in SA#107 and normative work will need to conclude in Q2 2025
Maintenance work is well under way on the other Work Items
But the planning for Rel-20 anticipates a rapid reduction in time dedicated to Rel-19 maintenance over the next few meetings
Per-company quotas per topic are likely to be needed from August onwards
 |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
 |  | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU | Oct #177 EU | Nov #178 US
Rel-19 |  |  |  |  |  |  |  |  |  |  |  | 
19.x | Original planned total TU's | 11 | 11 | 9 | 6 | 6 | 4 | 4 | 4 | 3 | 3 | 3

## Slide 4: Rel-20 planning
(See SP-240458 endorsed in SA#103 Maastricht)
Studies for 6G in 3GPP are expected to start from Release 20
  First TSG-wide 6G workshop held in March 2025
  SA1 SID was approved in Sept 2024
  SA2 SID is expected to be approved in June 2025
  SA2 6G SI completion: No later than Mar 2027 (see SP-250416 endorsed in SA#107)
    SA will have check point in Dec 2025 to further review SA2 6G SI completion date and make final decision on whether it is Dec 2026 or Mar 2027
For 5G-Advanced
  Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
  100% means no exceptions in September

## Slide 5: Rel-20 planning – 5GA topic preparation
Plan for preparation and approval of the 5GA topics
Topic | Moderator | Set | Status on 17th March | Next steps
Integration of satellite components in the 5G architecture Phase 4 | Hucheng Wang (CATT) | A | SID approved in SA#107 | Start technical work
AI/ML Enhancements | Xiaobo Wu (vivo) | A | SID approved in SA#107 | Start technical work
Integrated Sensing and Communication | Jianing Liu (Xiaomi) | A | SID approved in SA#107 | Start technical work
Energy Efficiency Enhancements | Jungshin Park (Samsung) | A | SID approved in SA#107 | Start technical work
Enhancements for ePDG based access to 5GC | Stefano Faccin (Qualcomm) | A | Discussed in SA2#167 but not approved | Moderator to submit SID to SA2#169
Industrial network enhancements | Shabnam Sultana (Ericsson) | A | Discussed in SA2#167 but not approved | Moderator to submit SID to SA2#169
XR and Media Services | Georgios Gkellas (Nokia) | B | Moderated discussion completed | Moderator to submit SID to SA2#168
Indirect Network Sharing Phase 2 | TianQi Xing (China Unicom) | B | Moderated discussion completed | Moderator to submit SID to SA2#168
Mission Critical Services, Multimedia Priority Services | Robert Streijl (Peraton) | B | Moderated discussion completed | Moderator to submit SID to SA2#168
NG_RTC continuation | Yi Jiang (China Mobile) | B | Moderated discussion completed | Moderator to submit SID to SA2#168
Ambient IoT | Runze Zhou (Huawei) | C | SA#107 gives guidance to start moderated discussion in Q2 2025 | Discussion papers invited for SA2#168, moderated discussion after SA2#168. Moderator to submit SID to SA2#169.
User Identities and Authentication Architecture – Phase 2 | Mike Starsinic (interdigital) | C | SA#107 gives guidance that no moderated discussion should start in SA2 until SA3 provides input | Wait for SA3 input to SA2. Once received start moderated discussion and target SID submission to SA2#169
SMS to Emergency Centre | Krisztian Kiss (Apple) | C | SA#107 gives guidance to start moderated discussion in Q2 2025 | Moderator to submit SID to SA2#169
IMS resiliency | TBC | C | Topic added during SA#107 SA#107 gives guidance on moderated discussion plan | Based on CT WGs feedback, moderated discussion in SA2 can start after SA2#168 meeting, if needed

## Slide 6: Rel-20 planning – 5GA item planning
Planning of 5GA study and normative work
 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
 | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100%
Items starting in April | Meeting #1 | Meeting #2 | Meeting #3 | Meeting #4 | Meeting #5 | Meeting #6 | Meeting #7 | Meeting #8 | Meeting #9
Priority | KI’s | Solutions | Solutions | Solution updates, conclusions | Solution updates, conclusions | Normative | Normative | Normative | Normative
Items starting in August |  |  | Meeting #1 | Meeting #2 | Meeting #3 | Meeting #4 | Meeting #5 | Meeting #6 | Meeting #7
Priority |  |  | KI’s | Solutions | Solutions, conclusions | Solution updates, conclusions | Normative | Normative | Normative

## Slide 7: Upcoming meetings in Q2 and Q3 2025

## Slide 8
SA2#169 (Fukuoka) Dates/Agenda
SA2#169 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 work item (AmbientIoT-ARC)
  AI 19.X: Rel-19 maintenance
  AI 20.X – for SI’s approved in March
  AI 30.X: 5G Advanced proposals for Rel-20 from SA list (Core and Misc) (excluding TEI20)
  AI 30.X: TEI20 proposals (for information)
  AI 30.X: 6G Study Item proposal (from moderator)
  SA2 leadership elections will take place
Doc request deadline | Friday 09 May 2025 |  | 2359 UTC
Doc submission deadline | Friday 09 May 2025 |  | 2359 UTC
Registration | Monday 12 May 2025 |  | 0800 UTC
Start of meeting | Monday 19 May 2025 | 0900 Local time | 0000 UTC
Close of meeting | Friday 23 May 2025 | 1630 Local time (or earlier) | 0830 UTC
Upload approved documents | Friday 23 May 2025 | 1730 Local time | 0930 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting

## Slide 9
SA2#170 (Goteborg) Dates/Agenda
SA2#170 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 maintenance
    Quota limited: 4 per company per AI?
  AI 20.X: Approved SIDs
  AI 30.X: TEI20 proposals for approval
Doc request deadline | Friday 15 August 2025 |  | 2359 UTC
Doc submission deadline | Friday 15 August 2025 |  | 2359 UTC
Registration | Monday 18 August 2025 |  | 0800 UTC
Start of meeting | Monday 25 August 2025 | 0900 Local time | 0700 UTC
Close of meeting | Friday 29 August 2025 | 1630 Local time (or earlier) | 1430 UTC
Upload approved documents | Friday 29 August 2025 | 1730 Local time | 1530 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting