## Slide 1: Rel-19 TU management
Suresh Nair, SA3 Chair, Nokia

## Slide 2: Rel-19 Timeline for SA3
Rel-19 timeline (no change compared to SA#99 endorsement, March 2023, SP-230390):
Dec 2023 (TSG#102): Stage 1 freeze
Dec 2024 (TSG#106): Stage 2 normative work freeze -> Q1 2025 for SA3
Sept 2025 (TSG#109): Stage 3 freeze
Dec 2025 (TSG#110): “coding freeze” (ASN.1, Open APIs)
SA3 capacity
Max TUs: 98 (over 7 meetings)
Additional buffer TUs: 14
Max number of SIs/WIs: 14 topic with full TUs/ 28 topics with ½ TUs
Note: one feature made up of SI+WI is counted as one item
Max TUs per Feature: 7

## Slide 3: Rel-19 Meetings for SA3
SA3#113 Nov 6-10, 2023 | SA3#114 Jan 22-26, 2024 (Cancelled) | SA3#115 Feb 26- Mar1, 2024 | SA3#116 May 13-17, 2024 | SA3#116 Adhoc ? June-Jul TBD | SA3#117 Aug 26-30, 2024 | SA3#118 Oct 7-11, 2023 | SA3#119 Nov 11-15, 2024 | SA3#120 Jan TBD 2025 | SA3#121 Feb TBD 2025
Kick start Security Features. Wait for SA2/6, RAN features | Start second set of features | Start second set of features |  |  |  |  |  |  | 
Study Phase
Normative work Phase

## Slide 4: Rel-19 SA2 package (from SA#101)
First Rel-19 package for SA2 approved, with 5 studies. Work can start in Q4 2023, but down-scoping is still possible in December SA#102.
XRM Ph2 SP-231198
Energy Efficiency and Energy Saving SP-231192
Integration of satellite components in the 5G architecture Phase III SP-231199
Next generation real time communication services phase 2 SP-231196
MPS for IMS Messaging and SMS services SP-231197
There are 16 other candidate items for final SA2 Rel-19 package:

## Slide 5: Short SA3 Prime topics
Handle Short SA3 prime topics as mini WIDs.
Restrict mini WIDs to 2-3 meeting cycles max.
Restrict TU budget for mini WIDs

## Slide 6: Thank You!
Suresh Nair
3GPP SA3 Chairman
mail: suresh.p.nair@nokia.com
phone: +1 973 978 9038