Source:	3GPP SA4 Audio SWG

Title:	Organization of IVAS Characterization Phase – rev 1

Document for:	Agreement

Agenda Item:	1.5

# 1. Introduction

This document provides the outline on organization of IVAS Characterization Phase. The document was discussed and agreed in the Audio SWG, with SA4 power to agree on the requirements for the IVAS floating-point to fixed-point conversion.

Basis are the working assumptions discussed at SA4#124, contributions received, and discussions in Audio SWG and between Audio SWG and Ittiam.

# 2. Goals of IVAS Characterization Phase

While IVAS Selection Phase ran on the basis of floating-point code, the Characterization Phase aims testing the fixed-point code. In accordance with the IVAS_Codec_Ph2 WID, as agreed by SA4, the IVAS fixed-point reference code in TS 26.251 aims completion by June 2025. Hence the Characterization Phase consists of two sub-tasks, namely making the FX code available in time, and running subjective listening evaluation of IVAS using the FX code. The test results of the Characterization tests will be documented in TR 26.997, also targeted by June 2025. This means that fully functioning FX code needs to be available earlier than June 2025, in time for the characterization testing.

Considerations were made how to achieve these goals. First the availability of the FX code in time had to be solved and for this, outsourcing the conversion of FL code to FX to a specialized expert company was identified as the only feasible way. The Audio SWG chairman made a call over the 3GPP SA4 reflector on 9 May 2023. Ittiam replied on 15 May 2023 and expressed interest, then contacts were established to Ittiam, and officials provided a presentation and quote to Audio SWG, and discussion was organized to identify key factors / requirements of FL-to-FX conversion. For this sub-task, part of the collected funds of 1.2Mio euro is planned to be spent.

The quote by Ittiam to perform the FL-to-FX conversion was accepted and a service contract between ETSI and Ittiam was signed on Oct 3, 2023. The service contract was subsequently prolonged on March 28, 2024, since more time was needed to complete the project. At SA4#128 meeting (May 2024), the delivery of TS 26.251 was moved to the new work item, IVAS_Codec_Ph2, since the milestone of the fixed-point code delivery was not met. A further extension of the service contract between ETSI and Ittiam is therefore necessary.

The second sub-task will be to run the characterization phase subjective experiments. For this sub-task, part of the collected funds of 1.2Mio euro is planned to be spent to external listening labs, according to the characterization test plan (see IVAS-2 for the development schedule). In addition, 3GPP member companies indicated interest to perform listening tests on voluntary basis.

3. Key factors / requirements for IVAS FL-to-FX conversion

BASOPS

- Usage of BASOPs in IVAS FX code

- STL2023 BASOPs are used in IVAS FX code (64-bit and shorter).

- The EVS part of IVAS FX is reused from the “alternative” 64-bit FX EVS implementation (TS 26.452).

- Overflow and Carry flag used inside the BASOPs and written to global variables shall be avoided. In case Overflow or Carry would be required, new dedicated operators that expose those flags without the use of global variables shall be used.

To reflect this and potential other necessary improvements, some operators may need an update; this update will be provided by Audio SWG to Ittiam in time.

- Contribution to ITU-T on modified BASOPs will be desirable.

Complexity

- Complexity (WMOPS) ratio between IVAS FX and IVAS FL should be no worse than the complexity ratio between EVS FX and EVS FL; the goal is that the design constraints are met with the FX code.

- Memory savings: always use the smallest data type (and respective BASOPs) as far as possible, in a reasonable balance with complexity.

FX coding practices

- 3GPP Forge will be used as the platform of FX development, similarly to the development of FL code in Public Collaboration.

- Inclusion of 3rd party code or open-source code is not allowed; inclusion of code from generative  AI tools is not allowed.

- Structure of FL code shall be preserved to the maximum extent to allow comparison between FL and FX code and easier maintainability of the two code bases. This includes the best preservation of function prototypes and comments in the code; file names shall remain unchanged. In addition, all variables converted to FX shall be marked with precision information (integer, fractional) in Q-notation; precision changes should be documented; the goal is that the original functions could be used interchangeably during development; function names of converted functions shall avoid symbol clashes during the development; the objective is to ultimately have maximum similarity to the FL code and eventually all variables and function names also in FX shall be unified to their FL counterpart.

- The performance of the FX code should match the performance of the FL code, both in terms of subjective quality and complexity.

  - For decoding, the output synthesis of FX decoder (FL enc+ FX dec) compared to FL decoder (FL enc + FL dec) should be within the limit of segmental SNR (per frame and then averaged) > [60 dB], and MLD < 5.

  - For bit-streams generated with the FX encoder, the output synthesis of the bit-stream decoded with the FL decoder compared to the synthesis of a bit-stream generated with the FL encoder and decoded with the FL decoder should be within the limit of MLD < [TBD], PEAQ (basic profile) < [0.1].

NOTE: In case of doubt regarding the performance based on objective measures, the subjective quality should be assessed.

- For non-EVS operation, the performance shall be measured using both the short and long test vector sets as specified in 3GPP Forge, with nominal level and +-10 dB.

- Interoperability between FX and FL codes shall be guaranteed; for example, valid FL bitstreams shall be decodable by the FX-decoder, related to certain quality requirements (no drop).

- Making test vectors available for conversion is responsibility of Audio SWG.

- Further practical matters should be discussed between Audio SWG and Ittiam.

Project organization

- Collaborative development includes regular email exchange and a weekly call, regular time: Wednesday 12:00-13:00 CEST/CET.

- SA4/Audio/IVAS BASOP project at 3GPP Forge (forge.3gpp.org) is used for coordination on specific issues related to the code conversion.

- Additional calls are scheduled on a need basis.

- Maintenance by Ittiam for FL-to-FX conversion expected until Feb 2025.

Milestones

- Aug 2024: Delivery of Decoder and Renderer to SA4, fulfilling the FL-to-FX requirements

- SA4#130, Nov 18-22, 2024 (or earlier if Audio SWG call with power to agree): Agreement by TSG SA WG 4 (SA4) on Delivery of Decoder and Renderer, fulfilling the FL-to-FX requirements

- SA#106, Dec 10-13, 2024: Approval by TSG SA of Delivery of Decoder and Renderer, fulfilling the FL-to-FX requirements, based on agreement in SA4

- Delivery of Encoder to SA4, fulfilling the FL-to-FX requirements

  - Sep 2024

    - Mono (EVS)

    - ISM (core coder)

    - Stereo

    - MCT

  - Oct 2024

    - MASA

    - SBA

    - Parametric modes

  - Nov 2024

    - Combined formats

- SA4#131, Feb 17-21, 2025: Agreement by TSG SA WG 4 (SA4) on Delivery of Encoder, fulfilling the FL-to-FX requirements

- SA#107, Mar 12-14, 2025: Approval by TSG SA of Delivery of Encoder, fulfilling the FL-to-FX requirements, based on agreement in SA4

- Jun 2025: Approval by TSG SA on TS 26.251 and TR 26.997

4. Characterization Phase Testing

Listening lab experiments are planned to be run in external listening labs (against payment) and in the labs of volunteering 3GPP member companies. The external listening labs will be determined in time to run the experiments as scheduled in IVAS-2.

To date, the following companies offered to run listening experiments on voluntary basis: Dolby, Ericsson, Fraunhofer IIS, Huawei, Nokia, NTT, Orange, Panasonic, Philips, Qualcomm, VoiceAge. Further offers will be welcome.

5. Budget

The following table contains the allocation of budget to sub-tasks.

| Task | Sub-task | Amount in EUR |
| --- | --- | --- |
| Selection Phase | Listening lab – Force Technology | 239000 |
|  | Listening lab – HEAD acoustics | 179000 |
|  | Listening lab – Mesaqin.com | 180000 |
|  | Listening lab – MC University | 36000 |
|  | Global Analysis Lab – HEAD acoustics | 12000 |
| Characterization Phase | FL-to-FX conversion – Ittiam | 350000 |
|  | Listening labs and GAL – external labs (tbd) | 204000 |
| Total |  | 1200000 |

6. Action Items

On this basis, ETSI MCC is kindly requested to

- amend the service contract with Ittiam for performing the IVAS FL-to-FX conversion work in accordance with the Key factors / requirements for IVAS FL-to-FX conversion in clause 3;

- annex the present document to the contract as for technical requirements.