Source:	Samsung Electronics Co., Ltd. (Rapporteur)

Title:	[5GSTAR] Updated Work Plan

Version	0.5

Agenda Item:	10.9

Document for:	Agreement

# Introduction

During SA4#109 the New Study Item on “5G Glass-type AR/MR Devices” in SA4-200897 was agreed and afterwards approved in by SA plenary#88 in SP-200399.

The objective of this study item are primarily to identify the AR glasses structures, media flow architecture, media exchange formats and profiles, and necessary content delivery protocols for glass-type AR/MR services. Key performance indicators, QoE factors for the AR use cases and device form-factor issues are also identified.

The concrete objectives are as follows:

- Provide formal definitions for the functional structures of AR glasses, classified as device types of XR5G-A4 (standalone) and XR5G-A2, A5 (wirelessly tethered) in TR 26.928, including their capabilities and constraints with respect to communication, computing and graphics processing, tracking, sensors, display, and power consumption

NOTE 1: Device type of XR5G-A3 (video see-through HMD) are not the primary scope of this study, but are not excluded per se.

- Describe key use cases for AR services over 5G based on those in Table 4.10 of TR 26.928, map each use case to suitable device types, and define relevant processing functions and reference architectures for the devices that are required to support the use cases, taking into account the constraints and capabilities identified under the first objective.

NOTE 2: The preferred cases will be those capable of delivering experiences previous or existing media services could not support, e.g., those requiring features for AR/MR 3D download, communication or conversational (related to use cases 1, 2, 7, 8, 11, 15, 16, 17, 19, 20, or 23). The study also allows new use cases not covered in TR 26.928.

- Describe the architecture for media flow relevant to the use cases identified in the second objective. Identify media (exchange) formats and profiles relevant to the use cases identified in the second objective that can be processed on AR platforms as defined under the first objective. Identify where media processing functions occur and which type of media formats are used for exchange between these elements to the described architecture.

NOTE 3: Exchange formats include both, formats and signals consumed on AR devices (e.g. overlays, scenes, animations) as well as those that are generated (and shared) on/by those (for example to support spatial localization, object recognition and tracking).

- Identify necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities (e.g., device, edge, network) and QoS (including radio access and core network technologies) required for the use cases. If existing technologies and protocols cannot serve the cases sufficiently, describe the necessary functionalities and features.

- Identify key performance indicators and quality of experience factors (such as immersiveness, presence, localization, and world tracking accuracy) for the AR use cases based on the initial considerations in TR26.928, clause 4.2 with additional emphasis on the use cases, device platforms and exchanges formats for AR as identified in earlier objectives.

NOTE 4: As there can be several approaches for the optical implementation of displays, this study does not prefer any display types, nor will it define any detailed criteria or quality requirements.

- Identify relevant radio and system parameters (required bitrates, latencies, loss rates, range, etc.) to support the identified AR use cases and the required QoE, in particular when the AR device is connected via 5G sidelink interfaces.

NOTE 5: Depending on the use cases, other types of peripheral devices, such as external cameras and sensors, can also be connected to the UEs in a similar fashion.

- For each of the identified use cases and AR device platforms, provide a detailed overall power analysis for media AR related processing and communication building on the information in TR26.928, clause 4.8. Different design options should be considered, for example if media processing is carried out on the device, on a puck/smartphone or in the edge/cloud. It is recommended to contact relevant 3GPP WGs, in particular, and RAN4, on expected modem power consumption for certain use cases.

NOTE 6: Support other 3GPP WGs and other SDOs on relevant aspects related to their work and responsibilities for these new design options and form factors on a need basis, in particular when requested for processing functions in scope of SA4.

- Identify potential areas for normative work as the next phase and communicate with other 3GPP WGs on relevant aspects related to the study.

# Proposed Time and Work Plan

| Meeting | Feasibility Study on 5G Glass-type AR/MR Devices - #880011 |
| --- | --- |
| SA4#109 (20 May – 03 Jun, 2020, e-meeting) | - Agree New Study Item on “Feasibility Study on 5G Glass-type AR/MR Devices” in S4-200897 |
| SA#88 (30 Jun – 03 Jul, 2020, e-meeting) | - Approve New Study Item on “Feasibility Study on 5G Glass-type AR/MR Devices” in SP-200399 - Allocate specification number specification number TR 26.998 to 5G Glass-type AR/MR Devices |
| SA4#110 (19 – 28 Aug 2020, e-meeting) | - Agree Specification skeleton and Scope for TR 26.998 - Agree initial Work Plan - Agree a template for use case proposal and documentation |
| 3GPP SA4 Video SWG Telco on 5GSTAR #1 (Sep 08, 2020, 15:00 – 16:00 CEST, Host TBD) | - Initiate work on the following items: - Use cases and scenarios for AR/MR glasses - Device type - Functional structure for each of device type - Review existing information on glass-type AR/MR devices and services in other 3GPP working groups and external organizations - Identify core use cases - Document the agreements in the Permanent Document - Submission deadline Sep 07, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco on 5GSTAR #2 (Sep 22, 2020, 15:00 – 16:00 CEST, Host TBD) | - Progress on the following items: - Use cases and scenarios for AR/MR glasses - Device type - Functional structure for each of device type - Review existing information on glass-type AR/MR devices and services in other 3GPP working groups and external organizations - Identify core use cases - Document the agreements in the Permanent Document - Submission deadline Sep 21, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco on 5GSTAR #3 (Oct 06, 2020, 15:00 – 16:00 CEST, Host TBD) | - Progress on the following items: - Use cases and scenarios for AR/MR glasses - Device type - Functional structure for each of device type - Review existing information on glass-type AR/MR devices and services in other 3GPP working groups and external organizations - Identify core use cases - Document the agreements in the Permanent Document - Submission deadline Oct 05, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco on 5GSTAR #4 (Oct 20, 2020, 15:00 – 16:00 CEST, Host TBD) | - Progress on the following items: - Use cases and scenarios for AR/MR glasses - Device type - Functional structure for each of device type - Review existing information on glass-type AR/MR devices and services in other 3GPP working groups and external organizations - Complete work on identification of core use cases - Document the agreements in the Permanent Document - Submission deadline Oct 19, 15:00 CEST. |
| SA4#111 (11 – 20 Nov 2020, e-meeting) | - Progress the summary of use cases - Use case categorization - Detailed functional structure for use cases - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Update core use cases as necessary - Initiate the discussion of device form-factor related issues - Progress the Permanent Document - Document the agreements in TR 26.998 |
| 3GPP SA4 Video SWG Telco #1 (Dec. 1, 2020, 15:00 – 17:00 CET, Host Qualcomm) | - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Submission Deadline Nov. 30, 15:00 CET |
| 3GPP SA4 Video SWG Telco #2 (Dec 8, 2020, 15:00 – 17:00 CET, Host Qualcomm) | - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Submission Deadline Dec 7, 15:00 CET |
| 3GPP SA4 Video SWG Telco #3 (Dec 15, 2020, 15:00 – 17:00 CET, Host Qualcomm) | - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Submission Deadline Dec 14, 15:00 CET |
| 3GPP SA4 Video SWG Telco #4 (Jan, 19, 2020, 15:00 – 17:00 CET, Host Qualcomm) | - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Submission Deadline Jan 18, 15:00 CET |
| SA4#112 (1 – 10 Feb 2021, e-Meeting, Host MCC, TBD) February 28, 2019, 4pm - 6pm cet () | - Based on the core use cases and device structure, - Progress work on the architecture for media flow, media exchange formats / profiles, and the media processing function required - Progress identifying necessary content delivery transport protocols and capability exchange mechanisms, as well as suitable 5G system functionalities - Progress identifying the necessary key performance indicators and quality of experience factors - Update core use cases as necessary - Progress work on identifying device form-factor related issues - Agree on TR 26.998 v1.0.0 |
| SA4 Video SWG Telco #1 (23 Feb, 2021, 15:00 – 17:00 CET, Host Qualcomm) | - Progress work on mapping use case to 5G system - Extended device architecture for media flow / media exchange formats and profiles - Necessary KPIs and QoS/QoE factors - Map the use case against device/network architecture - Submission deadline Feb 22, 15 CET |
| SA4 Video SWG Telco #2 (2 Mar, 2021, 15:00 – 17:00 CET, Host Qualcomm) | - Progress work on mapping use case to 5G system - Extended device architecture for media flow / media exchange formats and profiles - Necessary KPIs and QoS/QoE factors - Map the use case against device/network architecture - Submission deadline Mar 1, 15 CET |
| SA4 Video SWG Telco #3 (16 Mar, 2021, 15:00 – 17:00 CET, Host Qualcomm) | - Progress work on mapping use case to 5G system - Extended device architecture for media flow / media exchange formats and profiles - Necessary KPIs and QoS/QoE factors - Map the use case against device/network architecture - Submission deadline Mar 15, 15 CET |
| SA4 Video SWG Telco #4 (23 Mar, 2021, 22:30 – 00:30 CET, Host Qualcomm) | - Progress work on mapping use case to 5G system - Extended device architecture for media flow / media exchange formats and profiles - Necessary KPIs and QoS/QoE factors - Map the use case against device/network architecture - Submission deadline Mar 22, 15 CET |
| SA4#113 (6 – 14 Apr 2021, e-Meeting, MCC, TBD) | - Progress work on the following item: - Media exchange formats / profiles, and the media processing function - Content delivery transport protocols and capability exchange mechanisms - Key performance indicators and quality of experience factors - Document the agreements in TR 26.998 |
| SA4 Video SWG Telco #1 (4 May, 2021, 15:00 – 18:00 CEST, Host Qualcomm) | - Progress work on the following item: - Media exchange formats / profiles, and the media processing function - Content delivery transport protocols and capability exchange mechanisms - Key performance indicators and quality of experience factors - Potentially discuss the commonalities with FS_EMSA (17:00 – 18:00 CEST) - Submission deadline May 3, 15:00 CEST |
| SA4 Video SWG Telco #2 (11 May, 2021, 15:00 – 17:00 CEST, Host Qualcomm) | - Progress work on the following item: - Media exchange formats / profiles, and the media processing function - Content delivery transport protocols and capability exchange mechanisms - Key performance indicators and quality of experience factors - Submission deadline May 10, 15:00 CEST |
| SA4#114 (19 – 28 May 2021, e-Meeting, MCC) | - Progress work on the following item: - Media exchange formats / profiles, and the media processing function - Content delivery transport protocols and capability exchange mechanisms - Key performance indicators and quality of experience factors - Freeze device architecture for 5G immersive media streaming |
| SA4 Video SWG Telco #1 (8 June 2021, 15:30 – 18:00 CEST, Host Qualcomm) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Joint Session with MTSI (17:00– 18:00 CEST) on AR calls - Submission deadline Jun. 7, 15:30 CEST |
| SA4 Video SWG Telco #2 (22 June 2021, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Submission deadline Jun. 21, 15:30 CEST |
| SA4 Video SWG Telco #3 (6 July 2021, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Submission deadline Jul. 5, 15:30 CEST |
| SA4 Video SWG Telco #4 (20 July 2021, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Submission deadline Jun. 19, 15:30 CEST |
| SA4 Video SWG Telco #5 (3 Aug. 2021, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Submission deadline Aug. 2, 15:30 CEST |
| SA4#115 (18 – 27 Aug 2021, e-Meeting, MCC) | - Progress work on the following scenarios: - 5G Interactive immersive service - 5G Cognitive - AR two-party calls - AR conferencing - Agree on TR 26.998 v1.0.0 |
| SA#93 (14 – 20 Sep 2021, e-Meeting, MCC) | - Present TR 26.998 v1.0.0 for information |
| SA4#116 (10 – 19 Nov 2021, e-Meeting, MCC) | - Complete all open issues raised for completion of TR26.998 - Complete documenting conclusions and potential normative work - Communicate with other 3GPP working group and external organizations, if required - Agree on TR 26.998 v2.0.0 to be sent to SA plenary for approval |
| SA#94 (15 – 17 Dec 2021, TBD) | - Present TR 26.998 v2.0.0 for approval |

# Proposal

We propose to agree the updated work plan in clause 2.