3GPP TSG SA WG4#120-e meeting	S4-220974

17th – 26th August 2022 	revision of S4-220762

Agenda item: 	9.6

Source: 	Qualcomm Incorporated (Rapporteur)

Title: 	Proposed Updates to Work Plan for FS_XRTraffic

Version:	0.13

Document for	Agreement

# Introduction

During SA4#107 the New Study Item on “Feasibility Study on Extensions to Typical Traffic Characteristics” in S4-200334 was agreed and afterwards approved in by SA plenary #87 in SP-200054.

The work item was updated and agreed in S4-210280.

The objective of the study is as follows:

- Collect and document traffic characteristics including for different services, but not limited to

  - Downlink data rate ranges

  - Uplink data rate ranges

  - Maximum packet delay budget in uplink and downlink

  - Maximum Packet Error Rate,

  - Maximum Round Trip Time

  - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including.

- Collect additional information, such as codecs and protocols in use.

- Provide the information from above at least for the following services (initial services)

  - Viewport independent 6DoF Streaming

  - Viewport dependent 6DoF Streaming

  - Simple Single Buffer split rendering for online cloud gaming

  - Cloud gaming

  - MTSI-based XR conversational services

- Create a new Technical Report

  - Document reference designs for each of the services

  - Provide suitable simulation models for each of the services

  - Provide suitable metrics to evaluate the quality of the services

- Identify additional relevant XR and other media services and document their traffic characteristics

- Document additional developments in the industry that impact traffic characteristics in future networks

- Identify the applicability of existing 5QIs/PQIs for such services and potentially identify requirements for new 5QIs/PQIs or QoS related parameters.

- Communicate with other 3GPP groups and external organizations on relevant aspects related to the study.

The following 4 slots are proposed:

-	31/05 MeCAR, AI/ML, FS_XRTraffic, Maintenance

-	14/06 MeCAR, AI/ML, FS_XRTraffic, Maintenance

-	28/06 MeCAR, AI/ML, FS_XRTraffic, Maintenance

-	12/07 MeCAR, AI/ML, FS_XRTraffic, Maintenance

# Proposed Time and Work Plan

| Meeting |  | Feasibility Study on Typical Traffic Characteristics for XR Services and other Media Characteristics - #870013 |
| --- | --- | --- |
| SA4#107 (20 – 24 January, 2020, Wroclaw, Poland) |  | - Agree New Study Item on “Feasibility Study on Typical Traffic Characteristics for XR Services and other Media” in S4-200334 |
| SA#87 (18 - 20 Mar, 2020, Jeju, Korea, e-meeting) |  | - Approve New Study Item on “Feasibility Study on Typical Traffic Characteristics for XR Services and other Media” in SP-200054 |
| SA4#108 (6 – 9 Apr 2020, Sophia Antipolis, FR, e-meeting) |  | - Define and agree a work and time plan - Create draft skeleton of a draft CR 26.925 for XR Traffic Models - Decide allocation of Study Item to Video SWG for future SA4 meetings - In order to progress the work, only the following type of documents are expected to be progressed and agreed in the following priority: - Time Plan - Skeleton draft CR26.925 on XR Traffic Models, if time permits - Other type of documents will not be addressed during SA4#108 and are hence not encouraged to be submitted. |
| 3GPP SA4 Video SWG Telco on FS_XRTraffic (May 12, 2020, 16:00 – 17:00 CEST, Host Qualcomm) |  | - Initiate discussion on traffic characteristics for a subset of XR services - Initiate the discussion on a methodology to collect traffic characteristics for XR - Progress draft CR on on XR Traffic Models - Submission deadline May 11, 16:00 CEST. |
| SA4#109 (20 May – June 3, 2020, e-meeting) |  | - Agree on a methodology to collect traffic characteristics for XR - Progress draft CR on on XR Traffic Models - Agree on initial version of Permanent Document - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco (June 23, 2020, 15:00 – 17:00 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline June 22, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco (July 7, 2020, 15:00 – 17:00 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline July 6, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco (July 21, 2020, 15:00 – 17:00 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline July 20, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco (August 4, 2020, 15:00 – 17:00 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline August 3, 15:00 CEST. |
| SA4#110-e (19 – 28 Aug 2020, online) |  | - Collect and document traffic characteristics including for different services, but not limited to - Downlink data rate ranges - Uplink data rate ranges - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Collect additional information, such as codecs and protocols in use. - Provide the information from above at least for the following services (initial services) - Viewport independent 6DoF Streaming - Viewport dependent 6DoF Streaming - Simple Single Buffer split rendering for online cloud gaming - Cloud gaming - MTSI-based XR conversational services - Progress the Permanent Document - Agree on CR26.295 for XR Traffic Models taking into account the above information. - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco on FS_XRTraffic (Sep 22, 2020, 15:00 – 16:30 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline Sep 21, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco (Sep 29, 2020, 15:00 – 16:30 CEST, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline Sep 28, 15:00 CEST. |
| 3GPP SA4 Video SWG Telco (Oct 27, 2020, 15:00 – 16:30 CET, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline Oct 25, 15:00 CET. |
| SA4#111-e (04 – 13 Nov 2020, tbc, online) |  | - Collect and document traffic characteristics including for different services, but not limited to - Downlink data rate ranges - Uplink data rate ranges - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Collect additional information, such as codecs and protocols in use. - Provide the information from above at least for the following services (initial services) - Viewport independent 6DoF Streaming - Viewport dependent 6DoF Streaming - Simple Single Buffer split rendering for online cloud gaming - Cloud gaming - MTSI-based XR conversational services - Progress the Permanent Document - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco on FS_XRTraffic (Nov 24, 2020, 15:00 – 17:00 CET, Host Qualcomm) |  | - Dispose postponed documents from SA4 - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline November 23, 15:00 CET. |
| 3GPP SA4 Video SWG Telco (Dec 15, 2020, 15:00 – 17:00 CET, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Document the agreements in the Permanent Document - Submission deadline Dec 14, 15:00 CET. |
| 3GPP SA4 Video SWG Telco on FS_XRTraffic (Dec 22, 2020, 15:00 – 17:00 CET, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Agree XR traffic models and send LS to RAN1 - Document the agreements in the Permanent Document - Singing Christmas songs and eating cookies and drinking Glühwein - Submission deadline December 21, 15:00 CET. |
| 3GPP SA4 Video SWG Telco on FS_XRTraffic (Jan 12, 2021, 15:00 – 17:00 CET, Host Qualcomm) |  | - For each relevant XR Service, progress and document - System Assumptions - Simulation Methodology - Traffic Characteristics - Agree XR traffic models and send LS to RAN1 - Document the agreements in the Permanent Document - Submission deadline January 8, 23:59 CET. |
| RAN1#104 (25 January – 05 Feb 2021, tbd) |  | - Receive LS from 3GPP SA4 - Expected agreement on Traffic Models |
| SA4#112 (01 – 10 Feb 2021) |  | - Collect and document traffic characteristics including for different services in TR 26.925, but not limited to - Downlink data rate ranges - Uplink data rate ranges - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Provide the information from above at least for the following services - VR1: Viewport dependent 6DoF Streaming - VR2: Split Rendering: Viewport rendering with Time Warp in device - CG: Cloud gaming - AR1: XR Distributed Computing - AR2: MTSI-based XR conversational services - Update work item to address new developments - Progress development and documentation as Annex to TR 26.925 or new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco (Feb 23, 2021, 15:00 – 17:00 CET, Host Qualcomm) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Submission deadline Feb 22, 15 CET. |
| 3GPP SA4 Video SWG Telco (Mar 2, 2021, 15:00 – 17:00 CET, Host Qualcomm) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Submission deadline Mar 1, 15 CET |
| 3GPP SA4 Video SWG Telco (Mar 16, 2021, 15:00 – 17:00 CET, Host Qualcomm) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Send LS to RAN1 with updated information, if appropriate - Submission deadline Mar 15, 15 CET |
| 3GPP SA4 Video SWG Telco (Mar 22, 2021, 22:30 – 00:30 CET, Host Qualcomm) |  | - Progress development and documentation afrom PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Submission deadline Mar 21, 15 CET |
| SA#91-e (March 24-29 2021) |  | - Approve work item update |
| SA4#113 (6 – 14 Apr 2021) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Progress collection document traffic characteristics including for different services in TR 26.925, but not limited to - Downlink data rate ranges - Uplink data rate ranges - Document Traffic Characteristics for additional relevant XR and other media services. - Document additional developments in the industry that impact traffic characteristics in future networks - Document the applicability of existing 5QIs/PQIs for such services and potentially identify requirements for new 5QIs/PQIs or QoS related parameters. - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco (May 4, 2021, 15:00 – 17:00 CEST, Host Qualcomm) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Submission deadline May 3, 15 CEST |
| 3GPP SA4 Video SWG Telco (May 11, 2021, 15:00 – 17:00 CEST, Host Qualcomm) |  | - Progress development and documentation from PD to new TR - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Submission deadline May 10, 15 CEST |
| SA4#114-e (19 – 28 May 2021) |  | - Progress development and documentation of new TR for XR-relevant services - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Document Traffic Characteristics for additional relevant XR and other media services. - Document additional developments in the industry that impact traffic characteristics in future networks - Document the applicability of existing 5QIs/PQIs for such services and potentially identify requirements for new 5QIs/PQIs or QoS related parameters. - Update PD - Update TR 26.926 - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary |
| 3GPP SA4 Video SWG Telco (June 8, 2021, 15:30 – 17:00 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline June 7, 16:30 CEST. |
| SA#92-e (June 15 - 21 2020) |  | - No updates |
| 3GPP SA4 Video SWG Telco (June 22, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline June 21, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (July 6, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline July 5, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (July 20, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline July 19, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (August 3, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline August 2, 16:30 CEST. |
| SA4#115-e (18 – 27 August 2021) |  | - Complete development and documentation of new TR for XR-relevant services - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Maximum packet delay budget in uplink and downlink - Maximum Packet Error Rate, - Maximum Round Trip Time - Traffic Characteristics on IP level in uplink and downlink in terms of packet sizes, and temporal characteristics. XR Services and Cloud Gaming based on the initial information documented in TR26.928 including. - Complete collection document traffic characteristics for XR services - Downlink data rate ranges - Uplink data rate ranges - Document Traffic Characteristics for additional relevant XR and other media services. - Document additional developments in the industry that impact traffic characteristics in future networks - Document the applicability of existing 5QIs/PQIs for such services and potentially identify requirements for new 5QIs/PQIs or QoS related parameters. - Communicate with other 3GPP groups and external organizations on relevant aspects related to the study, if necessary - Update TR 26.926 |
| 3GPP SA4 Video SWG Telco (Aug 31, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - agree TR26.926 in version 1.0.0 based on PD - Submission deadline Aug 30, 16:30 CEST. |
| SA#93 (Sep 15 - 17 2021, tbd) |  | - Present TR26.926 in version 1.0.0 for information |
| 3GPP SA4 Video SWG Telco (Sep 28, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline Sep 27, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (Oct 5, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline Oct 4, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (Oct 19, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline Oct 18, 16:30 CEST. |
| 3GPP SA4 Video SWG Telco (Oct 26, 2021, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress development and documentation - Document reference designs for each of the services - Provide suitable simulation models for each of the services - Provide traffic traces - Provide suitable metrics to evaluate the quality of the services - Update TR 26.926 - Submission deadline Oct 25, 16:30 CEST. |
| SA4#116-e (10 – 19 November 2021) |  | - Progress dCR26.925 on different Traffic Models - Agree new TR in version 1.0.0 |
| 3GPP SA4 Video SWG Telco (Nov 30, 2021, 15:30 – 17:30 CET, Host Qualcomm) |  | - Progress TR26.926 - Progress draft CRs to TR26.925 - Submission deadline Nov 29, 16:30 CET. |
| SA#94-e (December 15 - 17 2021) |  | - Present TR26.926 in version 1.0.0 for information |
| 3GPP SA4 Video SWG Telco (Dec 14, 2021, 15:30 – 17:30 CET, Host Qualcomm) |  | - Progress TR26.926 - Progress draft CRs to TR26.925 - Submission deadline Dec 13, 16:30 CET. |
| 3GPP SA4 Video SWG Telco (Jan 11, 2022, 15:30 – 17:30 CET, Host Qualcomm) |  | - Progress TR26.926 - Progress draft CRs to TR26.925 - Submission deadline Jan 10, 16:30 CET. |
| 3GPP SA4 Video SWG Telco (Feb 1, 2022, 15:30 – 17:30 CEST, Host Qualcomm) |  | - Progress TR26.926 - Progress draft CRs to TR26.925 - Submission deadline Feb 28, 16:30 CET. |
| SA4#117-e (E-meeting:14-23 February 2022) |  | - Progress work - Progress TR 26.926 - Communicate with other 3GPP groups and external organizations |
| 3GPP SA4 Video SWG Telco (Mar 8, 2022, 15:30 – 17:30 CET, Host Qualcomm) |  | - Progress work - Progress TR 26.926 - Submission deadline Mar 7, 16:30 CET. |
| SA#95-e (March 16 - 18 2022) |  | - no actions |
| 3GPP SA4 Video SWG Telco (Mar 22, 2022, 15:30 – 17:30 CET, Host Qualcomm) |  | - Progress work - Progress TR 26.926 - Submission deadline Mar 21, 16:30 CET. |
| SA4#118-e (E-meeting: 6-14 April 2022) |  | - Progress CR26.925 on different Traffic Models - Progress TR26.926 - Communicate with other 3GPP groups and external organizations |
| No telcos are planned between SA4#118-e and SA4#119-e |  |  |
| SA4#119-e (E-meeting:11-20 May) | - no progress |  |
| 3GPP SA4 Video SWG Telco (May 31, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline May 30, 16:30 CET. |  |
| 3GPP SA4 Video SWG Telco (June 14, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline June 13, 16:30 CET. |  |
| 3GPP SA4 Video SWG Telco (June 28, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline June 27, 16:30 CET. |  |
| 3GPP SA4 Video SWG Telco (July 12, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline July 11, 16:30 CET. |  |
| SA4#120e (17-26 August, online) | - Progress work - Progress CR26.925 on different Traffic Models - Progress TR 26.926 - Communicate with other 3GPP groups and external organizations |  |
| 3GPP SA4 Video SWG Telco (September 20, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline Sep 19, 16:30 CEST. |  |
| 3GPP SA4 Video SWG Telco (October 11, 2022, 15:30 – 17:30 CEST, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline Oct 10, 16:30 CEST. |  |
| 3GPP SA4 Video SWG Telco (November 2, 2022, 15:30 – 17:30 CET, Host Qualcomm) | - Progress work - Progress TR 26.926 - Submission deadline Oct 31, 16:30 CET. |  |
| SA4#121 (14-18 November, tbd, EU) | - Complete work - Agree CR26.925 on different Traffic Models - Agree new TR in version 2.0.0 - Communicate with other 3GPP groups and external organizations |  |
| SA#98e (Dec 13 - 19 2022, online) | - Present CR26.925 on all Traffic Models and other information for approval - Present TR26.926 in version 2.0.0 for approval |  |